## 00_Start
Rapha Development Profitability Model
የራፋ የግንባታ ፕሮጀክት ትርፋማነት ሞዴል
A · Private residence ¦ B · Commercial project ¦ Excel · LibreOffice · Google Sheets
Plan it, cost it, test it · ያቅዱ፣ ዋጋውን ይወቁ፣ ይፈትሹ
Two tools in one workbook: A – a private-house cost estimate with a home-loan plan; B – a full profitability model for a commercial building. Pick one in step 1, then use that card only.
| STEP 1 · What are you planning? · ምን እያቀዱ ነው? | [5 empty] | helpers
| Choose ▸ | Commercial project – full profitability · የንግድ ፕሮጀክት |  |  |  |  | TRACK | 2
| → Use card B (right). Card A is switched off. | [5 empty] | P_DATA | 2
[7 empty] | PROJECT_MODE | 3
| A · PRIVATE RESIDENCE |  |  | B · COMMERCIAL PROJECT |  |  | DATA_SET | 2
| Cost estimate, cash per month and home-loan plan · የግል ቤት |  |  | Profitability, IFRS statements, loan and lender metrics · የንግድ ፕሮጀክት |  |  | SCEN_SEL | 1
[7 empty] | MODE_NAME | Mixed
| Which data? | 2 – SAMPLE: G+1 family house · ምሳሌ ቤት |  | Project type | 3 – Mixed (sell part, hold part) · ቅይጥ |  | SCEN_NAME | Base
| የትኛውን መረጃ? |  |  | የፕሮጀክት ዓይነት |  |  | UNIT_LBL | ETB '000
|  |  |  | Which data? | 2 – SAMPLE 1: B+G+8 mixed-use · ምሳሌ 1 |  | cf helper | VIABLE
| STATUS · ሁኔታ |  |  | የትኛውን መረጃ? |  |  | cf helper | 0
| Checks passed |  | 12 / 12 | Scenario | 1 – Base · መሠረታዊ |  | cf helper | 0
| Model status |  | ALL CHECKS PASS | ሁኔታ |  |  | cf helper | 0
| Total cost of the house (ETB) |  | 12911120.0914 |  |  |  | cf helper | FALSE
| Monthly instalment (ETB) |  | 72062.1258 | STATUS · ሁኔታ
| Affordability |  | Affordable | Checks passed |  | 25 / 25
| Funding gap (ETB) |  | 0 | Model status |  | ALL CHECKS PASS
|  |  |  | Verdict · ውሳኔ |  | VIABLE · አዋጭ
| GO TO · ወደ |  |  | Total development cost (ETB) |  | 550828221.8186
| ▸ My house – estimate (one page) | የቤት ግምት |  | Equity IRR |  | 27.4%
| ▸ My house – inputs | ግብዓቶች |  | Minimum DSCR |  | 1.7682
| ▸ Calculations & loan schedule | ስሌትና የብድር ሰንጠረዥ
| ▸ Checks | ማረጋገጫዎች |  | GO TO · ወደ
| ▸ Glossary | መዝገበ ቃላት |  | ▸ Dashboard | ▸ Cash flow
|  |  |  | ▸ Inputs | ▸ Loan schedule
|  |  |  | ▸ Space schedule & rent roll | ▸ Returns
|  |  |  | ▸ Scenarios | ▸ Sensitivity & break-even
|  |  |  | ▸ Profit & loss | ▸ Checks
|  |  |  | ▸ Balance sheet | ▸ Tax law register
ALL SHEETS – click to jump · ሁሉም ገጾች
| P1 Inputs | 21 Area |  | 40 PL
| P2 Calc | 22 Capex |  | 41 BS
| P3 Estimate | 23 Construction |  | 42 CF
| P4 Checks | 24 Revenue |  | 43 Ratios
| 01 Dashboard | 25 Opex |  | 50 Returns
| 10 Inputs | 26 Assets |  | 51 Payback
| 11 Scenarios | 27 Loan |  | 52 Sensitivity
| 12 TaxLaw | 28 Tax |  | 60 Checks
| 13 Spaces | 29 VAT |  | 61 Glossary
| 20 Timeline | 30 WorkingCap
HOW TO USE · አጠቃቀም
1 | Step 1: choose Private residence or Commercial project. Only the matching card is active.
ደረጃ 1፡ የግል መኖሪያ ቤት ወይም የንግድ ፕሮጀክት ይምረጡ።
2 | Private: pick 'My house', type your values in column E of P1 Inputs, then open the Estimate.
ለግል ቤት፡ 'የእኔ ቤት'ን ይምረጡ፣ በP1 ዓምድ E ላይ ይጻፉ፣ ከዚያ ግምቱን ይክፈቱ።
3 | Commercial: pick the project type and 'My project', fill 10 Inputs (column E) and 13 Spaces (top block).
ለንግድ ፕሮጀክት፡ ዓይነቱንና 'የእኔ ፕሮጀክት'ን ይምረጡ፣ ገጽ 10 እና 13ን ይሙሉ።
4 | Read the status box (all checks must pass), then the Dashboard. Stress-test with scenarios and the dials on 52.
የማረጋገጫ ሳጥኑን ይመልከቱ፣ ከዚያ ዳሽቦርዱን፤ በሁኔታዎችና በገጽ 52 ይፈትሹ።
| COLOUR CODE · የቀለም ኮድ |  |  | GOOGLE SHEETS · ጉግል ሺትስ
| Input – type here | ግብዓት – እዚህ ይጻፉ |  | Upload the .xlsx to Google Drive → right-click → Open with → Google Sheets (or File → Save as Google Sheets).
| Formula – do not overwrite | ቀመር – አይጻፉበት |  | Every link on this page and every '◂ Start' / 'Dashboard ▸' link in the sheet headers jumps to its sheet.
| Link from another sheet | ከሌላ ገጽ ማገናኛ |  | Dropdowns, checks, charts and the sensitivity sheet all recalculate live – no macros, no Data Tables.
| Key output / check | ቁልፍ ውጤት / ማረጋገጫ |  | File → Settings → Calculation: leave 'Iterative calculation' OFF (the model has no circular references).
METHOD NOTES
No circularity: interest during construction (IDC) is built month by month on the opening balance plus draws; the arrangement fee is charged on a facility base that excludes IDC; undistributed-profits tax uses a closed form.
Commercial timeline: construction monthly (up to 48 months) rolled up to C1–C4; operations O1–O10 annually; returns use dated cash flows (XIRR). Private track: 48 construction months plus a 240-month loan schedule.
IFRS: IAS 2 units for sale, IAS 40 let space (cost model), IAS 16 owner-held, IAS 23 capitalised borrowing cost, IFRS 15 sales, IFRS 16 rent, IAS 12 tax, IAS 36 impairment test, IAS 7 indirect cash flow.
Disclaimer: a planning tool only – not investment, tax or legal advice. Confirm tax rates (sheet 12) before use.
ማሳሰቢያ፡ ይህ የዕቅድ መሣሪያ ብቻ ነው፤ የኢንቨስትመንት፣ የግብር ወይም የሕግ ምክር አይደለም።

## P1_Inputs
P1 · My house – inputs | [6 empty] | ◂ Start
የግል መኖሪያ ቤት – ግብዓቶች | [6 empty] | Estimate ▸
SAMPLE — G+1 family house, Addis Ababa ¦ Private residence – cost estimate & home loan
Input | ግብዓት | Unit | MY HOUSE (your values) | SAMPLE G+1 house | ACTIVE (used) | Range name | Notes
Type your own values in column E (blue on amber). Column G uses the data set chosen on the Start sheet (1 = My house, 2 = Sample). The sample is an example only – "Sample value — not market advice".
1. Your house | 1. ቤትዎ
Project name | የፕሮጀክት ስም | text | My house | SAMPLE — G+1 family house, Addis Ababa | SAMPLE — G+1 family house, Addis Ababa | P_NAME | Shown on the estimate
Location (sub-city / town) | አካባቢ | text |  | Addis Ababa – Bole sub-city | Addis Ababa – Bole sub-city | P_LOCATION
Location class for cost factor | የቦታ ዓይነት | list | Addis Ababa | Addis Ababa | 1 | P_LOC_TYPE | Regional towns use a lower location factor
Plot area | የቦታ ስፋት | m² | 0 | 300 | 300 | P_PLOT | From your title deed
Construction start date | የግንባታ መጀመሪያ ቀን | date | 2027-01-01 | 2027-01-01 | 2027-01-01 | P_START | Budget date for prices
Construction period | የግንባታ ጊዜ | months | 12 | 14 | 14 | P_MONTHS | 1–48 months
Building type | የሕንፃው ዓይነት | list | G+1 | G+1 | 2 | P_BTYPE | Checked against the floors below
Finish level | የማጠናቀቂያ ደረጃ | list | Standard | Standard | 2 | P_FINISH | Selects the cost-library column
Basement? | ምድር ቤት አለው? | Y/N | No | No | 0 | P_BASE_YN | Checked against the floors below
2. Gross floor area (incl. walls and stairs) | 2. ጠቅላላ የወለል ስፋት
Basement – gross area | ምድር ቤት – ጠቅላላ ስፋት | m² | 0 | 0 | 0 | P_FL1
Ground floor – gross area | ምድር ወለል – ጠቅላላ ስፋት | m² | 0 | 130 | 130 | P_FL2
Floor 1 – gross area | 1ኛ ፎቅ – ጠቅላላ ስፋት | m² | 0 | 120 | 120 | P_FL3
Floor 2 – gross area | 2ኛ ፎቅ – ጠቅላላ ስፋት | m² | 0 | 0 | 0 | P_FL4
Floor 3 – gross area | 3ኛ ፎቅ – ጠቅላላ ስፋት | m² | 0 | 0 | 0 | P_FL5
3. Construction extras and fees | 3. ተጨማሪ ሥራዎችና ክፍያዎች
Basement extra (excavation, retaining walls) | የምድር ቤት ተጨማሪ | ETB/m² | 10000 | 10000 | 10000 | P_BASE_RATE | Applied to basement area
Compound wall? | የአጥር ግንብ? | Y/N | No | Yes | 1 | P_COMP_YN
Compound wall length | የአጥር ርዝመት | m | 0 | 70 | 70 | P_COMP_LEN
Compound wall rate (incl. gate) | የአጥር ዋጋ በሜትር | ETB/m | 18000 | 18000 | 18000 | P_COMP_RATE
Septic tank? | የፍሳሽ ጉድጓድ? | Y/N | No | Yes | 1 | P_SEPT_YN | Not needed where sewer exists
Septic tank cost | የፍሳሽ ጉድጓድ ዋጋ | ETB | 450000 | 450000 | 450000 | P_SEPT_RATE
Water tanks – number | የውሃ ታንከር ብዛት | no. | 0 | 2 | 2 | P_WTANK_QTY
Water tank cost each (stand, pump) | የአንዱ ዋጋ | ETB | 60000 | 60000 | 60000 | P_WTANK_RATE
Paving / garden area | የንጣፍ / የአትክልት ስፋት | m² | 0 | 80 | 80 | P_PAVE_M2
Paving / garden rate | የንጣፍ ዋጋ | ETB/m² | 3500 | 3500 | 3500 | P_PAVE_RATE
Contingency (% of escalated building cost) | ያልተጠበቀ ወጪ መጠባበቂያ | % | 10% | 10% | 10% | P_CONT
Design & permit drawings (% of building cost) | የዲዛይን ክፍያ | % | 4% | 4% | 4% | P_DESIGN | Paid in month 1
Site supervision (% of building cost) | የቁጥጥር ክፍያ | % | 2% | 2% | 2% | P_SUPERV
Building permit & utility connections | ፈቃድና የአገልግሎት ቅጥያ | ETB | 0 | 120000 | 120000 | P_PERMITS | Paid in month 1
Furniture & appliances | የቤት ዕቃዎች | ETB | 0 | 1000000 | 1000000 | P_FURN | Paid in the last month
Price escalation | የዋጋ ጭማሪ | % p.a. | 15% | 15% | 15% | P_ESC | Building prices rise during construction
Spend profile | የወጪ ስርጭት | list | S-curve (sigmoid) | S-curve (sigmoid) | 1 | P_SCURVE
Retention held from contractor | ከኮንትራክተር የሚያዝ | % | 5% | 5% | 5% | P_RETENTION | Paid after the defects period
Retention released – months after completion | የሚለቀቅበት ጊዜ | months | 6 | 6 | 6 | P_RET_M
Estimate range – low side | የግምት ዝቅተኛ ወሰን | % | -10% | -10% | -10% | P_EST_LOW
Estimate range – high side | የግምት ከፍተኛ ወሰን | % | 15% | 15% | 15% | P_EST_HIGH
4. Land | 4. መሬት
Land | መሬት | list | Already owned – no cost | Already owned – no cost | 1 | P_LAND_TYPE
Land / lease payment during construction | የመሬት / የሊዝ ክፍያ | ETB | 0 | 0 | 0 | P_LAND_COST | Paid in month 1 when land type = Buying
5. Funding | 5. የገንዘብ ምንጭ
Own savings available | የራስ ቁጠባ | ETB | 0 | 5000000 | 5000000 | P_SAVINGS | Used first
Family / diaspora contributions | የቤተሰብ / ዳያስፖራ መዋጮ | ETB | 0 | 2500000 | 2500000 | P_FAMILY | Used after savings
Home loan – maximum the bank will lend | ከፍተኛ የቤት ብድር | ETB | 0 | 7000000 | 7000000 | P_LOAN_MAX | Used last
Home loan interest rate | የብድር ወለድ | % p.a. | 14% | 14% | 14% | P_RATE | Verify the bank offer
Repayment period after completion | የመክፈያ ጊዜ | years | 15 | 15 | 15 | P_TENOR | Max 20
Grace period after completion (interest only) | የእፎይታ ጊዜ | months | 0 | 0 | 0 | P_GRACE
Interest while building | በግንባታ ወቅት ወለድ | list | Capitalised into the loan | Capitalised into the loan | 2 | P_IDC | Paid monthly = you pay it from income; Capitalised = added to the loan
Loan arrangement fee (% of loan limit) | የብድር ማመቻቻ ክፍያ | % | 1% | 1% | 1% | P_ARR | Paid in month 1
6. Affordability | 6. የመክፈል አቅም
Household monthly net income | የቤተሰብ ወርሃዊ የተጣራ ገቢ | ETB/month | 0 | 300000 | 300000 | P_INCOME | All earners, after tax
Other monthly loan payments | ሌሎች ወርሃዊ የብድር ክፍያዎች | ETB/month | 0 | 0 | 0 | P_OTHER_DEBT
Max total debt payments as % of income | ከገቢ ከፍተኛ የክፍያ ድርሻ | % | 35% | 35% | 35% | P_AFF_MAX | Typical bank rule 30–40%
7. Optional: rent out part of the house | 7. አማራጭ፡ ከፊሉን ማከራየት
Rent out part of the house? | ከፊሉን ያከራያሉ? | Y/N | No | Yes | 1 | P_RENT_YN
Area rented out | የሚከራየው ስፋት | m² | 0 | 60 | 60 | P_RENT_AREA | e.g. ground-floor unit
Monthly rent (today's prices) | ወርሃዊ ኪራይ | ETB/month | 0 | 25000 | 25000 | P_RENT_M
Rent increase per year | የኪራይ ጭማሪ | % p.a. | 8% | 8% | 8% | P_RENT_ESC
Months empty per year (vacancy) | ባዶ የሚሆንባቸው ወራት | % | 8% | 8% | 8% | P_VACANCY | ≈ 1 month a year
Running costs & rental income tax (% of rent) | ወጪና የኪራይ ገቢ ግብር | % | 20% | 20% | 20% | P_RENT_COST | Repairs, cleaning, schedule-B rental income tax – verify
8. Cost library for houses – ETB per m² gross, budget-date prices | 8. የቤት ግንባታ ወጪ መረጃ
|  |  | Basic | Standard | Premium |  | Applies to both data sets. Update with current local prices.
Preliminaries & site set-up | ቅድመ-ሥራዎች | ETB/m² | 900 | 1100 | 1400 | P_LIB
Foundation / substructure | የመሠረት ሥራ | ETB/m² | 3200 | 3500 | 3900 | P_LIB
Frame (columns, beams, slabs) | ፍሬም (ኮለን፣ ቢም፣ ስላብ) | ETB/m² | 6200 | 6800 | 7400 | P_LIB
Walls, windows & roof | ግድግዳ፣ መስኮትና ጣሪያ | ETB/m² | 3600 | 4500 | 6200 | P_LIB
Internal walls & doors | የውስጥ ግድግዳና በሮች | ETB/m² | 1600 | 2200 | 3200 | P_LIB
Finishes (floor, plaster, paint, tiles) | ማጠናቀቂያ (ወለል፣ ልስን፣ ቀለም፣ ሴራሚክ) | ETB/m² | 3000 | 5200 | 8800 | P_LIB
Electrical, plumbing & sanitary | ኤሌክትሪክ፣ ቧንቧና ንፅህና | ETB/m² | 2600 | 3800 | 5800 | P_LIB
Kitchen & built-in cabinets | ማዕድ ቤትና ቁም ሣጥኖች | ETB/m² | 600 | 1100 | 2200 | P_LIB
Total library rate |  |  | 21700 | 28200 | 38900
Location factor – Addis Ababa |  | x | 1 |  |  | P_LOCF_ADDIS | Base = 1.00
Location factor – regional town |  | x | 0.92 |  |  | P_LOCF_REG | Lower labour cost, higher transport
Formulas:
ACTIVE (used) = CHOOSE(P_DATA,[MY HOUSE (your values)],[SAMPLE G+1 house])
Note on F12: Sample value — not market advice
Note on F13: Sample value — not market advice
Note on F14: Sample value — not market advice
Note on F15: Sample value — not market advice
Note on F16: Sample value — not market advice
Note on F17: Sample value — not market advice
Note on F18: Sample value — not market advice
Note on F21: Sample value — not market advice
Note on F22: Sample value — not market advice
Note on F26: Sample value — not market advice
Note on F27: Sample value — not market advice
Note on F28: Sample value — not market advice
Note on F29: Sample value — not market advice
Note on F30: Sample value — not market advice
Note on F31: Sample value — not market advice
Note on F32: Sample value — not market advice
Note on F33: Sample value — not market advice
Note on F34: Sample value — not market advice
Note on F35: Sample value — not market advice
Note on F36: Sample value — not market advice
Note on F37: Sample value — not market advice
Note on F38: Sample value — not market advice
Note on F39: Sample value — not market advice
Note on F40: Sample value — not market advice
Note on F41: Sample value — not market advice
Note on F42: Sample value — not market advice
Note on F43: Sample value — not market advice
Note on F44: Sample value — not market advice
Note on F45: Sample value — not market advice
Note on F46: Sample value — not market advice
Note on F48: Sample value — not market advice
Note on F51: Sample value — not market advice
Note on F52: Sample value — not market advice
Note on F53: Sample value — not market advice
Note on F54: Sample value — not market advice
Note on F55: Sample value — not market advice
Note on F57: Sample value — not market advice
Note on F58: Sample value — not market advice
Note on F60: Sample value — not market advice
Note on F62: Sample value — not market advice
Note on F64: Sample value — not market advice
Note on F65: Sample value — not market advice
Note on F66: Sample value — not market advice
Note on F67: Sample value — not market advice
Note on F68: Sample value — not market advice
Note on F69: Sample value — not market advice
Note on E73: Sample value — not market advice
Note on F73: Sample value — not market advice
Note on G73: Sample value — not market advice
Note on E74: Sample value — not market advice
Note on F74: Sample value — not market advice
Note on G74: Sample value — not market advice
Note on E75: Sample value — not market advice
Note on F75: Sample value — not market advice
Note on G75: Sample value — not market advice
Note on E76: Sample value — not market advice
Note on F76: Sample value — not market advice
Note on G76: Sample value — not market advice
Note on E77: Sample value — not market advice
Note on F77: Sample value — not market advice
Note on G77: Sample value — not market advice
Note on E78: Sample value — not market advice
Note on F78: Sample value — not market advice
Note on G78: Sample value — not market advice
Note on E79: Sample value — not market advice
Note on F79: Sample value — not market advice
Note on G79: Sample value — not market advice
Note on E80: Sample value — not market advice
Note on F80: Sample value — not market advice
Note on G80: Sample value — not market advice

## P2_Calc
P2 · My house – calculations | [13 empty] | ◂ Start
የቤት ወጪ፣ የገንዘብ ምንጭና የብድር ስሌት | [13 empty] | Estimate ▸
SAMPLE — G+1 family house, Addis Ababa ¦ Private residence – cost estimate & home loan
Building summary | የሕንፃ ማጠቃለያ
Gross floor area | m² | 250
Basement area | m² | 0
Above-ground floors built | no. | 2
Configuration found |  | G+1
Building type matches floors (1 = yes) | flag | 1
Location factor | x | 1
Building cost at today's prices (library rate × area × location) | የሕንፃ ወጪ በዛሬ ዋጋ
Preliminaries & site set-up · ቅድመ-ሥራዎች | ETB | 275000
Foundation / substructure · የመሠረት ሥራ | ETB | 875000
Frame (columns, beams, slabs) · ፍሬም (ኮለን፣ ቢም፣ ስላብ) | ETB | 1700000
Walls, windows & roof · ግድግዳ፣ መስኮትና ጣሪያ | ETB | 1125000
Internal walls & doors · የውስጥ ግድግዳና በሮች | ETB | 550000
Finishes (floor, plaster, paint, tiles) · ማጠናቀቂያ (ወለል፣ ልስን፣ ቀለም፣ ሴራሚክ) | ETB | 1300000
Electrical, plumbing & sanitary · ኤሌክትሪክ፣ ቧንቧና ንፅህና | ETB | 950000
Kitchen & built-in cabinets · ማዕድ ቤትና ቁም ሣጥኖች | ETB | 275000
Basement extra | ETB | 0
Compound wall | ETB | 1260000
Septic tank | ETB | 450000
Water tanks | ETB | 120000
Paving / garden | ETB | 280000
External works (wall + septic + tanks + paving) | ETB | 2110000
BUILDING COST AT TODAY'S PRICES | ETB | 9160000
Month by month (columns = construction months) | ወር በወር
Month |  | Total | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36 | M37 | M38 | M39 | M40 | M41 | M42 | M43 | M44 | M45 | M46 | M47 | M48
Month number | no. |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
Month starting | date | time axis 2027-01-01 to 2030-12-01
Construction month (1 = yes) | flag | 14 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative progress | % |  | 0.5882% | 2.703% | 6.923% | 13.79% | 23.58% | 36% | 50% | 64% | 76.42% | 86.21% | 93.08% | 97.3% | 99.41% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Work done this month | % | 100% | 0.5882% | 2.114% | 4.22% | 6.87% | 9.792% | 12.42% | 14% | 14% | 12.42% | 9.792% | 6.87% | 4.22% | 2.114% | 0.5882% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Price escalation factor | x |  | 1.0058 | 1.0176 | 1.0295 | 1.0416 | 1.0538 | 1.0662 | 1.0786 | 1.0913 | 1.1041 | 1.117 | 1.1301 | 1.1433 | 1.1567 | 1.1703 | 1.184 | 1.1978 | 1.2119 | 1.2261 | 1.2404 | 1.255 | 1.2697 | 1.2845 | 1.2996 | 1.3148 | 1.3302 | 1.3458 | 1.3616 | 1.3775 | 1.3937 | 1.41 | 1.4265 | 1.4432 | 1.4601 | 1.4772 | 1.4945 | 1.512 | 1.5298 | 1.5477 | 1.5658 | 1.5842 | 1.6027 | 1.6215 | 1.6405 | 1.6597 | 1.6791 | 1.6988 | 1.7187 | 1.7389
Building work (incl. price rises) | ETB | 9942815.0004 | 54197.0476 | 197098.6725 | 398008.0157 | 655476.9501 | 945191.4757 | 1212454.1969 | 1383252.6351 | 1399457.3248 | 1255566.7358 | 1001868.1332 | 711155.3767 | 441992.8041 | 224038.8766 | 63056.7558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingency | ETB | 994281.5 | 5419.7048 | 19709.8673 | 39800.8016 | 65547.695 | 94519.1476 | 121245.4197 | 138325.2635 | 139945.7325 | 125556.6736 | 100186.8133 | 71115.5377 | 44199.2804 | 22403.8877 | 6305.6756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design & drawings | ETB | 366400 | 366400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Site supervision | ETB | 198856.3 | 1083.941 | 3941.9735 | 7960.1603 | 13109.539 | 18903.8295 | 24249.0839 | 27665.0527 | 27989.1465 | 25111.3347 | 20037.3627 | 14223.1075 | 8839.8561 | 4480.7775 | 1261.1351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Permits & connections | ETB | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Furniture & appliances | ETB | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Land / lease payment | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan arrangement fee | ETB | 70000 | 70000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL COST THIS MONTH (excl. interest) | ETB | 12692352.8005 | 617100.6933 | 220750.5132 | 445768.9775 | 734134.1841 | 1058614.4527 | 1357948.7006 | 1549242.9513 | 1567392.2037 | 1406234.7441 | 1122092.3092 | 796494.0219 | 495031.9406 | 250923.5417 | 1070623.5664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention held back from contractor | ETB | 497140.75 | 2709.8524 | 9854.9336 | 19900.4008 | 32773.8475 | 47259.5738 | 60622.7098 | 69162.6318 | 69972.8662 | 62778.3368 | 50093.4067 | 35557.7688 | 22099.6402 | 11201.9438 | 3152.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention set aside at handover | ETB | 497140.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 497140.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CASH NEEDED THIS MONTH | ETB | 12692352.8005 | 614390.8409 | 210895.5796 | 425868.5768 | 701360.3366 | 1011354.879 | 1297325.9907 | 1480080.3195 | 1497419.3375 | 1343456.4073 | 1071998.9025 | 760936.253 | 472932.3004 | 239721.5979 | 1564611.4787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Who pays: savings → family → home loan → gap | ማን ይከፍላል
(1) Own savings | ETB | 5000000 | 614390.8409 | 210895.5796 | 425868.5768 | 701360.3366 | 1011354.879 | 1297325.9907 | 738803.7964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(2) Family / diaspora | ETB | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 741276.5231 | 1497419.3375 | 261304.1394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(3) Home loan draw | ETB | 5192352.8005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1082152.2679 | 1071998.9025 | 760936.253 | 472932.3004 | 239721.5979 | 1564611.4787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(4) Still to find (funding gap) | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative savings used | ETB | 5000000 | 614390.8409 | 825286.4205 | 1251154.9973 | 1952515.3339 | 2963870.2129 | 4261196.2036 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
Cumulative family money used | ETB | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 741276.5231 | 2238695.8606 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
Cumulative loan drawn | ETB | 5192352.8005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1082152.2679 | 2154151.1704 | 2915087.4234 | 3388019.7239 | 3627741.3218 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005 | 5192352.8005
Check: sources − cash needed | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Home loan while building | በግንባታ ወቅት ብድር
Opening loan balance | ETB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1094777.3777 | 2192055.3368 | 2987443.1584 | 3500746.5058 | 3784106.8983 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914
Interest for the month | ETB | 218767.2909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12625.1098 | 25279.0566 | 34451.5685 | 40371.047 | 43638.7945 | 62401.7144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest added to the loan | ETB | 218767.2909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12625.1098 | 25279.0566 | 34451.5685 | 40371.047 | 43638.7945 | 62401.7144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest you pay from income | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closing loan balance | ETB | 5411120.0914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1094777.3777 | 2192055.3368 | 2987443.1584 | 3500746.5058 | 3784106.8983 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914 | 5411120.0914
Totals | ድምር
Building work incl. price rises | ETB | 9942815.0004
Contingency | ETB | 994281.5
Design | ETB | 366400
Supervision | ETB | 198856.3
Permits | ETB | 120000
Furniture | ETB | 1000000
Land | ETB | 0
Arrangement fee | ETB | 70000
Interest while building (capitalised + paid) | ETB | 218767.2909
of which added to the loan | ETB | 218767.2909
Highest monthly interest paid from income while building | ETB | 0
Retention (paid after the defects period) | ETB | 497140.75
CONSTRUCTION COST (building, contingency, fees, furniture) | ETB | 12622352.8005
TOTAL COST OF THE HOUSE (incl. land, loan fees & interest while building) | ETB | 12911120.0914
Construction cost per m² gross | ETB/m² | 50489.4112
Low estimate (construction cost) | ETB | 11360117.5204
High estimate (construction cost) | ETB | 14515705.7205
Cash needed in total | ETB | 12692352.8005
Savings used | ETB | 5000000
Family money used | ETB | 2500000
Loan drawn | ETB | 5192352.8005
Funding gap | ETB | 0
Peak month of spending | ETB | 1564611.4787
Check: sources − uses | ETB | 0
Loan balance at completion | ETB | 5411120.0914
Cost breakdown (sums to total cost) | የወጪ ክፍፍል
Foundation & basement | ETB | 875000
Frame, walls & roof | ETB | 2825000
Internal walls, finishes & kitchen | ETB | 2125000
Electrical & plumbing | ETB | 950000
Site set-up & external works | ETB | 2385000
Price rises & contingency | ETB | 1777096.5005
Design, supervision & permits | ETB | 685256.3
Furniture & appliances | ETB | 1000000
Land | ETB | 0
Loan fee & interest while building | ETB | 288767.2909
Total (= total cost) | ETB | 12911120.0914
Paying the contractor – stages (building work incl. price rises & contingency) | ለኮንትራክተር የክፍያ ደረጃዎች
1 Mobilisation & site set-up | ETB | 328351.6962
2 Foundation | ETB | 1044755.3972
3 Frame (columns, beams, slabs) | ETB | 2029810.4859
4 Walls, windows & roof | ETB | 1343256.9392
5 Electrical, plumbing & internal walls | ETB | 1791009.2523
6 Finishes, kitchen & external works | ETB | 4399912.7297
Total contractor payments | ETB | 10937096.5005
Home-loan schedule after completion (one row per month) | ከግንባታ በኋላ የብድር ክፍያ ሰንጠረዥ (በወር)
Monthly payments after the grace period | no. | 180
Monthly instalment (after grace) | ETB | 72062.1258
Monthly interest-only payment during grace | ETB | 63129.7344
Loan repaid by | date | 2043-02-28
Debt payments ÷ income | % | 24.02%
Affordability |  | Affordable
ውሳኔ |  | ይቻላል
Largest loan the income supports (at the max %) | ETB | 7884413.6674
Month after completion | Date | Loan year | 2027-01-01: Opening balance; 2027-02-01: Interest; 2027-03-01: Payment; 2027-04-01: Principal; 2027-05-01: Closing balance
1 | 2028-03-01 | 1 | 2027-01-01: 5411120.0914; 2027-02-01: 63129.7344; 2027-03-01: 72062.1258; 2027-04-01: 8932.3914; 2027-05-01: 5402187.7
2 | 2028-04-01 | 1 | 2027-01-01: 5402187.7; 2027-02-01: 63025.5232; 2027-03-01: 72062.1258; 2027-04-01: 9036.6026; 2027-05-01: 5393151.0973
3 | 2028-05-01 | 1 | 2027-01-01: 5393151.0973; 2027-02-01: 62920.0961; 2027-03-01: 72062.1258; 2027-04-01: 9142.0297; 2027-05-01: 5384009.0677
4 | 2028-06-01 | 1 | 2027-01-01: 5384009.0677; 2027-02-01: 62813.4391; 2027-03-01: 72062.1258; 2027-04-01: 9248.6867; 2027-05-01: 5374760.381
5 | 2028-07-01 | 1 | 2027-01-01: 5374760.381; 2027-02-01: 62705.5378; 2027-03-01: 72062.1258; 2027-04-01: 9356.588; 2027-05-01: 5365403.7929
6 | 2028-08-01 | 1 | 2027-01-01: 5365403.7929; 2027-02-01: 62596.3776; 2027-03-01: 72062.1258; 2027-04-01: 9465.7482; 2027-05-01: 5355938.0447
7 | 2028-09-01 | 1 | 2027-01-01: 5355938.0447; 2027-02-01: 62485.9439; 2027-03-01: 72062.1258; 2027-04-01: 9576.1819; 2027-05-01: 5346361.8628
8 | 2028-10-01 | 1 | 2027-01-01: 5346361.8628; 2027-02-01: 62374.2217; 2027-03-01: 72062.1258; 2027-04-01: 9687.9041; 2027-05-01: 5336673.9587
9 | 2028-11-01 | 1 | 2027-01-01: 5336673.9587; 2027-02-01: 62261.1962; 2027-03-01: 72062.1258; 2027-04-01: 9800.9296; 2027-05-01: 5326873.0291
10 | 2028-12-01 | 1 | 2027-01-01: 5326873.0291; 2027-02-01: 62146.852; 2027-03-01: 72062.1258; 2027-04-01: 9915.2738; 2027-05-01: 5316957.7553
11 | 2029-01-01 | 1 | 2027-01-01: 5316957.7553; 2027-02-01: 62031.1738; 2027-03-01: 72062.1258; 2027-04-01: 10030.952; 2027-05-01: 5306926.8033
12 | 2029-02-01 | 1 | 2027-01-01: 5306926.8033; 2027-02-01: 61914.146; 2027-03-01: 72062.1258; 2027-04-01: 10147.9798; 2027-05-01: 5296778.8235
13 | 2029-03-01 | 2 | 2027-01-01: 5296778.8235; 2027-02-01: 61795.7529; 2027-03-01: 72062.1258; 2027-04-01: 10266.3729; 2027-05-01: 5286512.4507
14 | 2029-04-01 | 2 | 2027-01-01: 5286512.4507; 2027-02-01: 61675.9786; 2027-03-01: 72062.1258; 2027-04-01: 10386.1472; 2027-05-01: 5276126.3035
15 | 2029-05-01 | 2 | 2027-01-01: 5276126.3035; 2027-02-01: 61554.8069; 2027-03-01: 72062.1258; 2027-04-01: 10507.3189; 2027-05-01: 5265618.9845
16 | 2029-06-01 | 2 | 2027-01-01: 5265618.9845; 2027-02-01: 61432.2215; 2027-03-01: 72062.1258; 2027-04-01: 10629.9043; 2027-05-01: 5254989.0802
17 | 2029-07-01 | 2 | 2027-01-01: 5254989.0802; 2027-02-01: 61308.2059; 2027-03-01: 72062.1258; 2027-04-01: 10753.9199; 2027-05-01: 5244235.1603
18 | 2029-08-01 | 2 | 2027-01-01: 5244235.1603; 2027-02-01: 61182.7435; 2027-03-01: 72062.1258; 2027-04-01: 10879.3823; 2027-05-01: 5233355.7781
19 | 2029-09-01 | 2 | 2027-01-01: 5233355.7781; 2027-02-01: 61055.8174; 2027-03-01: 72062.1258; 2027-04-01: 11006.3084; 2027-05-01: 5222349.4697
20 | 2029-10-01 | 2 | 2027-01-01: 5222349.4697; 2027-02-01: 60927.4105; 2027-03-01: 72062.1258; 2027-04-01: 11134.7153; 2027-05-01: 5211214.7544
21 | 2029-11-01 | 2 | 2027-01-01: 5211214.7544; 2027-02-01: 60797.5055; 2027-03-01: 72062.1258; 2027-04-01: 11264.6203; 2027-05-01: 5199950.134
22 | 2029-12-01 | 2 | 2027-01-01: 5199950.134; 2027-02-01: 60666.0849; 2027-03-01: 72062.1258; 2027-04-01: 11396.0409; 2027-05-01: 5188554.0931
23 | 2030-01-01 | 2 | 2027-01-01: 5188554.0931; 2027-02-01: 60533.1311; 2027-03-01: 72062.1258; 2027-04-01: 11528.9947; 2027-05-01: 5177025.0984
24 | 2030-02-01 | 2 | 2027-01-01: 5177025.0984; 2027-02-01: 60398.6261; 2027-03-01: 72062.1258; 2027-04-01: 11663.4997; 2027-05-01: 5165361.5987
25 | 2030-03-01 | 3 | 2027-01-01: 5165361.5987; 2027-02-01: 60262.552; 2027-03-01: 72062.1258; 2027-04-01: 11799.5738; 2027-05-01: 5153562.0249
26 | 2030-04-01 | 3 | 2027-01-01: 5153562.0249; 2027-02-01: 60124.8903; 2027-03-01: 72062.1258; 2027-04-01: 11937.2355; 2027-05-01: 5141624.7894
27 | 2030-05-01 | 3 | 2027-01-01: 5141624.7894; 2027-02-01: 59985.6225; 2027-03-01: 72062.1258; 2027-04-01: 12076.5033; 2027-05-01: 5129548.2861
28 | 2030-06-01 | 3 | 2027-01-01: 5129548.2861; 2027-02-01: 59844.73; 2027-03-01: 72062.1258; 2027-04-01: 12217.3958; 2027-05-01: 5117330.8903
29 | 2030-07-01 | 3 | 2027-01-01: 5117330.8903; 2027-02-01: 59702.1937; 2027-03-01: 72062.1258; 2027-04-01: 12359.9321; 2027-05-01: 5104970.9583
30 | 2030-08-01 | 3 | 2027-01-01: 5104970.9583; 2027-02-01: 59557.9945; 2027-03-01: 72062.1258; 2027-04-01: 12504.1313; 2027-05-01: 5092466.827
31 | 2030-09-01 | 3 | 2027-01-01: 5092466.827; 2027-02-01: 59412.113; 2027-03-01: 72062.1258; 2027-04-01: 12650.0128; 2027-05-01: 5079816.8141
32 | 2030-10-01 | 3 | 2027-01-01: 5079816.8141; 2027-02-01: 59264.5295; 2027-03-01: 72062.1258; 2027-04-01: 12797.5963; 2027-05-01: 5067019.2178
33 | 2030-11-01 | 3 | 2027-01-01: 5067019.2178; 2027-02-01: 59115.2242; 2027-03-01: 72062.1258; 2027-04-01: 12946.9016; 2027-05-01: 5054072.3162
34 | 2030-12-01 | 3 | 2027-01-01: 5054072.3162; 2027-02-01: 58964.177; 2027-03-01: 72062.1258; 2027-04-01: 13097.9488; 2027-05-01: 5040974.3675
35 | 2031-01-01 | 3 | 2027-01-01: 5040974.3675; 2027-02-01: 58811.3676; 2027-03-01: 72062.1258; 2027-04-01: 13250.7582; 2027-05-01: 5027723.6093
36 | 2031-02-01 | 3 | 2027-01-01: 5027723.6093; 2027-02-01: 58656.7754; 2027-03-01: 72062.1258; 2027-04-01: 13405.3504; 2027-05-01: 5014318.2589
37 | 2031-03-01 | 4 | 2027-01-01: 5014318.2589; 2027-02-01: 58500.3797; 2027-03-01: 72062.1258; 2027-04-01: 13561.7461; 2027-05-01: 5000756.5128
38 | 2031-04-01 | 4 | 2027-01-01: 5000756.5128; 2027-02-01: 58342.1593; 2027-03-01: 72062.1258; 2027-04-01: 13719.9665; 2027-05-01: 4987036.5463
39 | 2031-05-01 | 4 | 2027-01-01: 4987036.5463; 2027-02-01: 58182.093; 2027-03-01: 72062.1258; 2027-04-01: 13880.0328; 2027-05-01: 4973156.5135
40 | 2031-06-01 | 4 | 2027-01-01: 4973156.5135; 2027-02-01: 58020.1593; 2027-03-01: 72062.1258; 2027-04-01: 14041.9665; 2027-05-01: 4959114.5471
41 | 2031-07-01 | 4 | 2027-01-01: 4959114.5471; 2027-02-01: 57856.3364; 2027-03-01: 72062.1258; 2027-04-01: 14205.7894; 2027-05-01: 4944908.7576
42 | 2031-08-01 | 4 | 2027-01-01: 4944908.7576; 2027-02-01: 57690.6022; 2027-03-01: 72062.1258; 2027-04-01: 14371.5236; 2027-05-01: 4930537.234
43 | 2031-09-01 | 4 | 2027-01-01: 4930537.234; 2027-02-01: 57522.9344; 2027-03-01: 72062.1258; 2027-04-01: 14539.1914; 2027-05-01: 4915998.0426
44 | 2031-10-01 | 4 | 2027-01-01: 4915998.0426; 2027-02-01: 57353.3105; 2027-03-01: 72062.1258; 2027-04-01: 14708.8153; 2027-05-01: 4901289.2273
45 | 2031-11-01 | 4 | 2027-01-01: 4901289.2273; 2027-02-01: 57181.7077; 2027-03-01: 72062.1258; 2027-04-01: 14880.4182; 2027-05-01: 4886408.8091
46 | 2031-12-01 | 4 | 2027-01-01: 4886408.8091; 2027-02-01: 57008.1028; 2027-03-01: 72062.1258; 2027-04-01: 15054.023; 2027-05-01: 4871354.7861
47 | 2032-01-01 | 4 | 2027-01-01: 4871354.7861; 2027-02-01: 56832.4725; 2027-03-01: 72062.1258; 2027-04-01: 15229.6533; 2027-05-01: 4856125.1328
48 | 2032-02-01 | 4 | 2027-01-01: 4856125.1328; 2027-02-01: 56654.7932; 2027-03-01: 72062.1258; 2027-04-01: 15407.3326; 2027-05-01: 4840717.8002
49 | 2032-03-01 | 5 | 2027-01-01: 4840717.8002; 2027-02-01: 56475.041; 2027-03-01: 72062.1258; 2027-04-01: 15587.0848; 2027-05-01: 4825130.7154
50 | 2032-04-01 | 5 | 2027-01-01: 4825130.7154; 2027-02-01: 56293.1917; 2027-03-01: 72062.1258; 2027-04-01: 15768.9341; 2027-05-01: 4809361.7813
51 | 2032-05-01 | 5 | 2027-01-01: 4809361.7813; 2027-02-01: 56109.2208; 2027-03-01: 72062.1258; 2027-04-01: 15952.905; 2027-05-01: 4793408.8763
52 | 2032-06-01 | 5 | 2027-01-01: 4793408.8763; 2027-02-01: 55923.1036; 2027-03-01: 72062.1258; 2027-04-01: 16139.0222; 2027-05-01: 4777269.854
53 | 2032-07-01 | 5 | 2027-01-01: 4777269.854; 2027-02-01: 55734.815; 2027-03-01: 72062.1258; 2027-04-01: 16327.3108; 2027-05-01: 4760942.5432
54 | 2032-08-01 | 5 | 2027-01-01: 4760942.5432; 2027-02-01: 55544.3297; 2027-03-01: 72062.1258; 2027-04-01: 16517.7961; 2027-05-01: 4744424.747
55 | 2032-09-01 | 5 | 2027-01-01: 4744424.747; 2027-02-01: 55351.622; 2027-03-01: 72062.1258; 2027-04-01: 16710.5038; 2027-05-01: 4727714.2433
56 | 2032-10-01 | 5 | 2027-01-01: 4727714.2433; 2027-02-01: 55156.6662; 2027-03-01: 72062.1258; 2027-04-01: 16905.4596; 2027-05-01: 4710808.7837
57 | 2032-11-01 | 5 | 2027-01-01: 4710808.7837; 2027-02-01: 54959.4358; 2027-03-01: 72062.1258; 2027-04-01: 17102.69; 2027-05-01: 4693706.0937
58 | 2032-12-01 | 5 | 2027-01-01: 4693706.0937; 2027-02-01: 54759.9044; 2027-03-01: 72062.1258; 2027-04-01: 17302.2214; 2027-05-01: 4676403.8723
59 | 2033-01-01 | 5 | 2027-01-01: 4676403.8723; 2027-02-01: 54558.0452; 2027-03-01: 72062.1258; 2027-04-01: 17504.0806; 2027-05-01: 4658899.7917
60 | 2033-02-01 | 5 | 2027-01-01: 4658899.7917; 2027-02-01: 54353.8309; 2027-03-01: 72062.1258; 2027-04-01: 17708.2949; 2027-05-01: 4641191.4968
61 | 2033-03-01 | 6 | 2027-01-01: 4641191.4968; 2027-02-01: 54147.2341; 2027-03-01: 72062.1258; 2027-04-01: 17914.8917; 2027-05-01: 4623276.6051
62 | 2033-04-01 | 6 | 2027-01-01: 4623276.6051; 2027-02-01: 53938.2271; 2027-03-01: 72062.1258; 2027-04-01: 18123.8987; 2027-05-01: 4605152.7063
63 | 2033-05-01 | 6 | 2027-01-01: 4605152.7063; 2027-02-01: 53726.7816; 2027-03-01: 72062.1258; 2027-04-01: 18335.3442; 2027-05-01: 4586817.3621
64 | 2033-06-01 | 6 | 2027-01-01: 4586817.3621; 2027-02-01: 53512.8692; 2027-03-01: 72062.1258; 2027-04-01: 18549.2566; 2027-05-01: 4568268.1055
65 | 2033-07-01 | 6 | 2027-01-01: 4568268.1055; 2027-02-01: 53296.4612; 2027-03-01: 72062.1258; 2027-04-01: 18765.6646; 2027-05-01: 4549502.441
66 | 2033-08-01 | 6 | 2027-01-01: 4549502.441; 2027-02-01: 53077.5285; 2027-03-01: 72062.1258; 2027-04-01: 18984.5973; 2027-05-01: 4530517.8436
67 | 2033-09-01 | 6 | 2027-01-01: 4530517.8436; 2027-02-01: 52856.0415; 2027-03-01: 72062.1258; 2027-04-01: 19206.0843; 2027-05-01: 4511311.7593
68 | 2033-10-01 | 6 | 2027-01-01: 4511311.7593; 2027-02-01: 52631.9705; 2027-03-01: 72062.1258; 2027-04-01: 19430.1553; 2027-05-01: 4491881.6041
69 | 2033-11-01 | 6 | 2027-01-01: 4491881.6041; 2027-02-01: 52405.2854; 2027-03-01: 72062.1258; 2027-04-01: 19656.8404; 2027-05-01: 4472224.7636
70 | 2033-12-01 | 6 | 2027-01-01: 4472224.7636; 2027-02-01: 52175.9556; 2027-03-01: 72062.1258; 2027-04-01: 19886.1702; 2027-05-01: 4452338.5934
71 | 2034-01-01 | 6 | 2027-01-01: 4452338.5934; 2027-02-01: 51943.9503; 2027-03-01: 72062.1258; 2027-04-01: 20118.1755; 2027-05-01: 4432220.4179
72 | 2034-02-01 | 6 | 2027-01-01: 4432220.4179; 2027-02-01: 51709.2382; 2027-03-01: 72062.1258; 2027-04-01: 20352.8876; 2027-05-01: 4411867.5303
73 | 2034-03-01 | 7 | 2027-01-01: 4411867.5303; 2027-02-01: 51471.7879; 2027-03-01: 72062.1258; 2027-04-01: 20590.338; 2027-05-01: 4391277.1923
74 | 2034-04-01 | 7 | 2027-01-01: 4391277.1923; 2027-02-01: 51231.5672; 2027-03-01: 72062.1258; 2027-04-01: 20830.5586; 2027-05-01: 4370446.6337
75 | 2034-05-01 | 7 | 2027-01-01: 4370446.6337; 2027-02-01: 50988.5441; 2027-03-01: 72062.1258; 2027-04-01: 21073.5817; 2027-05-01: 4349373.052
76 | 2034-06-01 | 7 | 2027-01-01: 4349373.052; 2027-02-01: 50742.6856; 2027-03-01: 72062.1258; 2027-04-01: 21319.4402; 2027-05-01: 4328053.6118
77 | 2034-07-01 | 7 | 2027-01-01: 4328053.6118; 2027-02-01: 50493.9588; 2027-03-01: 72062.1258; 2027-04-01: 21568.167; 2027-05-01: 4306485.4448
78 | 2034-08-01 | 7 | 2027-01-01: 4306485.4448; 2027-02-01: 50242.3302; 2027-03-01: 72062.1258; 2027-04-01: 21819.7956; 2027-05-01: 4284665.6492
79 | 2034-09-01 | 7 | 2027-01-01: 4284665.6492; 2027-02-01: 49987.7659; 2027-03-01: 72062.1258; 2027-04-01: 22074.3599; 2027-05-01: 4262591.2893
80 | 2034-10-01 | 7 | 2027-01-01: 4262591.2893; 2027-02-01: 49730.2317; 2027-03-01: 72062.1258; 2027-04-01: 22331.8941; 2027-05-01: 4240259.3952
81 | 2034-11-01 | 7 | 2027-01-01: 4240259.3952; 2027-02-01: 49469.6929; 2027-03-01: 72062.1258; 2027-04-01: 22592.4329; 2027-05-01: 4217666.9623
82 | 2034-12-01 | 7 | 2027-01-01: 4217666.9623; 2027-02-01: 49206.1146; 2027-03-01: 72062.1258; 2027-04-01: 22856.0112; 2027-05-01: 4194810.9511
83 | 2035-01-01 | 7 | 2027-01-01: 4194810.9511; 2027-02-01: 48939.4611; 2027-03-01: 72062.1258; 2027-04-01: 23122.6647; 2027-05-01: 4171688.2864
84 | 2035-02-01 | 7 | 2027-01-01: 4171688.2864; 2027-02-01: 48669.6967; 2027-03-01: 72062.1258; 2027-04-01: 23392.4291; 2027-05-01: 4148295.8573
85 | 2035-03-01 | 8 | 2027-01-01: 4148295.8573; 2027-02-01: 48396.785; 2027-03-01: 72062.1258; 2027-04-01: 23665.3408; 2027-05-01: 4124630.5164
86 | 2035-04-01 | 8 | 2027-01-01: 4124630.5164; 2027-02-01: 48120.6894; 2027-03-01: 72062.1258; 2027-04-01: 23941.4364; 2027-05-01: 4100689.08
87 | 2035-05-01 | 8 | 2027-01-01: 4100689.08; 2027-02-01: 47841.3726; 2027-03-01: 72062.1258; 2027-04-01: 24220.7532; 2027-05-01: 4076468.3268
88 | 2035-06-01 | 8 | 2027-01-01: 4076468.3268; 2027-02-01: 47558.7971; 2027-03-01: 72062.1258; 2027-04-01: 24503.3287; 2027-05-01: 4051964.9981
89 | 2035-07-01 | 8 | 2027-01-01: 4051964.9981; 2027-02-01: 47272.925; 2027-03-01: 72062.1258; 2027-04-01: 24789.2008; 2027-05-01: 4027175.7973
90 | 2035-08-01 | 8 | 2027-01-01: 4027175.7973; 2027-02-01: 46983.7176; 2027-03-01: 72062.1258; 2027-04-01: 25078.4082; 2027-05-01: 4002097.3891
91 | 2035-09-01 | 8 | 2027-01-01: 4002097.3891; 2027-02-01: 46691.1362; 2027-03-01: 72062.1258; 2027-04-01: 25370.9896; 2027-05-01: 3976726.3995
92 | 2035-10-01 | 8 | 2027-01-01: 3976726.3995; 2027-02-01: 46395.1413; 2027-03-01: 72062.1258; 2027-04-01: 25666.9845; 2027-05-01: 3951059.4151
93 | 2035-11-01 | 8 | 2027-01-01: 3951059.4151; 2027-02-01: 46095.6932; 2027-03-01: 72062.1258; 2027-04-01: 25966.4326; 2027-05-01: 3925092.9824
94 | 2035-12-01 | 8 | 2027-01-01: 3925092.9824; 2027-02-01: 45792.7515; 2027-03-01: 72062.1258; 2027-04-01: 26269.3743; 2027-05-01: 3898823.6081
95 | 2036-01-01 | 8 | 2027-01-01: 3898823.6081; 2027-02-01: 45486.2754; 2027-03-01: 72062.1258; 2027-04-01: 26575.8504; 2027-05-01: 3872247.7577
96 | 2036-02-01 | 8 | 2027-01-01: 3872247.7577; 2027-02-01: 45176.2238; 2027-03-01: 72062.1258; 2027-04-01: 26885.902; 2027-05-01: 3845361.8558
97 | 2036-03-01 | 9 | 2027-01-01: 3845361.8558; 2027-02-01: 44862.555; 2027-03-01: 72062.1258; 2027-04-01: 27199.5708; 2027-05-01: 3818162.2849
98 | 2036-04-01 | 9 | 2027-01-01: 3818162.2849; 2027-02-01: 44545.2267; 2027-03-01: 72062.1258; 2027-04-01: 27516.8991; 2027-05-01: 3790645.3858
99 | 2036-05-01 | 9 | 2027-01-01: 3790645.3858; 2027-02-01: 44224.1962; 2027-03-01: 72062.1258; 2027-04-01: 27837.9296; 2027-05-01: 3762807.4562
100 | 2036-06-01 | 9 | 2027-01-01: 3762807.4562; 2027-02-01: 43899.4203; 2027-03-01: 72062.1258; 2027-04-01: 28162.7055; 2027-05-01: 3734644.7507
101 | 2036-07-01 | 9 | 2027-01-01: 3734644.7507; 2027-02-01: 43570.8554; 2027-03-01: 72062.1258; 2027-04-01: 28491.2704; 2027-05-01: 3706153.4803
102 | 2036-08-01 | 9 | 2027-01-01: 3706153.4803; 2027-02-01: 43238.4573; 2027-03-01: 72062.1258; 2027-04-01: 28823.6685; 2027-05-01: 3677329.8118
103 | 2036-09-01 | 9 | 2027-01-01: 3677329.8118; 2027-02-01: 42902.1811; 2027-03-01: 72062.1258; 2027-04-01: 29159.9447; 2027-05-01: 3648169.8671
104 | 2036-10-01 | 9 | 2027-01-01: 3648169.8671; 2027-02-01: 42561.9818; 2027-03-01: 72062.1258; 2027-04-01: 29500.144; 2027-05-01: 3618669.7231
105 | 2036-11-01 | 9 | 2027-01-01: 3618669.7231; 2027-02-01: 42217.8134; 2027-03-01: 72062.1258; 2027-04-01: 29844.3124; 2027-05-01: 3588825.4107
106 | 2036-12-01 | 9 | 2027-01-01: 3588825.4107; 2027-02-01: 41869.6298; 2027-03-01: 72062.1258; 2027-04-01: 30192.496; 2027-05-01: 3558632.9147
107 | 2037-01-01 | 9 | 2027-01-01: 3558632.9147; 2027-02-01: 41517.384; 2027-03-01: 72062.1258; 2027-04-01: 30544.7418; 2027-05-01: 3528088.1729
108 | 2037-02-01 | 9 | 2027-01-01: 3528088.1729; 2027-02-01: 41161.0287; 2027-03-01: 72062.1258; 2027-04-01: 30901.0971; 2027-05-01: 3497187.0758
109 | 2037-03-01 | 10 | 2027-01-01: 3497187.0758; 2027-02-01: 40800.5159; 2027-03-01: 72062.1258; 2027-04-01: 31261.6099; 2027-05-01: 3465925.4658
110 | 2037-04-01 | 10 | 2027-01-01: 3465925.4658; 2027-02-01: 40435.7971; 2027-03-01: 72062.1258; 2027-04-01: 31626.3287; 2027-05-01: 3434299.1371
111 | 2037-05-01 | 10 | 2027-01-01: 3434299.1371; 2027-02-01: 40066.8233; 2027-03-01: 72062.1258; 2027-04-01: 31995.3025; 2027-05-01: 3402303.8346
112 | 2037-06-01 | 10 | 2027-01-01: 3402303.8346; 2027-02-01: 39693.5447; 2027-03-01: 72062.1258; 2027-04-01: 32368.5811; 2027-05-01: 3369935.2535
113 | 2037-07-01 | 10 | 2027-01-01: 3369935.2535; 2027-02-01: 39315.9113; 2027-03-01: 72062.1258; 2027-04-01: 32746.2145; 2027-05-01: 3337189.039
114 | 2037-08-01 | 10 | 2027-01-01: 3337189.039; 2027-02-01: 38933.8721; 2027-03-01: 72062.1258; 2027-04-01: 33128.2537; 2027-05-01: 3304060.7853
115 | 2037-09-01 | 10 | 2027-01-01: 3304060.7853; 2027-02-01: 38547.3758; 2027-03-01: 72062.1258; 2027-04-01: 33514.75; 2027-05-01: 3270546.0354
116 | 2037-10-01 | 10 | 2027-01-01: 3270546.0354; 2027-02-01: 38156.3704; 2027-03-01: 72062.1258; 2027-04-01: 33905.7554; 2027-05-01: 3236640.28
117 | 2037-11-01 | 10 | 2027-01-01: 3236640.28; 2027-02-01: 37760.8033; 2027-03-01: 72062.1258; 2027-04-01: 34301.3225; 2027-05-01: 3202338.9574
118 | 2037-12-01 | 10 | 2027-01-01: 3202338.9574; 2027-02-01: 37360.6212; 2027-03-01: 72062.1258; 2027-04-01: 34701.5046; 2027-05-01: 3167637.4528
119 | 2038-01-01 | 10 | 2027-01-01: 3167637.4528; 2027-02-01: 36955.7703; 2027-03-01: 72062.1258; 2027-04-01: 35106.3555; 2027-05-01: 3132531.0973
120 | 2038-02-01 | 10 | 2027-01-01: 3132531.0973; 2027-02-01: 36546.1961; 2027-03-01: 72062.1258; 2027-04-01: 35515.9297; 2027-05-01: 3097015.1676
121 | 2038-03-01 | 11 | 2027-01-01: 3097015.1676; 2027-02-01: 36131.8436; 2027-03-01: 72062.1258; 2027-04-01: 35930.2822; 2027-05-01: 3061084.8854
122 | 2038-04-01 | 11 | 2027-01-01: 3061084.8854; 2027-02-01: 35712.657; 2027-03-01: 72062.1258; 2027-04-01: 36349.4688; 2027-05-01: 3024735.4166
123 | 2038-05-01 | 11 | 2027-01-01: 3024735.4166; 2027-02-01: 35288.5799; 2027-03-01: 72062.1258; 2027-04-01: 36773.5459; 2027-05-01: 2987961.8707
124 | 2038-06-01 | 11 | 2027-01-01: 2987961.8707; 2027-02-01: 34859.5552; 2027-03-01: 72062.1258; 2027-04-01: 37202.5706; 2027-05-01: 2950759.3
125 | 2038-07-01 | 11 | 2027-01-01: 2950759.3; 2027-02-01: 34425.5252; 2027-03-01: 72062.1258; 2027-04-01: 37636.6006; 2027-05-01: 2913122.6994
126 | 2038-08-01 | 11 | 2027-01-01: 2913122.6994; 2027-02-01: 33986.4315; 2027-03-01: 72062.1258; 2027-04-01: 38075.6943; 2027-05-01: 2875047.0051
127 | 2038-09-01 | 11 | 2027-01-01: 2875047.0051; 2027-02-01: 33542.2151; 2027-03-01: 72062.1258; 2027-04-01: 38519.9107; 2027-05-01: 2836527.0943
128 | 2038-10-01 | 11 | 2027-01-01: 2836527.0943; 2027-02-01: 33092.8161; 2027-03-01: 72062.1258; 2027-04-01: 38969.3097; 2027-05-01: 2797557.7846
129 | 2038-11-01 | 11 | 2027-01-01: 2797557.7846; 2027-02-01: 32638.1742; 2027-03-01: 72062.1258; 2027-04-01: 39423.9517; 2027-05-01: 2758133.833
130 | 2038-12-01 | 11 | 2027-01-01: 2758133.833; 2027-02-01: 32178.2281; 2027-03-01: 72062.1258; 2027-04-01: 39883.8978; 2027-05-01: 2718249.9352
131 | 2039-01-01 | 11 | 2027-01-01: 2718249.9352; 2027-02-01: 31712.9159; 2027-03-01: 72062.1258; 2027-04-01: 40349.2099; 2027-05-01: 2677900.7253
132 | 2039-02-01 | 11 | 2027-01-01: 2677900.7253; 2027-02-01: 31242.1751; 2027-03-01: 72062.1258; 2027-04-01: 40819.9507; 2027-05-01: 2637080.7747
133 | 2039-03-01 | 12 | 2027-01-01: 2637080.7747; 2027-02-01: 30765.9424; 2027-03-01: 72062.1258; 2027-04-01: 41296.1834; 2027-05-01: 2595784.5912
134 | 2039-04-01 | 12 | 2027-01-01: 2595784.5912; 2027-02-01: 30284.1536; 2027-03-01: 72062.1258; 2027-04-01: 41777.9722; 2027-05-01: 2554006.619
135 | 2039-05-01 | 12 | 2027-01-01: 2554006.619; 2027-02-01: 29796.7439; 2027-03-01: 72062.1258; 2027-04-01: 42265.3819; 2027-05-01: 2511741.2371
136 | 2039-06-01 | 12 | 2027-01-01: 2511741.2371; 2027-02-01: 29303.6478; 2027-03-01: 72062.1258; 2027-04-01: 42758.478; 2027-05-01: 2468982.759
137 | 2039-07-01 | 12 | 2027-01-01: 2468982.759; 2027-02-01: 28804.7989; 2027-03-01: 72062.1258; 2027-04-01: 43257.3269; 2027-05-01: 2425725.4321
138 | 2039-08-01 | 12 | 2027-01-01: 2425725.4321; 2027-02-01: 28300.13; 2027-03-01: 72062.1258; 2027-04-01: 43761.9958; 2027-05-01: 2381963.4363
139 | 2039-09-01 | 12 | 2027-01-01: 2381963.4363; 2027-02-01: 27789.5734; 2027-03-01: 72062.1258; 2027-04-01: 44272.5524; 2027-05-01: 2337690.8839
140 | 2039-10-01 | 12 | 2027-01-01: 2337690.8839; 2027-02-01: 27273.0603; 2027-03-01: 72062.1258; 2027-04-01: 44789.0655; 2027-05-01: 2292901.8185
141 | 2039-11-01 | 12 | 2027-01-01: 2292901.8185; 2027-02-01: 26750.5212; 2027-03-01: 72062.1258; 2027-04-01: 45311.6046; 2027-05-01: 2247590.2139
142 | 2039-12-01 | 12 | 2027-01-01: 2247590.2139; 2027-02-01: 26221.8858; 2027-03-01: 72062.1258; 2027-04-01: 45840.24; 2027-05-01: 2201749.9739
143 | 2040-01-01 | 12 | 2027-01-01: 2201749.9739; 2027-02-01: 25687.083; 2027-03-01: 72062.1258; 2027-04-01: 46375.0428; 2027-05-01: 2155374.9311
144 | 2040-02-01 | 12 | 2027-01-01: 2155374.9311; 2027-02-01: 25146.0409; 2027-03-01: 72062.1258; 2027-04-01: 46916.0849; 2027-05-01: 2108458.8462
145 | 2040-03-01 | 13 | 2027-01-01: 2108458.8462; 2027-02-01: 24598.6865; 2027-03-01: 72062.1258; 2027-04-01: 47463.4393; 2027-05-01: 2060995.4069
146 | 2040-04-01 | 13 | 2027-01-01: 2060995.4069; 2027-02-01: 24044.9464; 2027-03-01: 72062.1258; 2027-04-01: 48017.1794; 2027-05-01: 2012978.2275
147 | 2040-05-01 | 13 | 2027-01-01: 2012978.2275; 2027-02-01: 23484.746; 2027-03-01: 72062.1258; 2027-04-01: 48577.3798; 2027-05-01: 1964400.8477
148 | 2040-06-01 | 13 | 2027-01-01: 1964400.8477; 2027-02-01: 22918.0099; 2027-03-01: 72062.1258; 2027-04-01: 49144.1159; 2027-05-01: 1915256.7318
149 | 2040-07-01 | 13 | 2027-01-01: 1915256.7318; 2027-02-01: 22344.6619; 2027-03-01: 72062.1258; 2027-04-01: 49717.4639; 2027-05-01: 1865539.2678
150 | 2040-08-01 | 13 | 2027-01-01: 1865539.2678; 2027-02-01: 21764.6248; 2027-03-01: 72062.1258; 2027-04-01: 50297.501; 2027-05-01: 1815241.7668
151 | 2040-09-01 | 13 | 2027-01-01: 1815241.7668; 2027-02-01: 21177.8206; 2027-03-01: 72062.1258; 2027-04-01: 50884.3052; 2027-05-01: 1764357.4616
152 | 2040-10-01 | 13 | 2027-01-01: 1764357.4616; 2027-02-01: 20584.1704; 2027-03-01: 72062.1258; 2027-04-01: 51477.9554; 2027-05-01: 1712879.5062
153 | 2040-11-01 | 13 | 2027-01-01: 1712879.5062; 2027-02-01: 19983.5942; 2027-03-01: 72062.1258; 2027-04-01: 52078.5316; 2027-05-01: 1660800.9747
154 | 2040-12-01 | 13 | 2027-01-01: 1660800.9747; 2027-02-01: 19376.0114; 2027-03-01: 72062.1258; 2027-04-01: 52686.1144; 2027-05-01: 1608114.8602
155 | 2041-01-01 | 13 | 2027-01-01: 1608114.8602; 2027-02-01: 18761.34; 2027-03-01: 72062.1258; 2027-04-01: 53300.7858; 2027-05-01: 1554814.0745
156 | 2041-02-01 | 13 | 2027-01-01: 1554814.0745; 2027-02-01: 18139.4975; 2027-03-01: 72062.1258; 2027-04-01: 53922.6283; 2027-05-01: 1500891.4462
157 | 2041-03-01 | 14 | 2027-01-01: 1500891.4462; 2027-02-01: 17510.4002; 2027-03-01: 72062.1258; 2027-04-01: 54551.7256; 2027-05-01: 1446339.7206
158 | 2041-04-01 | 14 | 2027-01-01: 1446339.7206; 2027-02-01: 16873.9634; 2027-03-01: 72062.1258; 2027-04-01: 55188.1624; 2027-05-01: 1391151.5582
159 | 2041-05-01 | 14 | 2027-01-01: 1391151.5582; 2027-02-01: 16230.1015; 2027-03-01: 72062.1258; 2027-04-01: 55832.0243; 2027-05-01: 1335319.5339
160 | 2041-06-01 | 14 | 2027-01-01: 1335319.5339; 2027-02-01: 15578.7279; 2027-03-01: 72062.1258; 2027-04-01: 56483.3979; 2027-05-01: 1278836.136
161 | 2041-07-01 | 14 | 2027-01-01: 1278836.136; 2027-02-01: 14919.7549; 2027-03-01: 72062.1258; 2027-04-01: 57142.3709; 2027-05-01: 1221693.7651
162 | 2041-08-01 | 14 | 2027-01-01: 1221693.7651; 2027-02-01: 14253.0939; 2027-03-01: 72062.1258; 2027-04-01: 57809.0319; 2027-05-01: 1163884.7332
163 | 2041-09-01 | 14 | 2027-01-01: 1163884.7332; 2027-02-01: 13578.6552; 2027-03-01: 72062.1258; 2027-04-01: 58483.4706; 2027-05-01: 1105401.2626
164 | 2041-10-01 | 14 | 2027-01-01: 1105401.2626; 2027-02-01: 12896.3481; 2027-03-01: 72062.1258; 2027-04-01: 59165.7777; 2027-05-01: 1046235.4849
165 | 2041-11-01 | 14 | 2027-01-01: 1046235.4849; 2027-02-01: 12206.0807; 2027-03-01: 72062.1258; 2027-04-01: 59856.0451; 2027-05-01: 986379.4398
166 | 2041-12-01 | 14 | 2027-01-01: 986379.4398; 2027-02-01: 11507.7601; 2027-03-01: 72062.1258; 2027-04-01: 60554.3657; 2027-05-01: 925825.0741
167 | 2042-01-01 | 14 | 2027-01-01: 925825.0741; 2027-02-01: 10801.2925; 2027-03-01: 72062.1258; 2027-04-01: 61260.8333; 2027-05-01: 864564.2408
168 | 2042-02-01 | 14 | 2027-01-01: 864564.2408; 2027-02-01: 10086.5828; 2027-03-01: 72062.1258; 2027-04-01: 61975.543; 2027-05-01: 802588.6978
169 | 2042-03-01 | 15 | 2027-01-01: 802588.6978; 2027-02-01: 9363.5348; 2027-03-01: 72062.1258; 2027-04-01: 62698.591; 2027-05-01: 739890.1068
170 | 2042-04-01 | 15 | 2027-01-01: 739890.1068; 2027-02-01: 8632.0512; 2027-03-01: 72062.1258; 2027-04-01: 63430.0746; 2027-05-01: 676460.0323
171 | 2042-05-01 | 15 | 2027-01-01: 676460.0323; 2027-02-01: 7892.0337; 2027-03-01: 72062.1258; 2027-04-01: 64170.0921; 2027-05-01: 612289.9402
172 | 2042-06-01 | 15 | 2027-01-01: 612289.9402; 2027-02-01: 7143.3826; 2027-03-01: 72062.1258; 2027-04-01: 64918.7432; 2027-05-01: 547371.197
173 | 2042-07-01 | 15 | 2027-01-01: 547371.197; 2027-02-01: 6385.9973; 2027-03-01: 72062.1258; 2027-04-01: 65676.1285; 2027-05-01: 481695.0685
174 | 2042-08-01 | 15 | 2027-01-01: 481695.0685; 2027-02-01: 5619.7758; 2027-03-01: 72062.1258; 2027-04-01: 66442.35; 2027-05-01: 415252.7185
175 | 2042-09-01 | 15 | 2027-01-01: 415252.7185; 2027-02-01: 4844.615; 2027-03-01: 72062.1258; 2027-04-01: 67217.5108; 2027-05-01: 348035.2077
176 | 2042-10-01 | 15 | 2027-01-01: 348035.2077; 2027-02-01: 4060.4108; 2027-03-01: 72062.1258; 2027-04-01: 68001.715; 2027-05-01: 280033.4927
177 | 2042-11-01 | 15 | 2027-01-01: 280033.4927; 2027-02-01: 3267.0574; 2027-03-01: 72062.1258; 2027-04-01: 68795.0684; 2027-05-01: 211238.4243
178 | 2042-12-01 | 15 | 2027-01-01: 211238.4243; 2027-02-01: 2464.4483; 2027-03-01: 72062.1258; 2027-04-01: 69597.6775; 2027-05-01: 141640.7468
179 | 2043-01-01 | 15 | 2027-01-01: 141640.7468; 2027-02-01: 1652.4754; 2027-03-01: 72062.1258; 2027-04-01: 70409.6504; 2027-05-01: 71231.0963
180 | 2043-02-01 | 15 | 2027-01-01: 71231.0963; 2027-02-01: 831.0295; 2027-03-01: 72062.1258; 2027-04-01: 71231.0963; 2027-05-01: 0
181 | 2043-03-01 | 16 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
182 | 2043-04-01 | 16 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
183 | 2043-05-01 | 16 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
184 | 2043-06-01 | 16 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
185 | 2043-07-01 | 16 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
186 | 2043-08-01 | 16 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
187 | 2043-09-01 | 16 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
188 | 2043-10-01 | 16 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
189 | 2043-11-01 | 16 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
190 | 2043-12-01 | 16 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
191 | 2044-01-01 | 16 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
192 | 2044-02-01 | 16 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
193 | 2044-03-01 | 17 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
194 | 2044-04-01 | 17 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
195 | 2044-05-01 | 17 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
196 | 2044-06-01 | 17 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
197 | 2044-07-01 | 17 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
198 | 2044-08-01 | 17 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
199 | 2044-09-01 | 17 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
200 | 2044-10-01 | 17 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
201 | 2044-11-01 | 17 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
202 | 2044-12-01 | 17 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
203 | 2045-01-01 | 17 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
204 | 2045-02-01 | 17 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
205 | 2045-03-01 | 18 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
206 | 2045-04-01 | 18 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
207 | 2045-05-01 | 18 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
208 | 2045-06-01 | 18 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
209 | 2045-07-01 | 18 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
210 | 2045-08-01 | 18 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
211 | 2045-09-01 | 18 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
212 | 2045-10-01 | 18 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
213 | 2045-11-01 | 18 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
214 | 2045-12-01 | 18 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
215 | 2046-01-01 | 18 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
216 | 2046-02-01 | 18 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
217 | 2046-03-01 | 19 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
218 | 2046-04-01 | 19 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
219 | 2046-05-01 | 19 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
220 | 2046-06-01 | 19 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
221 | 2046-07-01 | 19 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
222 | 2046-08-01 | 19 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
223 | 2046-09-01 | 19 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
224 | 2046-10-01 | 19 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
225 | 2046-11-01 | 19 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
226 | 2046-12-01 | 19 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
227 | 2047-01-01 | 19 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
228 | 2047-02-01 | 19 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
229 | 2047-03-01 | 20 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
230 | 2047-04-01 | 20 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
231 | 2047-05-01 | 20 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
232 | 2047-06-01 | 20 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
233 | 2047-07-01 | 20 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
234 | 2047-08-01 | 20 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
235 | 2047-09-01 | 20 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
236 | 2047-10-01 | 20 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
237 | 2047-11-01 | 20 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
238 | 2047-12-01 | 20 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
239 | 2048-01-01 | 20 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
240 | 2048-02-01 | 20 | 2027-01-01: 0; 2027-02-01: 0; 2027-03-01: 0; 2027-04-01: 0; 2027-05-01: 0
Loan totals | የብድር ድምር
Principal repaid in total | ETB | 5411120.0914
Interest after completion | ETB | 7560062.5534
Interest – total over the life of the loan | ETB | 7778829.8443
Balance left at end of the term | ETB | 0
Optional – renting out part of the house | አማራጭ – ከፊሉን ማከራየት
Rent in first year after completion (gross) | ETB | 328182.6641
Rent after vacancy, running costs & tax | ETB | 241542.4407
Rented area ÷ house area | % | 24%
Cost of the rented part (total cost × rented share of area) | ETB | 3098668.8219
Gross yield on the cost of the rented part | % | 10.59%
Simple payback of the rented part (years) | years | 12.8287
Net rent ÷ monthly instalment | % | 27.93%
Loan by year (for the estimate page) | ብድር በዓመት
Year | Interest | Principal | 2027-01-01: Payments; 2027-02-01: Closing balance
1 | 750404.2418 | 114341.2678 | 2027-01-01: 864745.5097; 2027-02-01: 5296778.8235
2 | 733328.2849 | 131417.2248 | 2027-01-01: 864745.5097; 2027-02-01: 5165361.5987
3 | 713702.1698 | 151043.3398 | 2027-01-01: 864745.5097; 2027-02-01: 5014318.2589
4 | 691145.051 | 173600.4587 | 2027-01-01: 864745.5097; 2027-02-01: 4840717.8002
5 | 665219.2062 | 199526.3035 | 2027-01-01: 864745.5097; 2027-02-01: 4641191.4968
6 | 635421.5432 | 229323.9665 | 2027-01-01: 864745.5097; 2027-02-01: 4411867.5303
7 | 601173.8366 | 263571.673 | 2027-01-01: 864745.5097; 2027-02-01: 4148295.8573
8 | 561811.5082 | 302934.0015 | 2027-01-01: 864745.5097; 2027-02-01: 3845361.8558
9 | 516570.7297 | 348174.78 | 2027-01-01: 864745.5097; 2027-02-01: 3497187.0758
10 | 464573.6015 | 400171.9082 | 2027-01-01: 864745.5097; 2027-02-01: 3097015.1676
11 | 404811.1167 | 459934.3929 | 2027-01-01: 864745.5097; 2027-02-01: 2637080.7747
12 | 336123.5812 | 528621.9285 | 2027-01-01: 864745.5097; 2027-02-01: 2108458.8462
13 | 257178.1097 | 607567.4 | 2027-01-01: 864745.5097; 2027-02-01: 1500891.4462
14 | 166442.7613 | 698302.7484 | 2027-01-01: 864745.5097; 2027-02-01: 802588.6978
15 | 62156.8118 | 802588.6978 | 2027-01-01: 864745.5097; 2027-02-01: 0
16 | 0 | 0 | 2027-01-01: 0; 2027-02-01: 0
17 | 0 | 0 | 2027-01-01: 0; 2027-02-01: 0
18 | 0 | 0 | 2027-01-01: 0; 2027-02-01: 0
19 | 0 | 0 | 2027-01-01: 0; 2027-02-01: 0
20 | 0 | 0 | 2027-01-01: 0; 2027-02-01: 0

## P3_Estimate
My house – estimate | [7 empty] | ◂ Start
የቤት ግንባታ ወጪ ግምት
SAMPLE — G+1 family house, Addis Ababa ¦ Private residence – cost estimate & home loan
helpers
Project · ፕሮጀክት | SAMPLE — G+1 family house, Addis Ababa | [7 empty] | 300000
Building · ሕንፃ | G+1 · 250 m² gross · Standard finish | [7 empty] | 0.24021
Where & how long · ቦታና ጊዜ | Addis Ababa – Bole sub-city · 14 months from Jan 2027 | [7 empty] | 0.35
0
CONSTRUCTION COST · የግንባታ ወጪ | TOTAL COST · ጠቅላላ ወጪ |  |  | MONTHLY INSTALMENT · ወርሃዊ ክፍያ |  | FUNDING GAP · የገንዘብ ክፍተት
12622352.8005 | 12911120.0914 |  |  | 72062.1258 |  | 0
Range 11.4 – 14.5 m | per m² building: 50,489 |  |  | 24% of income · Affordable |  | covered · በቂ ነው
COST BREAKDOWN · የወጪ ክፍፍል |  |  |  | WHERE THE MONEY GOES
Item | ETB | % total
Foundation & basement | 875000 | 6.777% | መሠረትና ምድር ቤት
Frame, walls & roof | 2825000 | 21.88% | ፍሬም፣ ግድግዳና ጣሪያ
Internal walls, finishes & kitchen | 2125000 | 16.46% | የውስጥ ሥራ፣ ማጠናቀቂያና ማዕድ ቤት
Electrical & plumbing | 950000 | 7.358% | ኤሌክትሪክና ቧንቧ
Site set-up & external works | 2385000 | 18.47% | ቅድመ-ሥራና የውጭ ሥራ
Price rises & contingency | 1777096.5005 | 13.76% | የዋጋ ጭማሪና መጠባበቂያ
Design, supervision & permits | 685256.3 | 5.307% | ዲዛይን፣ ቁጥጥርና ፈቃድ
Furniture & appliances | 1000000 | 7.745% | የቤት ዕቃዎች
Land | 0 | 0% | መሬት
Loan fee & interest while building | 288767.2909 | 2.237% | የብድር ክፍያና ወለድ
TOTAL COST · ጠቅላላ | 12911120.0914
PAYING THE CONTRACTOR · ለኮንትራክተር ክፍያ |  |  |  | CASH NEEDED EACH MONTH
Stage | ETB | Cum. % | ≈ month
1 Mobilisation & site set-up | 328351.6962 | 3.002% | 3
2 Foundation | 1044755.3972 | 12.55% | 4
3 Frame (columns, beams, slabs) | 2029810.4859 | 31.11% | 6
4 Walls, windows & roof | 1343256.9392 | 43.4% | 7
5 Electrical, plumbing & internal walls | 1791009.2523 | 59.77% | 8
6 Finishes, kitchen & external works | 4399912.7297 | 100% | 14
Retention paid after defects period | 497140.75 |  | 20
FUNDING & HOME LOAN · ገንዘብና ብድር |  |  |  | HOME-LOAN BY YEAR · ብድር በዓመት
Own savings used · ቁጠባ | 5000000 |  |  | Year | Interest | Principal | Closing
Family / diaspora · ቤተሰብ | 2500000 |  |  | 1 | 750404.2418 | 114341.2678 | 5296778.8235
Home loan drawn · የወጣ ብድር | 5192352.8005 |  |  | 2 | 733328.2849 | 131417.2248 | 5165361.5987
Funding gap · ክፍተት | 0 |  |  | 3 | 713702.1698 | 151043.3398 | 5014318.2589
Loan at completion (incl. interest added) | 5411120.0914 |  |  | 4 | 691145.051 | 173600.4587 | 4840717.8002
Interest rate · ወለድ | 14% |  |  | 5 | 665219.2062 | 199526.3035 | 4641191.4968
Repayment period (years) | 15 |  |  | 6 | 635421.5432 | 229323.9665 | 4411867.5303
Monthly instalment · ወርሃዊ ክፍያ | 72062.1258 |  |  | 7 | 601173.8366 | 263571.673 | 4148295.8573
Interest paid monthly while building (max) | 0 |  |  | 8 | 561811.5082 | 302934.0015 | 3845361.8558
Total interest over the loan · ጠቅላላ ወለድ | 7778829.8443 |  |  | 9 | 516570.7297 | 348174.78 | 3497187.0758
Loan repaid by · የሚያልቅበት | 2043-02-28 |  |  | 10 | 464573.6015 | 400171.9082 | 3097015.1676
Debt payments ÷ income · ከገቢ ድርሻ | 24.02% |  |  | 11 | 404811.1167 | 459934.3929 | 2637080.7747
Affordability · የመክፈል አቅም | Affordable · ይቻላል |  |  | 12 | 336123.5812 | 528621.9285 | 2108458.8462
Largest loan your income supports | 7884413.6674 |  |  | 13 | 257178.1097 | 607567.4 | 1500891.4462
|  |  |  | 14 | 166442.7613 | 698302.7484 | 802588.6978
OPTIONAL: RENT OUT PART · ከፊሉን ማከራየት |  |  |  | 15 | 62156.8118 | 802588.6978 | 0
Switched on? (P1 block 7) | Yes · አዎ |  |  | 16 | 0 | 0 | 0
Rent, first year (gross) · ኪራይ | 328182.6641 |  |  | 17 | 0 | 0 | 0
Rent after vacancy, costs & tax | 241542.4407 |  |  | 18 | 0 | 0 | 0
Gross yield on the rented part's cost · ገቢ ከወጪ | 10.59% |  |  | 19 | 0 | 0 | 0
Simple payback (years) · የመመለሻ ጊዜ | 12.8287 |  |  | 20 | 0 | 0 | 0
Net rent ÷ monthly instalment · የሚሸፍነው | 27.93%
Planning estimate only – get a priced BOQ from a licensed quantity surveyor before signing a contract.
ይህ ግምት ብቻ ነው፤ ውል ከመፈረምዎ በፊት ፈቃድ ካለው ባለሙያ የተዘጋጀ የሥራ መጠን ዝርዝር (BOQ) ያግኙ።

## P4_Checks
P4 · My house – checks |  |  |  | ◂ Start
የቤት ስሌት ማረጋገጫዎች |  |  |  | Estimate ▸
SAMPLE — G+1 family house, Addis Ababa ¦ Private residence – cost estimate & home loan
Private-track integrity checks – errors must PASS; warnings are advice | ማረጋገጫዎች
Check | Type | Value | Tolerance | Status
P01 Money in = money out every month (savings + family + loan + gap = cash needed) | Error | 0 | 1 | PASS
P02 Cost breakdown adds up to the total cost | Error | 0 | 1 | PASS
P03 Monthly costs + interest = total cost | Error | 0 | 1 | PASS
P04 Contractor stages = building work + contingency | Error | 0 | 1 | PASS
P05 Loan fully repaid at the end of the term | Error | 0 | 1 | PASS
P06 Principal repaid = loan balance at completion | Error | 0 | 1 | PASS
P07 Switches valid (track and data set) | Error | 0 | 0.5 | PASS
P08 No formula errors on P1–P3 | Error | 0 | 0.5 | PASS
P09 Building type matches the floors entered | Warning | 0 | 0.5 | PASS
P10 Funding gap = 0 (savings, family and loan cover the cost) | Warning | 0 | 1 | PASS
P11 Instalment within the affordability limit | Warning | 0 | 0.5 | PASS
P12 Rented area not larger than the house | Warning | 0 | 0.5 | PASS
Checks passed |  | 12
Errors (FAIL) |  | 0
Warnings |  | 0
Total checks |  | 12
Status |  | ALL CHECKS PASS
Fixing warnings: P09 – choose the building type that matches the floors in P1 block 2; P10 – add savings, family money or loan; P11 – lower the cost, borrow less or extend the term.

## 01_Dashboard
Dashboard | [16 empty] | ◂ Start
ዳሽቦርድ – ፕሮጀክቴ ያተርፋል?
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
helpers
Scenario | Base |  | Checks | 25 / 25 pass |  | Project type | Mixed |  | Verdict · ውሳኔ | VIABLE · አዋጭ |  |  |  |  | Equity IRR hurdle | 20% |  | VIABLE
ETB; IRR on dated cash flows (XIRR); verdict = equity IRR vs hurdle, profit on cost and DSCR covenant. | [17 empty] | 0
0
TOTAL DEVELOPMENT COST |  |  | GROSS DEVELOPMENT VALUE |  |  | PROFIT ON COST |  |  | EQUITY IRR |  |  | PEAK DEBT |  |  | MIN DSCR |  |  | 1
0
550828221.8186 |  |  | 836520727.1544 |  |  | 51.87% |  |  | 27.4% |  |  | 132698394.6015 |  |  | 1.7682
ETB · 86,067 per m² gross |  |  | GDV ÷ TDC = 1.52x |  |  | margin on GDV 34.2% |  |  | hurdle 20.0% ✓ above |  |  | incl. capitalised IDC 17.5 m |  |  | covenant 1.30x ✓ met
(a) Project cash flow and cumulative · ETB m | [5 empty] | (b) Loan balance at period end · ETB m | [5 empty] | (b) DSCR by year vs covenant · x (capped at 10)
(c) Revenue mix · ETB m | [5 empty] | (d) Development cost breakdown · ETB m | [5 empty] | Tornado – change in project value, ETB m (±20%; delay +6 mo)
SOURCES & USES – construction period (ETB) | [8 empty] | ALERTS · ማስጠንቀቂያዎች
Uses |  |  | Sources | [5 empty] | ✓ All model checks pass
TDC | 550828221.8186 |  | Equity committed | 177478493.4557 |  |  |  |  | ✓ DSCR covenant met
Capex VAT (refund) | 39251693.9936 |  | Top-up / gap | 0 |  |  |  |  | ✓ Funding fully covered
Lease paid in build | 27585000 |  | Bank debt drawn | 115241548.1987 |  |  |  |  | ✓ Cash above minimum
Pre-opening cost | 1500000 |  | Presale cash used | 158021910.3188 |  |  |  |  | ✓ No impairment indicator
|  |  | IDC capitalised | 17456846.4028 |  |  |  |  | ✓ FAR within limit
|  |  | Land non-cash | 135000000 |  |  |  |  | ✓ Equity IRR above hurdle
|  |  | Retention held | 15966117.4361 |  |  |  |  | ! 7 input(s) marked Low confidence – firm them up (10 Inputs, column K)
Total uses | 619164915.8122 |  | Total sources | 619164915.8122 |  |  |  |  | ! Tax rates must be verified (sheet 12) · የግብር መጣኔዎችን ያረጋግጡ
|  |  | Check (= 0) | 0
KEY FINDINGS – written by the model from the live numbers · ዋና ዋና ግኝቶች
• | SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa · type: Mixed · Base scenario → verdict: VIABLE (አዋጭ).
• | Returns: equity IRR 27.4% against a 20.0% hurdle; project IRR 34.6%; profit on cost 51.9%; equity multiple 4.80x.
• | Cost & funding: TDC ETB 550.8 m (86,067 per m² gross), funded by equity 177.5 m, bank debt 115.2 m and presales 158.0 m.
• | Lender view: minimum DSCR 1.77x against a 1.30x covenant – met in every repayment year. Peak debt ETB 132.7 m, repaid by Jun 2039.
• | Income: stabilised NOI ETB 30.4 m a year → yield on cost 22.3% vs exit cap rate 9.0% (positive development spread).
• | Biggest risk on the tornado: Sale price. Rents can fall 72% before NPV reaches zero; costs can overrun 18% before equity IRR drops below the hurdle.
• | Land: Lease (cash). 7 input(s) are marked Low confidence – test them on sheet 52.
Chart data (linked – do not edit)
Period | C1 | C2 | C3 | C4 | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | O9 | O10
Project cash flow | -89.631 | -144.8159 | 144.5971 | 0.20237 | 90.3732 | 77.2658 | 8.4066 | 14.1892 | 15.7532 | 17.4755 | 19.9929 | 22.0311 | 24.2242 | 637.3054
Cumulative | -89.631 | -234.447 | -89.8499 | -89.6475 | 0.72566 | 77.9914 | 86.3981 | 100.5873 | 116.3405 | 133.8161 | 153.809 | 175.8401 | 200.0643 | 837.3697
Loan balance | 0 | 111.3479 | 132.6984 | 132.6984 | 53.9614 | 21.9374 | 20.3892 | 18.5954 | 16.517 | 14.1088 | 11.3186 | 8.0858 | 4.34 | 0
DSCR | 0 | 0 | 0 | 0 | 6.2318 | 7.0093 | 1.7682 | 2.9844 | 3.3134 | 3.6757 | 4.2051 | 4.6339 | 5.0951 | 5.5928
Covenant | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
Sales | 0 | 0 | 327.4379 | 0 | 98.6111 | 72.3148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rent | 0 | 0 | 0 | 0 | 19.2236 | 27.7884 | 34.496 | 37.2556 | 40.2361 | 43.455 | 46.9314 | 50.6859 | 54.7408 | 59.12
Other | 0 | 0 | 0 | 0 | 4.2525 | 5.0713 | 5.7268 | 6.0312 | 6.3599 | 4.7925 | 5.1759 | 5.59 | 6.0372 | 6.5202

## 10_Inputs
10 · Inputs – all assumptions | [9 empty] | ◂ Start
ግብዓቶች – ሁሉም ግምቶች | [9 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Input | ግብዓት | Unit | MY PROJECT (your values) | SAMPLE 1 B+G+8 mixed | SAMPLE 2 Trade centre | ACTIVE (used by model) | Range name | Notes / source | Confidence | Source / date
Blue cells on amber are inputs. Column H picks the data set chosen on the Start sheet (1 = My project, 2 = Sample 1, 3 = Sample 2). Sample columns are examples – "Sample value — not market advice". Columns K–L record how sure you are of each number and where it came from.
1. Project | 1. ፕሮጀክት
Project name | የፕሮጀክት ስም | text | My project | SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa | SAMPLE 2 — B+G+10 trade centre & hotel, Addis Ababa | SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa | PROJ_NAME | Shown in every sheet header | High
Location (sub-city / town) | አካባቢ (ክ/ከተማ / ከተማ) | text |  | Addis Ababa – Kirkos sub-city | Addis Ababa – Lideta sub-city | Addis Ababa – Kirkos sub-city | LOCATION | Free text | High
Location class for cost factor | የቦታ ዓይነት (ለወጪ ማስተካከያ) | list | Addis Ababa | Addis Ababa | Addis Ababa | 1 | LOC_TYPE | Regional towns use the regional location factor | High
Plot area | የቦታ ስፋት | m² | 0 | 1000 | 2000 | 1000 | PLOT_AREA | From title deed / lease contract | High
Max floor-area ratio (FAR) permitted | የተፈቀደ የወለል ስፋት ጥምርታ | x | 0 | 8 | 8 | 8 | FAR | From the city master plan / building permit; 0 = not checked | Medium
Construction start date | የግንባታ መጀመሪያ ቀን | date | 2027-01-01 | 2027-01-01 | 2027-01-01 | 2027-01-01 | START_DATE | First month of construction (budget date for prices) | High
Construction period | የግንባታ ጊዜ | months | 24 | 30 | 36 | 30 | CONSTR_M | 1–48 months; scenario delay months are added | Medium
Memo: ETB per USD | ብር በአንድ ዶላር (ማስታወሻ) | ETB/USD | 155 | 155 | 155 | 155 | FX_USD | Memo only – the model runs in ETB. Verify current NBE rate | High
Finish level | የማጠናቀቂያ ደረጃ | list | Standard | Standard | Standard | 2 | FINISH | Selects the column of the cost library (block 12) | Medium
2. Gross floor area by floor (net lettable / saleable areas go on sheet 13 Spaces) | 2. ጠቅላላ የወለል ስፋት በፎቅ
Basement 2 – gross area | ምድር ቤት 2 – ጠቅላላ ስፋት | m² | 0 | 0 | 1800 | 0 | FL_A1 | Gross floor area incl. walls, cores & common areas | High
Basement 1 – gross area | ምድር ቤት 1 – ጠቅላላ ስፋት | m² | 0 | 900 | 1800 | 900 | FL_A2 | Gross floor area incl. walls, cores & common areas | High
Ground floor – gross area | ምድር ወለል – ጠቅላላ ስፋት | m² | 0 | 650 | 1400 | 650 | FL_A3 | Gross floor area incl. walls, cores & common areas | High
Floor 1 – gross area | 1ኛ ፎቅ – ጠቅላላ ስፋት | m² | 0 | 650 | 1300 | 650 | FL_A4 | Gross floor area incl. walls, cores & common areas | High
Floor 2 – gross area | 2ኛ ፎቅ – ጠቅላላ ስፋት | m² | 0 | 600 | 1300 | 600 | FL_A5 | Gross floor area incl. walls, cores & common areas | High
Floor 3 – gross area | 3ኛ ፎቅ – ጠቅላላ ስፋት | m² | 0 | 600 | 1300 | 600 | FL_A6 | Gross floor area incl. walls, cores & common areas | High
Floor 4 – gross area | 4ኛ ፎቅ – ጠቅላላ ስፋት | m² | 0 | 600 | 1300 | 600 | FL_A7 | Gross floor area incl. walls, cores & common areas | High
Floor 5 – gross area | 5ኛ ፎቅ – ጠቅላላ ስፋት | m² | 0 | 600 | 1300 | 600 | FL_A8 | Gross floor area incl. walls, cores & common areas | High
Floor 6 – gross area | 6ኛ ፎቅ – ጠቅላላ ስፋት | m² | 0 | 600 | 1300 | 600 | FL_A9 | Gross floor area incl. walls, cores & common areas | High
Floor 7 – gross area | 7ኛ ፎቅ – ጠቅላላ ስፋት | m² | 0 | 600 | 1300 | 600 | FL_A10 | Gross floor area incl. walls, cores & common areas | High
Floor 8 – gross area | 8ኛ ፎቅ – ጠቅላላ ስፋት | m² | 0 | 600 | 1300 | 600 | FL_A11 | Gross floor area incl. walls, cores & common areas | High
Floor 9 – gross area | 9ኛ ፎቅ – ጠቅላላ ስፋት | m² | 0 | 0 | 1300 | 0 | FL_A12 | Gross floor area incl. walls, cores & common areas | High
Floor 10 – gross area | 10ኛ ፎቅ – ጠቅላላ ስፋት | m² | 0 | 0 | 1300 | 0 | FL_A13 | Gross floor area incl. walls, cores & common areas | High
Floor 11 – gross area | 11ኛ ፎቅ – ጠቅላላ ስፋት | m² | 0 | 0 | 0 | 0 | FL_A14 | Gross floor area incl. walls, cores & common areas | High
Floor 12 – gross area | 12ኛ ፎቅ – ጠቅላላ ስፋት | m² | 0 | 0 | 0 | 0 | FL_A15 | Gross floor area incl. walls, cores & common areas | High
Floor 13 – gross area | 13ኛ ፎቅ – ጠቅላላ ስፋት | m² | 0 | 0 | 0 | 0 | FL_A16 | Gross floor area incl. walls, cores & common areas | High
3. Construction cost | 3. የግንባታ ወጪ
Preliminaries – entry method | ቅድመ-ሥራዎች – አገባብ | list | Rate x area | Rate x area | Rate x area | 1 | METH_PRELIM | Rate x area uses the cost library (block 12); Lump sum = detailed BOQ override | Medium
Substructure – entry method | የመሠረት ሥራ – አገባብ | list | Rate x area | Rate x area | Rate x area | 1 | METH_SUBSTR | Rate x area uses the cost library (block 12); Lump sum = detailed BOQ override | Medium
Superstructure (frame) – entry method | ከመሬት በላይ መዋቅር (ፍሬም) – አገባብ | list | Rate x area | Rate x area | Rate x area | 1 | METH_SUPER | Rate x area uses the cost library (block 12); Lump sum = detailed BOQ override | Medium
Envelope (walls, windows, roof) – entry method | ግድግዳ፣ መስኮትና ጣሪያ – አገባብ | list | Rate x area | Rate x area | Rate x area | 1 | METH_ENVEL | Rate x area uses the cost library (block 12); Lump sum = detailed BOQ override | Medium
Internal works (partitions, doors) – entry method | የውስጥ ሥራዎች (ክፍልፋይ፣ በር) – አገባብ | list | Rate x area | Rate x area | Rate x area | 1 | METH_INTERN | Rate x area uses the cost library (block 12); Lump sum = detailed BOQ override | Medium
Finishes – entry method | የማጠናቀቂያ ሥራዎች – አገባብ | list | Rate x area | Rate x area | Rate x area | 1 | METH_FINISH | Rate x area uses the cost library (block 12); Lump sum = detailed BOQ override | Medium
MEP (electrical, mechanical, plumbing) – entry method | ኤሌክትሪክ፣ ሜካኒካልና ቧንቧ – አገባብ | list | Rate x area | Rate x area | Rate x area | 1 | METH_MEP | Rate x area uses the cost library (block 12); Lump sum = detailed BOQ override | Medium
External works – entry method | የውጭ ሥራዎች – አገባብ | list | Rate x area | Rate x area | Rate x area | 1 | METH_EXTW | Rate x area uses the cost library (block 12); Lump sum = detailed BOQ override | Medium
Specialist systems (lifts, fire, CCTV) – entry method | ልዩ ሲስተሞች (ሊፍት፣ እሳት፣ ካሜራ) – አገባብ | list | Rate x area | Lump sum (BOQ) | Lump sum (BOQ) | 2 | METH_SPEC | Rate x area uses the cost library (block 12); Lump sum = detailed BOQ override | Medium
Preliminaries – lump sum (if BOQ) | ቅድመ-ሥራዎች – ጠቅላላ ዋጋ (BOQ) | ETB | 0 | 0 | 0 | 0 | LUMP_PRELIM | Used only when method = Lump sum (BOQ) | Medium
Substructure – lump sum (if BOQ) | የመሠረት ሥራ – ጠቅላላ ዋጋ (BOQ) | ETB | 0 | 0 | 0 | 0 | LUMP_SUBSTR | Used only when method = Lump sum (BOQ) | Medium
Superstructure (frame) – lump sum (if BOQ) | ከመሬት በላይ መዋቅር (ፍሬም) – ጠቅላላ ዋጋ (BOQ) | ETB | 0 | 0 | 0 | 0 | LUMP_SUPER | Used only when method = Lump sum (BOQ) | Medium
Envelope (walls, windows, roof) – lump sum (if BOQ) | ግድግዳ፣ መስኮትና ጣሪያ – ጠቅላላ ዋጋ (BOQ) | ETB | 0 | 0 | 0 | 0 | LUMP_ENVEL | Used only when method = Lump sum (BOQ) | Medium
Internal works (partitions, doors) – lump sum (if BOQ) | የውስጥ ሥራዎች (ክፍልፋይ፣ በር) – ጠቅላላ ዋጋ (BOQ) | ETB | 0 | 0 | 0 | 0 | LUMP_INTERN | Used only when method = Lump sum (BOQ) | Medium
Finishes – lump sum (if BOQ) | የማጠናቀቂያ ሥራዎች – ጠቅላላ ዋጋ (BOQ) | ETB | 0 | 0 | 0 | 0 | LUMP_FINISH | Used only when method = Lump sum (BOQ) | Medium
MEP (electrical, mechanical, plumbing) – lump sum (if BOQ) | ኤሌክትሪክ፣ ሜካኒካልና ቧንቧ – ጠቅላላ ዋጋ (BOQ) | ETB | 0 | 0 | 0 | 0 | LUMP_MEP | Used only when method = Lump sum (BOQ) | Medium
External works – lump sum (if BOQ) | የውጭ ሥራዎች – ጠቅላላ ዋጋ (BOQ) | ETB | 0 | 0 | 0 | 0 | LUMP_EXTW | Used only when method = Lump sum (BOQ) | Medium
Specialist systems (lifts, fire, CCTV) – lump sum (if BOQ) | ልዩ ሲስተሞች (ሊፍት፣ እሳት፣ ካሜራ) – ጠቅላላ ዋጋ (BOQ) | ETB | 0 | 45000000 | 95000000 | 45000000 | LUMP_SPEC | Used only when method = Lump sum (BOQ) | Medium
Superstructure uplift per storey above G+3 | ከG+3 በላይ ለእያንዳንዱ ፎቅ ጭማሪ | % | 2% | 2% | 2% | 2% | STOREY_UPLIFT | Taller frames cost more per m² | Medium
Basement extra (excavation, retaining, waterproofing) | የምድር ቤት ተጨማሪ ወጪ | ETB/m² | 12000 | 12000 | 12000 | 12000 | BASEMENT_RATE | Applied to basement gross area | Medium
Perimeter wall? | የአጥር ግንብ? | Y/N | No | Yes | Yes | 1 | COMPOUND_YN |  | Medium
Perimeter wall length | የአጥር ርዝመት | m | 0 | 120 | 180 | 120 | COMPOUND_LEN |  | Medium
Perimeter wall rate | የአጥር ዋጋ በሜትር | ETB/m | 18000 | 20000 | 20000 | 20000 | COMPOUND_RATE | Incl. gates | Medium
Septic tank / treatment plant? | የፍሳሽ ማስወገጃ? | Y/N | No | No | No | 0 | SEPTIC_YN | Not needed where sewer exists | Medium
Septic tanks – number | የፍሳሽ ጉድጓድ ብዛት | no. | 0 | 0 | 0 | 0 | SEPTIC_QTY |  | Medium
Septic tank – cost each | የአንዱ ዋጋ | ETB | 450000 | 450000 | 450000 | 450000 | SEPTIC_RATE |  | Medium
Water tanks? | የውሃ ታንከር? | Y/N | No | Yes | Yes | 1 | WTANK_YN |  | Medium
Water tanks – number | የውሃ ታንከር ብዛት | no. | 0 | 4 | 6 | 4 | WTANK_QTY |  | Medium
Water tank – cost each (incl. stand, pump) | የአንዱ ዋጋ | ETB | 250000 | 250000 | 250000 | 250000 | WTANK_RATE |  | Medium
Paving / landscaping area | የንጣፍ / የአትክልት ስፋት | m² | 0 | 250 | 400 | 250 | EXT_M2 |  | Medium
Paving / landscaping rate | የንጣፍ ዋጋ በካሬ | ETB/m² | 4500 | 4500 | 4500 | 4500 | EXT_RATE |  | Medium
Contingency (% of escalated hard cost) | ያልተጠበቀ ወጪ መጠባበቂያ | % | 10% | 8% | 8% | 8% | CONT_PCT |  | Medium
Design fee (% of hard cost) | የዲዛይን ክፍያ | % | 5% | 5% | 5% | 5% | DESIGN_PCT |  | Medium
Design fee paid upfront (month 1) | በመጀመሪያ ወር የሚከፈል ድርሻ | % | 50% | 50% | 50% | 50% | DESIGN_UPFRONT | Rest follows the S-curve | Medium
Supervision (% of escalated hard cost) | የቁጥጥር ክፍያ | % | 3% | 3% | 3% | 3% | SUPERV_PCT |  | Medium
Specialist consultancy (% of escalated hard cost) | የልዩ ባለሙያ አማካሪ ክፍያ | % | 0% | 0% | 1.5% | 0% | CONSULT_PCT | Hotel, façade, MEP, fire or traffic specialists; capitalised, follows the S-curve | Medium
Permits & municipal fees | ፈቃድና የማዘጋጃ ቤት ክፍያዎች | ETB | 0 | 2500000 | 6000000 | 2500000 | PERMITS | Paid month 1 | Medium
Furniture, fittings & equipment (FF&E) | የቤት ዕቃዎችና መገልገያዎች | ETB | 0 | 6000000 | 25000000 | 6000000 | FFE | Paid in the completion month; depreciated over the FF&E life | Medium
Pre-opening, leasing launch & marketing (expensed) | ከመክፈቻ በፊት ወጪና የገበያ ማስተዋወቂያ | ETB | 0 | 1500000 | 18000000 | 1500000 | PREOPEN | Paid in the completion month; expensed in P&L (not capitalised) but funded like construction cost | Medium
Construction cost escalation | የግንባታ ዋጋ ጭማሪ በዓመት | % p.a. | 15% | 15% | 15% | 15% | ESC_PA | Applied per month from the budget date | Medium
Use Rapha Construction Cost Index row instead | የራፋ የግንባታ ዋጋ ኢንዴክስ ይጠቀሙ | Y/N | No | No | No | 0 | INDEX_USE | Enter index values in the row on sheet 23 | Medium
Cost index at budget date | ኢንዴክስ በበጀት ቀን | index | 0 | 0 | 0 | 0 | INDEX_BASE | Rapha CCI value at START_DATE | Medium
Spend profile | የወጪ ስርጭት | list | S-curve (sigmoid) | S-curve (sigmoid) | S-curve (sigmoid) | 1 | SCURVE_TYPE |  | Medium
S-curve steepness | የS-ኩርባ ቅርጽ | x | 2 | 2 | 2 | 2 | SCURVE_A | 1 = linear, 2–3 = typical | Medium
Contractor retention | ከኮንትራክተር የሚያዝ ገንዘብ | % | 5% | 5% | 5% | 5% | RETENTION | Withheld from hard cost | Medium
Retention released – months after completion | የሚለቀቅበት ጊዜ | months | 12 | 12 | 12 | 12 | RET_REL_M |  | Medium
Share of capex carrying input VAT | ተ.እ.ታ ያለበት የወጪ ድርሻ | % | 70% | 70% | 70% | 70% | VAT_CAPEX_PCT | Reclaimable against output VAT or refunded | Medium
4. Land | 4. መሬት
Land arrangement | የመሬት ይዞታ ዓይነት | list | Lease (cash) | Lease (cash) | Partner in-kind (NCI) | 1 | LAND_TYPE | In-kind partner (e.g. city PPP) = non-controlling interest (NCI) | High
Land lease price / market value | የሊዝ ዋጋ / የገበያ ዋጋ | ETB | 0 | 150000000 | 250000000 | 150000000 | LAND_VALUE | Lease price, or agreed value of the land contributed in kind | High
Lease down payment | የሊዝ ቅድመ ክፍያ | % | 10% | 10% | 10% | 10% | LEASE_DP | Paid in month 1 | Medium
Lease instalment years | የሊዝ ክፍያ ዓመታት | years | 30 | 30 | 30 | 30 | LEASE_N | Annual instalments | Medium
Interest on unpaid lease balance | ባልተከፈለ ሊዝ ላይ ወለድ | % p.a. | 7% | 7% | 7% | 7% | LEASE_INT | Per lease contract; verify | Medium
5. Sales (prices per space are on sheet 13 Spaces) | 5. ሽያጭ
Sale price escalation | የሽያጭ ዋጋ ጭማሪ | % p.a. | 10% | 10% | 10% | 10% | PRICE_ESC |  | Medium
Presold in construction year 1 (% of saleable) | በ1ኛው የግንባታ ዓመት ቅድመ-ሽያጭ | % | 0% | 25% | 10% | 25% | PRESALE_1 |  | Low
Presold in construction year 2 | በ2ኛው ዓመት | % | 0% | 25% | 20% | 25% | PRESALE_2 |  | Low
Presold in construction year 3 | በ3ኛው ዓመት | % | 0% | 20% | 20% | 20% | PRESALE_3 |  | Low
Presold in construction year 4 | በ4ኛው ዓመት | % | 0% | 0% | 0% | 0% | PRESALE_4 | Total presales capped at 100% | Medium
After completion: % of unsold sold in O1 | ከግንባታ በኋላ በ1ኛው ዓመት የሚሸጥ | % | 60% | 60% | 60% | 60% | ABS_1 |  | Medium
… sold in O2 | በ2ኛው ዓመት | % | 40% | 40% | 40% | 40% | ABS_2 |  | Medium
… sold in O3 | በ3ኛው ዓመት | % | 0% | 0% | 0% | 0% | ABS_3 |  | Medium
… sold in O4 (any remainder sells in O5) | በ4ኛው ዓመት (ቀሪው በ5ኛው) | % | 0% | 0% | 0% | 0% | ABS_4 | Guarantees full sell-out by O5 | Medium
Payment plan: down payment at contract | ውል ሲፈረም ቅድመ ክፍያ | % | 30% | 30% | 30% | 30% | PAY_DP |  | Medium
Payment plan: instalments tied to construction progress | በግንባታ ሂደት የሚከፈል | % | 40% | 40% | 40% | 40% | PAY_INST | Balance is paid at handover | Medium
Sales commission | የሽያጭ ኮሚሽን | % | 2% | 2% | 2% | 2% | COMM_PCT | Expensed when revenue is recognised | Medium
Default / cancellation allowance | የውል ማፍረስ ቅናሽ | % | 2% | 2% | 2% | 2% | DEFAULT_PCT | Deducted from contract value | Medium
Marketing (% of contract value signed) | ማስታወቂያ | % | 1% | 1% | 1% | 1% | MKT_PCT |  | Medium
IFRS 15 revenue recognition for sales | የገቢ ዕውቅና ፖሊሲ | list | Point in time (handover) | Point in time (handover) | Point in time (handover) | 1 | REV_POLICY | Contract liability holds cash received before revenue | Medium
Share of sales value subject to VAT | ተ.እ.ታ የሚከፈልበት የሽያጭ ድርሻ | % | 0% | 0% | 0% | 0% | VAT_SALES_PCT | Treatment of building sales must be verified (VAT Proc. 1341/2024) | Medium
6. Leasing (rent and stabilised occupancy per space are on sheet 13 Spaces) | 6. ኪራይ
Lease-up: occupancy in O1 as % of stabilised | በ1ኛው ዓመት የተያዘ (ከተረጋጋው %) | % | 65% | 65% | 70% | 65% | RAMP_O1 | Applied to every space's stabilised occupancy | Low
Lease-up: occupancy in O2 as % of stabilised | በ2ኛው ዓመት | % | 87% | 87% | 90% | 87% | RAMP_O2 | O3 onwards = 100% of stabilised | Medium
Rent escalation | የኪራይ ጭማሪ | % p.a. | 8% | 8% | 8% | 8% | RENT_ESC | From today's prices | Medium
Key money (months of rent, received O1) | የቁልፍ ገንዘብ (በወራት ኪራይ) | months | 0 | 6 | 6 | 6 | KEY_MONTHS | Deferred and released over the period below (IFRS 16) | Medium
Key money release period | የቁልፍ ገንዘብ የሚታወቅበት ጊዜ | years | 5 | 5 | 5 | 5 | KEY_AMORT_Y |  | Medium
Service charge recovery (% of property opex) | የአገልግሎት ክፍያ ማስመለሻ | % | 60% | 60% | 60% | 60% | SC_RECOV |  | Medium
Bad debt (% of rent) | የማይሰበሰብ ዕዳ | % | 2% | 2% | 2% | 2% | BAD_DEBT |  | Medium
Residential rent exempt from VAT? | የመኖሪያ ኪራይ ከተ.እ.ታ ነፃ ነው? | Y/N | Yes | Yes | Yes | 1 | RES_VAT_EXEMPT | Share of rent subject to VAT is computed from the rent roll – verify | Medium
7. Hotel operator lease (used when sheet 13 has 'Hotel (operator lease)' space) | 7. የሆቴል ኦፕሬተር ኪራይ
Hotel rooms (keys) | የሆቴል ክፍሎች ብዛት | no. | 0 | 0 | 85 | 0 | HOT_KEYS |  | Medium
Average daily rate (today's prices) | አማካይ የቀን ክፍል ዋጋ | ETB/night | 0 | 0 | 12000 | 0 | HOT_ADR | Room revenue ÷ rooms sold | Low
ADR escalation | የክፍል ዋጋ ጭማሪ | % p.a. | 10% | 10% | 10% | 10% | HOT_ADR_ESC |  | Medium
Hotel occupancy O1 | የሆቴል ይዞታ O1 | % | 45% | 45% | 45% | 45% | HOT_OCC1 |  | Medium
Hotel occupancy O2 | የሆቴል ይዞታ O2 | % | 58% | 58% | 58% | 58% | HOT_OCC2 |  | Medium
Hotel occupancy – stabilised (O3+) | የተረጋጋ የሆቴል ይዞታ | % | 65% | 65% | 65% | 65% | HOT_OCC3 |  | Low
F&B and other hotel revenue (% of rooms revenue) | የምግብና ሌላ ገቢ (ከክፍል ገቢ %) | % | 60% | 60% | 60% | 60% | HOT_FB |  | Medium
Turnover rent (% of total hotel revenue) | ከጠቅላላ ገቢ የሚከፈል ኪራይ | % | 18% | 18% | 18% | 18% | HOT_TURN | Paid by the operator to the owner | Medium
Minimum guaranteed rent p.a. (today's prices) | ዝቅተኛ ዋስትና ያለው ኪራይ | ETB/yr | 0 | 0 | 20000000 | 0 | HOT_MIN | Escalated with rent escalation; owner receives the higher of minimum and turnover rent | Medium
8. Other income streams (year-1 amounts, today's prices) | 8. ሌሎች ገቢዎች
Stream 1 – name | ገቢ 1 – ስም | text | Signage & billboards | Signage & billboards | Signage & billboards | Signage & billboards | OINC1_NAME |  | Medium
Stream 1 – amount | ገቢ 1 – መጠን | ETB/yr | 0 | 400000 | 2400000 | 400000 | OINC1 |  | Medium
Stream 2 – name | ገቢ 2 – ስም | text | Telecom rooftop | Telecom rooftop | Telecom rooftop | Telecom rooftop | OINC2_NAME |  | Medium
Stream 2 – amount | ገቢ 2 – መጠን | ETB/yr | 0 | 200000 | 600000 | 200000 | OINC2 |  | Medium
Stream 3 – name | ገቢ 3 – ስም | text | Events & exhibitions | Events & exhibitions | Events & exhibitions | Events & exhibitions | OINC3_NAME |  | Medium
Stream 3 – amount | ገቢ 3 – መጠን | ETB/yr | 0 | 0 | 3000000 | 0 | OINC3 |  | Medium
Stream 4 – name | ገቢ 4 – ስም | text | Other | Other | Visitor parking (hourly) | Other | OINC4_NAME |  | Medium
Stream 4 – amount | ገቢ 4 – መጠን | ETB/yr | 0 | 0 | 1800000 | 0 | OINC4 |  | Medium
Other income escalation | የሌሎች ገቢዎች ጭማሪ | % p.a. | 8% | 8% | 8% | 8% | OI_ESC |  | Medium
9. Operating costs | 9. የሥራ ማስኬጃ ወጪ
Property opex basis | የወጪ አሰላል | list | % of rent | % of rent | % of rent | 1 | OPEX_METHOD |  | Medium
Property opex (% of rent) | የንብረት ወጪ (ከኪራይ %) | % | 15% | 15% | 15% | 15% | OPEX_PCT |  | Medium
Property opex (ETB/m²/yr, today's prices) | የንብረት ወጪ በካሬ | ETB/m²/yr | 1200 | 1200 | 1200 | 1200 | OPEX_M2 |  | Medium
Management fee (% of rent) | የአስተዳደር ክፍያ | % | 3% | 3% | 3% | 3% | MGMT_PCT |  | Medium
Insurance (% of building value p.a.) | መድን | % | 0.15% | 0.15% | 0.15% | 0.15% | INS_PCT |  | Medium
Property tax (% of land + building value p.a.) | የንብረት ግብር | % | 0.1% | 0.1% | 0.1% | 0.1% | PROPTAX_PCT | Verify current city proclamation | Medium
Maintenance reserve (% of building value p.a.) | የጥገና መጠባበቂያ | % | 0.5% | 0.5% | 0.5% | 0.5% | MAINT_PCT |  | Medium
Owner overheads (year 1, today's prices) | አጠቃላይ የአስተዳደር ወጪ | ETB/yr | 0 | 1200000 | 3000000 | 1200000 | OVERHEAD |  | Medium
Opex escalation | የወጪ ጭማሪ | % p.a. | 10% | 10% | 10% | 10% | OPEX_ESC |  | Medium
Share of opex carrying input VAT | ተ.እ.ታ ያለበት የወጪ ድርሻ | % | 50% | 50% | 50% | 50% | OPEX_VAT_PCT |  | Medium
Rent receivable days | የኪራይ ተሰብሳቢ ቀናት | days | 30 | 30 | 30 | 30 | RECV_DAYS |  | Medium
Opex payable days | የወጪ ተከፋይ ቀናት | days | 30 | 30 | 30 | 30 | PAY_DAYS |  | Medium
10. Financing | 10. ፋይናንስ
Equity share of funding need | የባለቤት ካፒታል ድርሻ | % | 40% | 40% | 50% | 40% | EQ_PCT | Debt = 1 − equity, capped by the loan cap | Medium
Draw order | የአወጣጥ ቅደም ተከተል | list | Equity first | Equity first | Equity first | 1 | DRAW_ORDER |  | Medium
Use presale cash to fund construction? | የቅድመ-ሽያጭ ገንዘብ ለግንባታ ይውላል? | Y/N | Yes | Yes | Yes | 1 | PRESALE_USE |  | Medium
Share of presale cash usable (rest in escrow) | ጥቅም ላይ የሚውለው ድርሻ | % | 80% | 80% | 80% | 80% | PRESALE_USE_PCT |  | Medium
Facility headroom for bank fees (% of debt) | ለባንክ ክፍያዎች ተጨማሪ የብድር መጠን | % | 3% | 3% | 3% | 3% | DEBT_HEADROOM | Lets the loan also fund the arrangement and commitment fees, so no gap is left for them | Medium
Loan cap (0 = no cap) | የብድር ጣሪያ | ETB | 0 | 0 | 0 | 0 | LOAN_CAP |  | Medium
Interest rate type | የወለድ ዓይነት | list | Fixed | Fixed | Fixed | 1 | RATE_TYPE |  | Medium
Interest rate (fixed, and during construction) | የወለድ መጠን | % p.a. | 15% | 15% | 15% | 15% | INT_RATE | Verify bank term sheet | Medium
Variable path – rate in O1 | ተለዋዋጭ ወለድ O1 | % p.a. | 15% | 15% | 15% | 15% | RATE_O1 | Used when type = Variable | Medium
Variable path – rate in O2 | ተለዋዋጭ ወለድ O2 | % p.a. | 15% | 15% | 15% | 15% | RATE_O2 | Used when type = Variable | Medium
Variable path – rate in O3 | ተለዋዋጭ ወለድ O3 | % p.a. | 15% | 15% | 15% | 15% | RATE_O3 | Used when type = Variable | Medium
Variable path – rate in O4 | ተለዋዋጭ ወለድ O4 | % p.a. | 15% | 15% | 15% | 15% | RATE_O4 | Used when type = Variable | Medium
Variable path – rate in O5 | ተለዋዋጭ ወለድ O5 | % p.a. | 15% | 15% | 15% | 15% | RATE_O5 | Used when type = Variable | Medium
Variable path – rate in O6 | ተለዋዋጭ ወለድ O6 | % p.a. | 15% | 15% | 15% | 15% | RATE_O6 | Used when type = Variable | Medium
Variable path – rate in O7 | ተለዋዋጭ ወለድ O7 | % p.a. | 15% | 15% | 15% | 15% | RATE_O7 | Used when type = Variable | Medium
Variable path – rate in O8 | ተለዋዋጭ ወለድ O8 | % p.a. | 15% | 15% | 15% | 15% | RATE_O8 | Used when type = Variable | Medium
Variable path – rate in O9 | ተለዋዋጭ ወለድ O9 | % p.a. | 15% | 15% | 15% | 15% | RATE_O9 | Used when type = Variable | Medium
Variable path – rate in O10 | ተለዋዋጭ ወለድ O10 | % p.a. | 15% | 15% | 15% | 15% | RATE_O10 | Used when type = Variable | Medium
Grace period after completion | ከግንባታ በኋላ የእፎይታ ጊዜ | months | 0 | 12 | 12 | 12 | GRACE_M | Interest during construction is always capitalised (IDC) | Medium
Interest during grace | በእፎይታ ጊዜ ወለድ | list | Interest-only (paid) | Interest-only (paid) | Capitalised | 1 | GRACE_TYPE | Capitalised suits lease-up: no debt service while occupancy builds | Medium
Tenor after completion (incl. grace) | የብድር ጊዜ (እፎይታን ጨምሮ) | years | 10 | 10 | 15 | 10 | TENOR_Y | Max 20 | Medium
Repayment type | የአከፋፈል ዓይነት | list | Annuity (PMT) | Annuity (PMT) | Annuity (PMT) | 1 | REPAY_TYPE |  | Medium
Balloon (% of balance at repayment start) | የመጨረሻ ትልቅ ክፍያ | % | 0% | 0% | 0% | 0% | BALLOON_PCT | Only for repayment type = Balloon | Medium
Repayment frequency | የክፍያ ድግግሞሽ | list | Monthly | Quarterly | Quarterly | 2 | FREQ |  | Medium
Arrangement fee (% of facility, excl. IDC) | የብድር ማመቻቻ ክፍያ | % | 1.5% | 1.5% | 1.5% | 1.5% | ARR_FEE | Base excludes IDC → no circularity | Medium
Commitment fee on undrawn (% p.a.) | ባልወጣ ብድር ላይ ክፍያ | % | 0.5% | 0.5% | 0.5% | 0.5% | COMMIT_FEE |  | Medium
Debt service reserve (months of next year's debt service) | የዕዳ ክፍያ መጠባበቂያ | months | 0 | 6 | 6 | 6 | DSRA_M |  | Medium
Cash sweep (% of sales proceeds to prepay loan) | ከሽያጭ ለብድር ቅድመ ክፍያ | % | 0% | 40% | 40% | 40% | SWEEP |  | Medium
DSCR covenant | የዕዳ ክፍያ ሽፋን ግዴታ | x | 1.3 | 1.3 | 1.3 | 1.3 | DSCR_COV | Dividends locked up below covenant | Medium
Return surplus cash to shareholders (capital reduction) | ትርፍ ገንዘብን ለባለአክሲዮኖች መመለስ | Y/N | Yes | Yes | Yes | 1 | DIST_SURPLUS | Subject to the DSCR lock-up test: first returns paid-in capital, then pays a special dividend from retained earnings | Medium
Minimum cash balance (operations) | ዝቅተኛ ጥሬ ገንዘብ | ETB | 0 | 2000000 | 5000000 | 2000000 | MIN_CASH |  | Medium
11. Tax, accounting & valuation | 11. ግብር፣ ሂሳብ አያያዝና ግምገማ
Corporate income tax | የንግድ ሥራ ገቢ ግብር | % | 30% | 30% | 30% | 30% | CIT | See TaxLaw register | High
Tax depreciation – buildings (straight line) | የሕንፃ የግብር እርጅና ቅናሽ | % p.a. | 5% | 5% | 5% | 5% | TAXDEP_BLD |  | Medium
Tax depreciation – plant & equipment pool (diminishing) | የመሣሪያ የግብር እርጅና ቅናሽ | % p.a. | 20% | 20% | 20% | 20% | TAXDEP_PLANT |  | Medium
Tax loss carry-forward period | ኪሳራ የሚሸጋገርበት ጊዜ | years | 5 | 5 | 5 | 5 | LCF_YEARS |  | Medium
Loss offset cap (% of taxable profit) | የኪሳራ ማካካሻ ጣሪያ | % | 100% | 100% | 100% | 100% | LCF_CAP |  | Medium
VAT rate | የተጨማሪ እሴት ታክስ መጣኔ | % | 15% | 15% | 15% | 15% | VAT_R |  | High
Excess input VAT refunded next year? | ትርፍ የግብዓት ታክስ ይመለሳል? | Y/N | Yes | Yes | Yes | 1 | VAT_REFUND_F | No = carried forward against output VAT | Medium
Undistributed profits tax | ያልተከፋፈለ ትርፍ ግብር | % | 10% | 10% | 10% | 10% | UPT_R | Closed-form, no circularity | Medium
Dividend payout ratio | የትርፍ ድርሻ ክፍፍል መጠን | % | 50% | 50% | 50% | 50% | DIV_PAYOUT |  | Medium
Dividend withholding tax (memo) | የትርፍ ድርሻ ተቀናሽ ግብር | % | 10% | 10% | 10% | 10% | DIV_WHT |  | Medium
Legal reserve transfer (% of profit) | ሕጋዊ መጠባበቂያ | % | 5% | 5% | 5% | 5% | LR_PCT |  | High
Legal reserve cap (% of share capital) | የሕጋዊ መጠባበቂያ ጣሪያ | % | 10% | 10% | 10% | 10% | LR_CAP |  | High
Useful life – building structure | የሕንፃ አገልግሎት ዘመን | years | 50 | 50 | 50 | 50 | LIFE_BLD |  | Medium
Useful life – building systems (MEP, lifts) | የሲስተሞች አገልግሎት ዘመን | years | 20 | 20 | 20 | 20 | LIFE_SYS |  | Medium
Useful life – FF&E | የዕቃዎች አገልግሎት ዘመን | years | 7 | 7 | 7 | 7 | LIFE_FFE |  | Medium
FF&E life cap | የዕቃዎች ዘመን ጣሪያ | years | 10 | 10 | 10 | 10 | FFE_LIFE_CAP |  | Medium
Project discount rate | የፕሮጀክት የቅናሽ መጠን | % | 18% | 18% | 18% | 18% | DISC_RATE |  | Medium
Cost of equity | የባለቤት ካፒታል ወጪ | % | 22% | 22% | 22% | 22% | COE |  | Medium
Terminal value method | የመጨረሻ ዋጋ ዘዴ | list | Exit cap rate | Exit cap rate | Exit cap rate | 1 | EXIT_METHOD |  | Medium
Exit cap rate | የመውጫ ካፕ ሬት | % | 9% | 9% | 9% | 9% | EXIT_CAP | On next-year NOI | Low
Exit EBITDA multiple | የመውጫ ብዜት | x | 10 | 10 | 10 | 10 | EXIT_MULT |  | Medium
Exit / disposal costs | የሽያጭ ወጪ | % | 2% | 2% | 2% | 2% | EXIT_COST |  | Medium
Equity IRR hurdle | ዝቅተኛ ተፈላጊ ተመላሽ | % | 20% | 20% | 20% | 20% | HURDLE |  | Medium
Marginal band below hurdle | የድንበር ክልል | % | 3% | 3% | 3% | 3% | MARGIN_BAND | Within this band below the hurdle = MARGINAL | Medium
[8 empty] | Inputs marked Low confidence | 7
12. Cost library – ETB per m² GFA, budget-date prices (link-ready to the Rapha Construction Cost Index) | 12. የወጪ መረጃ ቋት
|  |  | Basic | Standard | Premium |  |  | Applies to all data sets. Replace with Rapha Construction Cost Index rates when available.
Preliminaries | ቅድመ-ሥራዎች | ETB/m² | 1300 | 1600 | 2000 | 1600 | RATE_LIB
Substructure | የመሠረት ሥራ | ETB/m² | 3500 | 3800 | 4100 | 3800 | RATE_LIB
Superstructure (frame) | ከመሬት በላይ መዋቅር (ፍሬም) | ETB/m² | 7300 | 7800 | 8300 | 7800 | RATE_LIB
Envelope (walls, windows, roof) | ግድግዳ፣ መስኮትና ጣሪያ | ETB/m² | 3800 | 4800 | 6600 | 4800 | RATE_LIB
Internal works (partitions, doors) | የውስጥ ሥራዎች (ክፍልፋይ፣ በር) | ETB/m² | 1800 | 2400 | 3400 | 2400 | RATE_LIB
Finishes | የማጠናቀቂያ ሥራዎች | ETB/m² | 3300 | 5600 | 9200 | 5600 | RATE_LIB
MEP (electrical, mechanical, plumbing) | ኤሌክትሪክ፣ ሜካኒካልና ቧንቧ | ETB/m² | 3000 | 4400 | 6600 | 4400 | RATE_LIB
External works | የውጭ ሥራዎች | ETB/m² | 800 | 1200 | 1800 | 1200 | RATE_LIB
Specialist systems (lifts, fire, CCTV) | ልዩ ሲስተሞች (ሊፍት፣ እሳት፣ ካሜራ) | ETB/m² | 0 | 400 | 1200 | 400 | RATE_LIB
Total library rate (sum of elements) |  |  | 24800 | 32000 | 43200
Location factor – Addis Ababa |  | x | 1 |  |  |  | LOCF_ADDIS | Base = 1.00
Location factor – regional town |  | x | 0.92 |  |  |  | LOCF_REG | Lower labour cost, higher transport
Formulas:
ACTIVE (used by model) = CHOOSE(DATA_SET,[MY PROJECT (your values)],[SAMPLE 1 B+G+8 mixed],[SAMPLE 2 Trade centre])
Note on F12: Sample value — not market advice
Note on G12: Sample value — not market advice
Note on F13: Sample value — not market advice
Note on G13: Sample value — not market advice
Note on F14: Sample value — not market advice
Note on G14: Sample value — not market advice
Note on F15: Sample value — not market advice
Note on G15: Sample value — not market advice
Note on F16: Sample value — not market advice
Note on G16: Sample value — not market advice
Note on F17: Sample value — not market advice
Note on G17: Sample value — not market advice
Note on F18: Sample value — not market advice
Note on G18: Sample value — not market advice
Note on G20: Sample value — not market advice
Note on F21: Sample value — not market advice
Note on G21: Sample value — not market advice
Note on F22: Sample value — not market advice
Note on G22: Sample value — not market advice
Note on F23: Sample value — not market advice
Note on G23: Sample value — not market advice
Note on F24: Sample value — not market advice
Note on G24: Sample value — not market advice
Note on F25: Sample value — not market advice
Note on G25: Sample value — not market advice
Note on F26: Sample value — not market advice
Note on G26: Sample value — not market advice
Note on F27: Sample value — not market advice
Note on G27: Sample value — not market advice
Note on F28: Sample value — not market advice
Note on G28: Sample value — not market advice
Note on F29: Sample value — not market advice
Note on G29: Sample value — not market advice
Note on F30: Sample value — not market advice
Note on G30: Sample value — not market advice
Note on G31: Sample value — not market advice
Note on G32: Sample value — not market advice
Note on F37: Sample value — not market advice
Note on G37: Sample value — not market advice
Note on F38: Sample value — not market advice
Note on G38: Sample value — not market advice
Note on F39: Sample value — not market advice
Note on G39: Sample value — not market advice
Note on F40: Sample value — not market advice
Note on G40: Sample value — not market advice
Note on F41: Sample value — not market advice
Note on G41: Sample value — not market advice
Note on F42: Sample value — not market advice
Note on G42: Sample value — not market advice
Note on F43: Sample value — not market advice
Note on G43: Sample value — not market advice
Note on F44: Sample value — not market advice
Note on G44: Sample value — not market advice
Note on F45: Sample value — not market advice
Note on G45: Sample value — not market advice
Note on F54: Sample value — not market advice
Note on G54: Sample value — not market advice
Note on F55: Sample value — not market advice
Note on G55: Sample value — not market advice
Note on F56: Sample value — not market advice
Note on G56: Sample value — not market advice
Note on F57: Sample value — not market advice
Note on G57: Sample value — not market advice
Note on F58: Sample value — not market advice
Note on G58: Sample value — not market advice
Note on F59: Sample value — not market advice
Note on G59: Sample value — not market advice
Note on F60: Sample value — not market advice
Note on G60: Sample value — not market advice
Note on F62: Sample value — not market advice
Note on G62: Sample value — not market advice
Note on F63: Sample value — not market advice
Note on G63: Sample value — not market advice
Note on F64: Sample value — not market advice
Note on G64: Sample value — not market advice
Note on F65: Sample value — not market advice
Note on G65: Sample value — not market advice
Note on F66: Sample value — not market advice
Note on G66: Sample value — not market advice
Note on F67: Sample value — not market advice
Note on G67: Sample value — not market advice
Note on F68: Sample value — not market advice
Note on G68: Sample value — not market advice
Note on F69: Sample value — not market advice
Note on G69: Sample value — not market advice
Note on F70: Sample value — not market advice
Note on G70: Sample value — not market advice
Note on F71: Sample value — not market advice
Note on G71: Sample value — not market advice
Note on G72: Sample value — not market advice
Note on F73: Sample value — not market advice
Note on G73: Sample value — not market advice
Note on F74: Sample value — not market advice
Note on G74: Sample value — not market advice
Note on F75: Sample value — not market advice
Note on G75: Sample value — not market advice
Note on F76: Sample value — not market advice
Note on G76: Sample value — not market advice
Note on F77: Sample value — not market advice
Note on G77: Sample value — not market advice
Note on F79: Sample value — not market advice
Note on G79: Sample value — not market advice
Note on F80: Sample value — not market advice
Note on G80: Sample value — not market advice
Note on F81: Sample value — not market advice
Note on G81: Sample value — not market advice
Note on F82: Sample value — not market advice
Note on G82: Sample value — not market advice
Note on F83: Sample value — not market advice
Note on G83: Sample value — not market advice
Note on F85: Sample value — not market advice
Note on G85: Sample value — not market advice
Note on F86: Sample value — not market advice
Note on G86: Sample value — not market advice
Note on F87: Sample value — not market advice
Note on G87: Sample value — not market advice
Note on F88: Sample value — not market advice
Note on G88: Sample value — not market advice
Note on F89: Sample value — not market advice
Note on G89: Sample value — not market advice
Note on F91: Sample value — not market advice
Note on G91: Sample value — not market advice
Note on F92: Sample value — not market advice
Note on G92: Sample value — not market advice
Note on F93: Sample value — not market advice
Note on G93: Sample value — not market advice
Note on F94: Sample value — not market advice
Note on G94: Sample value — not market advice
Note on F96: Sample value — not market advice
Note on G96: Sample value — not market advice
Note on F97: Sample value — not market advice
Note on G97: Sample value — not market advice
Note on F100: Sample value — not market advice
Note on G100: Sample value — not market advice
Note on F101: Sample value — not market advice
Note on G101: Sample value — not market advice
Note on F102: Sample value — not market advice
Note on G102: Sample value — not market advice
Note on F103: Sample value — not market advice
Note on G103: Sample value — not market advice
Note on F104: Sample value — not market advice
Note on G104: Sample value — not market advice
Note on F105: Sample value — not market advice
Note on G105: Sample value — not market advice
Note on F108: Sample value — not market advice
Note on G108: Sample value — not market advice
Note on F109: Sample value — not market advice
Note on G109: Sample value — not market advice
Note on F110: Sample value — not market advice
Note on G110: Sample value — not market advice
Note on F111: Sample value — not market advice
Note on G111: Sample value — not market advice
Note on F112: Sample value — not market advice
Note on G112: Sample value — not market advice
Note on F113: Sample value — not market advice
Note on G113: Sample value — not market advice
Note on F114: Sample value — not market advice
Note on G114: Sample value — not market advice
Note on F115: Sample value — not market advice
Note on G115: Sample value — not market advice
Note on G117: Sample value — not market advice
Note on G118: Sample value — not market advice
Note on F119: Sample value — not market advice
Note on G119: Sample value — not market advice
Note on F120: Sample value — not market advice
Note on G120: Sample value — not market advice
Note on F121: Sample value — not market advice
Note on G121: Sample value — not market advice
Note on F122: Sample value — not market advice
Note on G122: Sample value — not market advice
Note on F123: Sample value — not market advice
Note on G123: Sample value — not market advice
Note on F124: Sample value — not market advice
Note on G124: Sample value — not market advice
Note on G125: Sample value — not market advice
Note on F128: Sample value — not market advice
Note on G128: Sample value — not market advice
Note on F130: Sample value — not market advice
Note on G130: Sample value — not market advice
Note on G132: Sample value — not market advice
Note on G134: Sample value — not market advice
Note on F135: Sample value — not market advice
Note on G135: Sample value — not market advice
Note on F137: Sample value — not market advice
Note on G137: Sample value — not market advice
Note on F138: Sample value — not market advice
Note on G138: Sample value — not market advice
Note on F139: Sample value — not market advice
Note on G139: Sample value — not market advice
Note on F140: Sample value — not market advice
Note on G140: Sample value — not market advice
Note on F141: Sample value — not market advice
Note on G141: Sample value — not market advice
Note on F142: Sample value — not market advice
Note on G142: Sample value — not market advice
Note on F143: Sample value — not market advice
Note on G143: Sample value — not market advice
Note on F144: Sample value — not market advice
Note on G144: Sample value — not market advice
Note on F145: Sample value — not market advice
Note on G145: Sample value — not market advice
Note on F146: Sample value — not market advice
Note on G146: Sample value — not market advice
Note on F147: Sample value — not market advice
Note on G147: Sample value — not market advice
Note on F148: Sample value — not market advice
Note on G148: Sample value — not market advice
Note on F150: Sample value — not market advice
Note on G150: Sample value — not market advice
Note on F151: Sample value — not market advice
Note on G151: Sample value — not market advice
Note on F152: Sample value — not market advice
Note on G152: Sample value — not market advice
Note on F153: Sample value — not market advice
Note on G153: Sample value — not market advice
Note on F154: Sample value — not market advice
Note on G154: Sample value — not market advice
Note on F156: Sample value — not market advice
Note on G156: Sample value — not market advice
Note on F157: Sample value — not market advice
Note on G157: Sample value — not market advice
Note on F158: Sample value — not market advice
Note on G158: Sample value — not market advice
Note on F159: Sample value — not market advice
Note on G159: Sample value — not market advice
Note on F160: Sample value — not market advice
Note on G160: Sample value — not market advice
Note on F161: Sample value — not market advice
Note on G161: Sample value — not market advice
Note on F162: Sample value — not market advice
Note on G162: Sample value — not market advice
Note on F163: Sample value — not market advice
Note on G163: Sample value — not market advice
Note on F164: Sample value — not market advice
Note on G164: Sample value — not market advice
Note on F165: Sample value — not market advice
Note on G165: Sample value — not market advice
Note on F166: Sample value — not market advice
Note on G166: Sample value — not market advice
Note on F167: Sample value — not market advice
Note on G167: Sample value — not market advice
Note on F168: Sample value — not market advice
Note on G168: Sample value — not market advice
Note on F169: Sample value — not market advice
Note on G169: Sample value — not market advice
Note on F170: Sample value — not market advice
Note on G170: Sample value — not market advice
Note on F171: Sample value — not market advice
Note on G171: Sample value — not market advice
Note on F173: Sample value — not market advice
Note on G173: Sample value — not market advice
Note on F174: Sample value — not market advice
Note on G174: Sample value — not market advice
Note on F175: Sample value — not market advice
Note on G175: Sample value — not market advice
Note on F176: Sample value — not market advice
Note on G176: Sample value — not market advice
Note on F177: Sample value — not market advice
Note on G177: Sample value — not market advice
Note on F178: Sample value — not market advice
Note on G178: Sample value — not market advice
Note on F179: Sample value — not market advice
Note on G179: Sample value — not market advice
Note on F180: Sample value — not market advice
Note on G180: Sample value — not market advice
Note on F182: Sample value — not market advice
Note on G182: Sample value — not market advice
Note on F183: Sample value — not market advice
Note on G183: Sample value — not market advice
Note on F184: Sample value — not market advice
Note on G184: Sample value — not market advice
Note on F185: Sample value — not market advice
Note on G185: Sample value — not market advice
Note on F186: Sample value — not market advice
Note on G186: Sample value — not market advice
Note on F187: Sample value — not market advice
Note on G187: Sample value — not market advice
Note on F188: Sample value — not market advice
Note on G188: Sample value — not market advice
Note on F189: Sample value — not market advice
Note on G189: Sample value — not market advice
Note on F190: Sample value — not market advice
Note on G190: Sample value — not market advice
Note on F191: Sample value — not market advice
Note on G191: Sample value — not market advice
Note on F192: Sample value — not market advice
Note on G192: Sample value — not market advice
Note on F193: Sample value — not market advice
Note on G193: Sample value — not market advice
Note on F194: Sample value — not market advice
Note on G194: Sample value — not market advice
Note on F195: Sample value — not market advice
Note on G195: Sample value — not market advice
Note on F196: Sample value — not market advice
Note on G196: Sample value — not market advice
Note on F197: Sample value — not market advice
Note on G197: Sample value — not market advice
Note on F198: Sample value — not market advice
Note on G198: Sample value — not market advice
Note on F199: Sample value — not market advice
Note on G199: Sample value — not market advice
Note on F200: Sample value — not market advice
Note on G200: Sample value — not market advice
Note on F201: Sample value — not market advice
Note on G201: Sample value — not market advice
Note on F202: Sample value — not market advice
Note on G202: Sample value — not market advice
Note on F203: Sample value — not market advice
Note on G203: Sample value — not market advice
Note on F204: Sample value — not market advice
Note on G204: Sample value — not market advice
Note on F205: Sample value — not market advice
Note on G205: Sample value — not market advice
Note on E211: Sample value — not market advice
Note on F211: Sample value — not market advice
Note on G211: Sample value — not market advice
Note on E212: Sample value — not market advice
Note on F212: Sample value — not market advice
Note on G212: Sample value — not market advice
Note on E213: Sample value — not market advice
Note on F213: Sample value — not market advice
Note on G213: Sample value — not market advice
Note on E214: Sample value — not market advice
Note on F214: Sample value — not market advice
Note on G214: Sample value — not market advice
Note on E215: Sample value — not market advice
Note on F215: Sample value — not market advice
Note on G215: Sample value — not market advice
Note on E216: Sample value — not market advice
Note on F216: Sample value — not market advice
Note on G216: Sample value — not market advice
Note on E217: Sample value — not market advice
Note on F217: Sample value — not market advice
Note on G217: Sample value — not market advice
Note on E218: Sample value — not market advice
Note on F218: Sample value — not market advice
Note on G218: Sample value — not market advice
Note on E219: Sample value — not market advice
Note on F219: Sample value — not market advice
Note on G219: Sample value — not market advice
Note on E222: Sample value — not market advice
Note on E223: Sample value — not market advice

## 11_Scenarios
11 · Scenarios – Base / Upside / Downside / Lender | [7 empty] | ◂ Start
ሁኔታዎች – መሠረታዊ፣ ብሩህ፣ አስቸጋሪ፣ ባንክ | [7 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Scenario adjustments (applied on top of the Inputs). Active = CHOOSE(SCEN, Base, Upside, Downside, Lender) | የሁኔታ ማስተካከያዎች
Driver | ነጂ | Unit | Base | Upside | Downside | Lender | ACTIVE | Name
Sale price | የሽያጭ ዋጋ | % | 0% | 10% | -10% | -15% | 0% | SC_PRICE
Rent | ኪራይ | % | 0% | 10% | -10% | -15% | 0% | SC_RENT
Occupancy (points) | የተያዘ መጠን | pts | 0% | 3% | -10% | -15% | 0% | SC_OCC
Construction cost | የግንባታ ወጪ | % | 0% | -5% | 10% | 15% | 0% | SC_COST
Construction delay | የግንባታ መዘግየት | months | 0 | 0 | 6 | 6 | 0 | SC_DELAY
Interest rate (points) | የወለድ መጠን | pts | 0% | -1% | 2% | 3% | 0% | SC_RATE
Presales achieved | ቅድመ-ሽያጭ | % | 0% | 10% | -25% | -40% | 0% | SC_PRESALE
Exit cap rate (points) | የመውጫ ካፕ ሬት | pts | 0% | -0.5% | 1% | 1.5% | 0% | SC_EXITCAP
Operating costs | የሥራ ማስኬጃ ወጪ | % | 0% | -5% | 10% | 15% | 0% | SC_OPEX
Cost escalation (points) | የዋጋ ጭማሪ | pts | 0% | -2% | 5% | 5% | 0% | SC_ESC
Rent escalation (points) | የኪራይ ጭማሪ | pts | 0% | 1% | -2% | -3% | 0% | SC_RESC
Sale price escalation (points) | የሽያጭ ዋጋ ጭማሪ | pts | 0% | 2% | -3% | -5% | 0% | SC_PESC
Default / cancellations (points) | የውል ማፍረስ | pts | 0% | -1% | 3% | 5% | 0% | SC_DEFAULT
Discount rates (points) | የቅናሽ መጠን | pts | 0% | 0% | 1% | 2% | 0% | SC_DISC
Sales absorption speed | የሽያጭ ፍጥነት | % | 0% | 20% | -30% | -50% | 0% | SC_ABS
Effective drivers used by the engine (scenario × flex cell) | ሞዴሉ የሚጠቀማቸው ውጤታማ ነጂዎች
Active scenario (1–4) |  | 1
Sale price factor |  | 1
Rent factor |  | 1
Construction cost factor |  | 1
Opex factor |  | 1
Occupancy points added |  | 0%
Occupancy factor |  | 1
Interest rate points added |  | 0%
Interest rate factor |  | 1
Effective base interest rate |  | 15%
Effective construction months (incl. delay) |  | 30
Presale factor |  | 1
Effective exit cap rate |  | 9%
Effective cost escalation |  | 15%
Effective rent escalation |  | 8%
Effective sale-price escalation |  | 10%
Effective default allowance |  | 2%
Effective project discount rate |  | 18%
Effective cost of equity |  | 22%
Absorption factor |  | 1

## 12_TaxLaw
12 · Tax law register |  |  |  |  | ◂ Start
የግብር ሕግ መዝገብ |  |  |  |  | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Rates used by the model and their statutory source – YOU MUST CONFIRM CURRENT RATES BEFORE USE | የግብር መጣኔዎች
Item | Rate used | Statutory source | Last verified | Verify before use | Model name
Corporate income tax | 30% | Federal Income Tax Proclamation No. 979/2016, Art. 19(1) – 30% for bodies | 2026-10-05 | YES – verify | CIT
Tax depreciation – buildings | 5% | Proc. 979/2016, Art. 25 & Income Tax Regulation No. 410/2017 – buildings 5% straight line | 2026-10-05 | YES – verify | TAXDEP_BLD
Tax depreciation – plant & equipment | 20% | Proc. 979/2016, Art. 25 – other business assets 20% (pool / diminishing value per spec) | 2026-10-05 | YES – verify | TAXDEP_PLANT
Loss carry-forward period | 500% | Proc. 979/2016, Art. 26 – losses carried forward up to 5 years (limits on number of carry-forwards apply) | 2026-10-05 | YES – verify | LCF_YEARS
Loss offset cap | 100% | Model assumption – no statutory cap identified; set below 100% if a cap applies | 2026-10-05 | YES – verify | LCF_CAP
VAT – standard rate | 15% | Value Added Tax Proclamation No. 1341/2024 – 15% standard rate | 2026-10-05 | YES – verify | VAT_R
VAT on sale of buildings (share taxable) | 0% | Proc. 1341/2024 – exemptions for residential dwellings; confirm treatment of new-build sales | 2026-10-05 | YES – verify | VAT_SALES_PCT
VAT on rent (share taxable – computed from the rent roll) | 100% | Proc. 1341/2024 – residential rent exempt; commercial rent taxable. Model: 1 − exempt residential rent ÷ total rent | 2026-10-05 | YES – verify | RENT_VAT_PCT
Undistributed profits tax | 10% | Proc. 979/2016, Art. 55 – undistributed / non-reinvested profits treated as dividend (10%) | 2026-10-05 | YES – verify | UPT_R
Dividend withholding tax | 10% | Proc. 979/2016, Art. 55 – 10% on dividends | 2026-10-05 | YES – verify | DIV_WHT
Legal reserve transfer | 5% | Commercial Code of Ethiopia, Proc. No. 1243/2021, Art. 434 – 5% of profits | 2026-10-05 | YES – verify | LR_PCT
Legal reserve cap | 10% | Commercial Code, Art. 434 – until reserve reaches 10% of capital | 2026-10-05 | YES – verify | LR_CAP
Property tax | 0.1% | City property-tax proclamation (Addis Ababa) – rate and base to be confirmed | 2026-10-05 | YES – verify | PROPTAX_PCT
Land lease down payment | 10% | Urban Lands Lease Holding Proclamation No. 721/2011 and city regulations – minimum down payment | 2026-10-05 | YES – verify | LEASE_DP
Land lease instalment period | 30 | Proc. 721/2011 – instalment period per lease contract | 2026-10-05 | YES – verify | LEASE_N
Interest on unpaid lease | 7% | Lease contract / city regulation – usually linked to the NBE / bank lending rate | 2026-10-05 | YES – verify | LEASE_INT
Note: 'Last verified' records a desk review on that date, not confirmation against the official gazette. Tax law in Ethiopia changes frequently – confirm every rate with the Ministry of Revenue, the city administration or a licensed tax adviser before relying on results.
ማሳሰቢያ፡ ሞዴሉን ከመጠቀምዎ በፊት ሁሉንም የግብር መጣኔዎች ከገቢዎች ሚኒስቴር ወይም ፈቃድ ካለው የግብር አማካሪ ያረጋግጡ።

## 13_Spaces
13 · Space schedule & rent roll | [16 empty] | ◂ Start
የቦታ ዝርዝርና የኪራይ መዝገብ | [16 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Every lettable or saleable space, one row each. The ACTIVE block at the bottom uses the data set chosen on Start and the project type: Build-to-Sell sells all saleable space, Build-to-Rent keeps it, Mixed uses the Sold % column. Hotel, owner-occupied and rent-free space is never sold. Hotel income comes from Inputs block 7.
MY PROJECT – your spaces (type here)
# | Space / unit name | Type | Net area m² | Sold % (Mixed) | Sale price ETB/m² | Rent ETB/m²/month | Stabilised occupancy
1 |  | Retail | 0 | 0% | 0 | 0 | 92%
2 |  | Retail | 0 | 0% | 0 | 0 | 92%
3 |  | Retail | 0 | 0% | 0 | 0 | 92%
4 |  | Retail | 0 | 0% | 0 | 0 | 92%
5 |  | Retail | 0 | 0% | 0 | 0 | 92%
6 |  | Retail | 0 | 0% | 0 | 0 | 92%
7 |  | Retail | 0 | 0% | 0 | 0 | 92%
8 |  | Retail | 0 | 0% | 0 | 0 | 92%
9 |  | Retail | 0 | 0% | 0 | 0 | 92%
10 |  | Retail | 0 | 0% | 0 | 0 | 92%
11 |  | Retail | 0 | 0% | 0 | 0 | 92%
12 |  | Retail | 0 | 0% | 0 | 0 | 92%
SAMPLE 1 – B+G+8 mixed-use
# | Space / unit name | Type | Net area m² | Sold % (Mixed) | Sale price ETB/m² | Rent ETB/m²/month | Stabilised occupancy
1 | Ground-floor shops | Retail | 552 | 0% | 180000 | 2000 | 92%
2 | First-floor shops | Retail | 553 | 0% | 180000 | 2000 | 92%
3 | Apartments F2–F8 | Residential | 3360 | 100% | 125000 | 650 | 92%
4 |  | Retail | 0 | 0% | 0 | 0 | 92%
5 |  | Retail | 0 | 0% | 0 | 0 | 92%
6 |  | Retail | 0 | 0% | 0 | 0 | 92%
7 |  | Retail | 0 | 0% | 0 | 0 | 92%
8 |  | Retail | 0 | 0% | 0 | 0 | 92%
9 |  | Retail | 0 | 0% | 0 | 0 | 92%
10 |  | Retail | 0 | 0% | 0 | 0 | 92%
11 |  | Retail | 0 | 0% | 0 | 0 | 92%
12 |  | Retail | 0 | 0% | 0 | 0 | 92%
SAMPLE 2 – B+G+10 trade centre & hotel
# | Space / unit name | Type | Net area m² | Sold % (Mixed) | Sale price ETB/m² | Rent ETB/m²/month | Stabilised occupancy
1 | Ground-floor shops | Retail | 1000 | 30% | 230000 | 2200 | 95%
2 | Retail galleria F1–F2 | Retail | 1900 | 30% | 190000 | 1500 | 90%
3 | Wholesale showrooms B1 | Showroom / wholesale | 1300 | 0% | 120000 | 900 | 90%
4 | Food court F3 | Food & beverage | 800 | 0% | 0 | 1400 | 90%
5 | Offices F4–F6 | Office | 2900 | 0% | 110000 | 800 | 85%
6 | Hotel F7–F10 (85 keys) | Hotel (operator lease) | 4100 | 0% | 0 | 0 | 100%
7 | Owner head office F3 | Owner-occupied | 200 | 0% | 0 | 0 | 100%
8 | City one-stop service desk | Rent-free / public service | 150 | 0% | 0 | 0 | 100%
9 | Tenant parking B2 | Parking | 1500 | 0% | 0 | 120 | 85%
10 | Storage units B1 | Warehouse / storage | 300 | 0% | 0 | 500 | 85%
11 |  | Retail | 0 | 0% | 0 | 0 | 92%
12 |  | Retail | 0 | 0% | 0 | 0 | 92%
ACTIVE – used by the model (do not type here) | [8 empty] | ያገለገለ – ሞዴሉ የሚጠቀመው
# | Space / unit name | Type | Net area m² | Sold % (Mixed) | Sale price ETB/m² | Rent ETB/m²/month | Stabilised occupancy | Type code | Share sold | Share owner-held | Share let | Sold m² | Let m² | Owner-held m² | Sales value (today) | Potential rent p.a. | Rent at stabilised occupancy
1 | Ground-floor shops | Retail | 552 | 0% | 180000 | 2000 | 92% | 1 | 0% | 0% | 100% | 0 | 552 | 0 | 0 | 13248000 | 12188160
2 | First-floor shops | Retail | 553 | 0% | 180000 | 2000 | 92% | 1 | 0% | 0% | 100% | 0 | 553 | 0 | 0 | 13272000 | 12210240
3 | Apartments F2–F8 | Residential | 3360 | 100% | 125000 | 650 | 92% | 3 | 100% | 0% | 0% | 3360 | 0 | 0 | 420000000 | 0 | 0
4 |  | Retail | 0 | 0% | 0 | 0 | 92% | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
5 |  | Retail | 0 | 0% | 0 | 0 | 92% | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Retail | 0 | 0% | 0 | 0 | 92% | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Retail | 0 | 0% | 0 | 0 | 92% | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Retail | 0 | 0% | 0 | 0 | 92% | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
9 |  | Retail | 0 | 0% | 0 | 0 | 92% | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Retail | 0 | 0% | 0 | 0 | 92% | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
11 |  | Retail | 0 | 0% | 0 | 0 | 92% | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
12 |  | Retail | 0 | 0% | 0 | 0 | 92% | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL |  | 4465 | [8 empty] | 3360 | 1105 | 0 | 420000000 | 26520000 | 24398400
| Hotel space (net m²) |  | 0
| Residential rent at stabilised occupancy |  | 0
| Spaces entered |  | 3
Mix by type (net m²) – chart source
| Retail |  | 1105
| Office |  | 0
| Residential |  | 3360
| Showroom / wholesale |  | 0
| Food & beverage |  | 0
| Warehouse / storage |  | 0
| Hotel (operator lease) |  | 0
| Parking |  | 0
| Owner-occupied |  | 0
| Rent-free / public service |  | 0
| Other |  | 0
Note on E25: Sample value — not market advice
Note on G25: Sample value — not market advice
Note on H25: Sample value — not market advice
Note on I25: Sample value — not market advice
Note on E26: Sample value — not market advice
Note on G26: Sample value — not market advice
Note on H26: Sample value — not market advice
Note on I26: Sample value — not market advice
Note on E27: Sample value — not market advice
Note on F27: Sample value — not market advice
Note on G27: Sample value — not market advice
Note on H27: Sample value — not market advice
Note on I27: Sample value — not market advice
Note on I28: Sample value — not market advice
Note on I29: Sample value — not market advice
Note on I30: Sample value — not market advice
Note on I31: Sample value — not market advice
Note on I32: Sample value — not market advice
Note on I33: Sample value — not market advice
Note on I34: Sample value — not market advice
Note on I35: Sample value — not market advice
Note on I36: Sample value — not market advice
Note on E40: Sample value — not market advice
Note on F40: Sample value — not market advice
Note on G40: Sample value — not market advice
Note on H40: Sample value — not market advice
Note on I40: Sample value — not market advice
Note on E41: Sample value — not market advice
Note on F41: Sample value — not market advice
Note on G41: Sample value — not market advice
Note on H41: Sample value — not market advice
Note on I41: Sample value — not market advice
Note on E42: Sample value — not market advice
Note on G42: Sample value — not market advice
Note on H42: Sample value — not market advice
Note on I42: Sample value — not market advice
Note on E43: Sample value — not market advice
Note on H43: Sample value — not market advice
Note on I43: Sample value — not market advice
Note on E44: Sample value — not market advice
Note on G44: Sample value — not market advice
Note on H44: Sample value — not market advice
Note on I44: Sample value — not market advice
Note on E45: Sample value — not market advice
Note on I45: Sample value — not market advice
Note on E46: Sample value — not market advice
Note on I46: Sample value — not market advice
Note on E47: Sample value — not market advice
Note on I47: Sample value — not market advice
Note on E48: Sample value — not market advice
Note on H48: Sample value — not market advice
Note on I48: Sample value — not market advice
Note on E49: Sample value — not market advice
Note on H49: Sample value — not market advice
Note on I49: Sample value — not market advice
Note on I50: Sample value — not market advice
Note on I51: Sample value — not market advice

## 20_Timeline
20 · Timeline & flags | [15 empty] | ◂ Start
የጊዜ ሰሌዳና ጠቋሚዎች | [15 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Period |  | Total | C1 | C2 | C3 | C4 | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | O9 | O10
Period end (Gregorian) |  |  | 2027-12-31 | 2028-12-31 | 2029-06-30 | 2029-06-30 | 2030-06-30 | 2031-06-30 | 2032-06-30 | 2033-06-30 | 2034-06-30 | 2035-06-30 | 2036-06-30 | 2037-06-30 | 2038-06-30 | 2039-06-30
Ethiopian calendar year |  |  | EC 2020 | EC 2021 | EC 2021 | EC 2021 | EC 2022 | EC 2023 | EC 2024 | EC 2025 | EC 2026 | EC 2027 | EC 2028 | EC 2029 | EC 2030 | EC 2031
Annual periods: C1–C4 construction years, O1–O10 operating years | ዓመታዊ ጊዜያት
Period number | no. |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Period label |  |  | C1 | C2 | C3 | C4 | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | O9 | O10
Construction-year index | no. |  | 1 | 2 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating-year index | no. |  | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Months in period | months | 150 | 12 | 12 | 6 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
Period active flag | flag |  | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Construction flag | flag | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating flag | flag | 10 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Completion (COD) period flag | flag | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
First month index | no. |  | 1 | 13 | 25 | 37 | 31 | 43 | 55 | 67 | 79 | 91 | 103 | 115 | 127 | 139
Last month index | no. |  | 12 | 24 | 30 | 30 | 42 | 54 | 66 | 78 | 90 | 102 | 114 | 126 | 138 | 150
Period end date | date |  | 2027-12-31 | 2028-12-31 | 2029-06-30 | 2029-06-30 | 2030-06-30 | 2031-06-30 | 2032-06-30 | 2033-06-30 | 2034-06-30 | 2035-06-30 | 2036-06-30 | 2037-06-30 | 2038-06-30 | 2039-06-30
Years from start (end of period) | years |  | 1 | 2.0027 | 2.4986 | 2.4986 | 3.4986 | 4.4986 | 5.5014 | 6.5014 | 7.5014 | 8.5014 | 9.5041 | 10.5041 | 11.5041 | 12.5041
Period length | years | 12.5 | 1 | 1 | 0.5 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Gregorian year (period end) |  |  | GC 2027 | GC 2028 | GC 2029 | GC 2029 | GC 2030 | GC 2031 | GC 2032 | GC 2033 | GC 2034 | GC 2035 | GC 2036 | GC 2037 | GC 2038 | GC 2039
Ethiopian calendar year (period end) |  |  | EC 2020 | EC 2021 | EC 2021 | EC 2021 | EC 2022 | EC 2023 | EC 2024 | EC 2025 | EC 2026 | EC 2027 | EC 2028 | EC 2029 | EC 2030 | EC 2031
Discount factor @ project rate | x |  | 0.84746 | 0.71786 | 0.66129 | 0.66129 | 0.56042 | 0.47493 | 0.4023 | 0.34093 | 0.28893 | 0.24485 | 0.20741 | 0.17577 | 0.14896 | 0.12623
Discount factor @ cost of equity | x |  | 0.81967 | 0.6715 | 0.60844 | 0.60844 | 0.49872 | 0.40879 | 0.33489 | 0.2745 | 0.225 | 0.18443 | 0.15109 | 0.12384 | 0.10151 | 0.083205
Key timing scalars | ቁልፍ የጊዜ መረጃዎች
Operating horizon (fixed design horizon) | years | 10 | GC 2027 EC 2020: Statements always show C1–C4 + O1–O10
Number of construction periods used | no. | 3
Completion (COD) date | date | 2029-06-30
End of operating horizon (O10) | date | 2039-06-30
Monthly timeline (construction up to 48 months + 240 months of loan life) | ወርሃዊ የጊዜ ሰሌዳ
Month index t | no. |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288
Month start date | date | time axis 2027-01-01 to 2050-12-01
Construction month flag | flag | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Months after completion k | no. |  | -29 | -28 | -27 | -26 | -25 | -24 | -23 | -22 | -21 | -20 | -19 | -18 | -17 | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258
Operating year (within O1–O10) | no. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan year after completion | no. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22
Annual period index (1–14, 0 = beyond horizon) | no. |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 21_Area
21 · Area programme | [17 empty] | ◂ Start
የቦታና የወለል ስፋት ፕሮግራም | [17 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Floors (from Inputs block 2) | ፎቆች
Floor |  |  | Basement 2 | Basement 1 | Ground floor | Floor 1 | Floor 2 | Floor 3 | Floor 4 | Floor 5 | Floor 6 | Floor 7 | Floor 8 | Floor 9 | Floor 10 | Floor 11 | Floor 12 | Floor 13
Gross floor area | m² | 6400 | 0 | 900 | 650 | 650 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 0 | 0 | 0 | 0 | 0
Basement flag | flag |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Floor built flag | flag | 10 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Building summary | የሕንፃ ማጠቃለያ
Gross floor area (GFA) | m² | 6400
Basement gross area | m² | 900
Above-ground gross area | m² | 5500
Above-ground floors built | no. | 9
Basement levels built | no. | 1
Building configuration |  | B1+G+8
Ground-floor footprint | m² | 650
Actual FAR (above-ground GFA ÷ plot) | x | 5.5
Space schedule summary (from sheet 13) – IAS 2 sold · IAS 40 let · IAS 16 owner-held | የቦታ ማጠቃለያ
Net area (all spaces) | m² | 4465
Net-to-gross ratio | % | 69.77%
Saleable area | m² | 3360
Lettable area (incl. hotel) | m² | 1105
Owner-held area (owner-occupied, rent-free) | m² | 0
of which hotel (operator lease) | m² | 0
Cost share → inventory (IAS 2) | % | 75.25%
Cost share → investment property (IAS 40) | % | 24.75%
Cost share → owner-held PPE (IAS 16) | % | 0%
Cost share retained (IAS 40 + IAS 16) | % | 24.75%
Sales value at today's prices | ETB | 420000000
Blended sale price (today, after scenario & flex) | ETB/m² | 125000
Potential rent p.a. – spaces (today's prices, 100% let) | ETB | 26520000
Stabilised occupancy – rent-weighted | % | 92%
Hotel rent at stabilisation (today's prices) | ETB | 0
Share of rent subject to VAT (residential exempt if set) | % | 100%
Net area above gross area (should be 0) | m² | 0
Share reconciliation (should be 100%) | % | 100%
Hotel inputs consistent (space ⇔ keys & rate) | flag | 0

## 22_Capex
22 · Capex – elemental BOQ, soft costs, land | [9 empty] | ◂ Start
የካፒታል ወጪ – የግንባታ ዝርዝር | [9 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Cost drivers | የወጪ መወሰኛዎች
Finish level (1 Basic · 2 Standard · 3 Premium) | code | 2
Location factor | x | 1
Storey factor (superstructure) | x | 1.1
Construction cost factor (scenario × flex) | x | 1
Elemental cost plan (budget-date prices) | የግንባታ ወጪ ዝርዝር (በበጀት ቀን ዋጋ)
Element | Unit | Budget (ETB) | Library rate | Location | Storey | Area m² | Rate × area | Method | Lump sum | Pre-flex
Preliminaries · ቅድመ-ሥራዎች | ETB | 10240000 | 1600 | 1 | 1 | 6400 | 10240000 | 1 | 0 | 10240000
Substructure · የመሠረት ሥራ | ETB | 24320000 | 3800 | 1 | 1 | 6400 | 24320000 | 1 | 0 | 24320000
Superstructure (frame) · ከመሬት በላይ መዋቅር (ፍሬም) | ETB | 54912000 | 7800 | 1 | 1.1 | 6400 | 54912000 | 1 | 0 | 54912000
Envelope (walls, windows, roof) · ግድግዳ፣ መስኮትና ጣሪያ | ETB | 30720000 | 4800 | 1 | 1 | 6400 | 30720000 | 1 | 0 | 30720000
Internal works (partitions, doors) · የውስጥ ሥራዎች (ክፍልፋይ፣ በር) | ETB | 15360000 | 2400 | 1 | 1 | 6400 | 15360000 | 1 | 0 | 15360000
Finishes · የማጠናቀቂያ ሥራዎች | ETB | 35840000 | 5600 | 1 | 1 | 6400 | 35840000 | 1 | 0 | 35840000
MEP (electrical, mechanical, plumbing) · ኤሌክትሪክ፣ ሜካኒካልና ቧንቧ | ETB | 28160000 | 4400 | 1 | 1 | 6400 | 28160000 | 1 | 0 | 28160000
External works · የውጭ ሥራዎች | ETB | 7680000 | 1200 | 1 | 1 | 6400 | 7680000 | 1 | 0 | 7680000
Specialist systems (lifts, fire, CCTV) · ልዩ ሲስተሞች (ሊፍት፣ እሳት፣ ካሜራ) | ETB | 45000000 | 400 | 1 | 1 | 6400 | 2560000 | 2 | 45000000 | 45000000
Basement extra (excavation, retaining, waterproofing) | ETB | 10800000
Compound wall | ETB | 2400000
Septic tank(s) | ETB | 0
Water tank(s) | ETB | 1000000
Paving / landscaping | ETB | 1125000
HARD COST AT BUDGET-DATE PRICES | ETB | 267557000
Total development cost (TDC) | ጠቅላላ የልማት ወጪ
Hard cost escalated (S-curve × escalation) | ETB | 319322348.7224
of which escalation | ETB | 51765348.7224
Contingency | ETB | 25545787.8978
Design fees | ETB | 13377850
Supervision | ETB | 9579670.4617
Specialist consultancy | ETB | 0
Permits & fees | ETB | 2500000
FF&E / furniture | ETB | 6000000
CONSTRUCTION COST (excl. land & finance) | ETB | 376325657.0819
Land | ETB | 150000000
Arrangement fee (IAS 23) | ETB | 4113064.0858
Commitment fees (IAS 23) | ETB | 2932654.2481
Interest during construction – capitalised (IAS 23) | ETB | 17456846.4028
Finance costs capitalised | ETB | 24502564.7368
TOTAL DEVELOPMENT COST (TDC) | ETB | 550828221.8186
Check: TDC vs monthly capex accrual | ETB | 0
TDC per gross m² | ETB/m² | 86066.9097
TDC per net m² | ETB/m² | 123365.7832
Construction cost per gross m² | ETB/m² | 58800.8839
Memo: TDC in USD | USD | 3553730.4633
Allocation of TDC (IAS 2 / IAS 40 / IAS 16) | የወጪ ድልድል
Inventory – units for sale (IAS 2) | ETB | 414509031.4246
Investment property – let (IAS 40, cost model) | ETB | 136319190.3941
Owner-occupied (IAS 16) | ETB | 0
Allocation difference (should be 0) | ETB | 0
Depreciation components of retained assets | የእርጅና ቅናሽ ክፍሎች
Land fraction of TDC | % | 27.23%
FF&E fraction of TDC | % | 1.089%
Systems share of hard cost (MEP + specialist) | % | 27.34%
Systems fraction of TDC | % | 19.6%
Structure fraction of TDC | % | 52.08%
Retained cost (IAS 40 + IAS 16) | ETB | 136319190.3941
Depreciable base – structure | ETB | 70994097.6249
Depreciable base – systems | ETB | 26718149.8801
Depreciable base – FF&E | ETB | 1484882.4188
Land (not depreciated) | ETB | 37122060.4703
Cost breakdown for charts (sums to TDC) | የወጪ ክፍፍል
Substructure & basement | ETB | 35120000
Frame & envelope | ETB | 85632000
Internal works & finishes | ETB | 51200000
MEP & specialist systems | ETB | 73160000
Preliminaries & external works | ETB | 22445000
Escalation & contingency | ETB | 77311136.6202
Fees, consultancy & permits | ETB | 25457520.4617
Furniture & FF&E | ETB | 6000000
Land | ETB | 150000000
Finance costs (fees + IDC) | ETB | 24502564.7368
Total (= TDC) | ETB | 550828221.8186
Contractor payment stages (construction cost incl. escalation & contingency) | ለኮንትራክተር የክፍያ ደረጃዎች
1 Mobilisation & site set-up | ETB | 13198868.7233
2 Foundation / substructure | ETB | 45267995.0743
3 Frame (columns, beams, slabs) | ETB | 70778933.5285
4 Walls, windows & roof | ETB | 39596606.1698
5 MEP & internal works | ETB | 114098033.1429
6 Finishes & external works | ETB | 61927699.9814
Total contractor payments | ETB | 344868136.6202

## 23_Construction
23 · Construction – monthly S-curve, funding waterfall, presales | [15 empty] | ◂ Start
የግንባታ ወርሃዊ ወጪ፣ የገንዘብ ምንጭና ቅድመ-ሽያጭ | [15 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Month |  | Total | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36 | M37 | M38 | M39 | M40 | M41 | M42 | M43 | M44 | M45 | M46 | M47 | M48
Month start | time axis 2027-01-01 to 2030-12-01
Annual period |  |  | C1 | C1 | C1 | C1 | C1 | C1 | C1 | C1 | C1 | C1 | C1 | C1 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C3 | C3 | C3 | C3 | C3 | C3 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O2 | O2 | O2 | O2 | O2 | O2
Timing | ጊዜ
Construction month flag | flag | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Annual period index | no. |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6
Spend profile (S-curve) and escalation | የወጪ ስርጭትና የዋጋ ጭማሪ
User % profile (input row – used if profile = User %) | % | 0% | bar: 2027-01-01 to 2030-12-01
Rapha Construction Cost Index (input row, optional) | index |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative progress | % |  | 0.1188% | 0.5076% | 1.22% | 2.312% | 3.846% | 5.882% | 8.478% | 11.68% | 15.52% | 20% | 25.1% | 30.77% | 36.9% | 43.36% | 50% | 56.64% | 63.1% | 69.23% | 74.9% | 80% | 84.48% | 88.32% | 91.52% | 94.12% | 96.15% | 97.69% | 98.78% | 99.49% | 99.88% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Monthly progress | % | 100% | 0.1188% | 0.3888% | 0.7119% | 1.093% | 1.534% | 2.036% | 2.595% | 3.201% | 3.838% | 4.483% | 5.104% | 5.665% | 6.13% | 6.463% | 6.637% | 6.637% | 6.463% | 6.13% | 5.665% | 5.104% | 4.483% | 3.838% | 3.201% | 2.595% | 2.036% | 1.534% | 1.093% | 0.7119% | 0.3888% | 0.1188% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Escalation factor | x |  | 1.0058 | 1.0176 | 1.0295 | 1.0416 | 1.0538 | 1.0662 | 1.0786 | 1.0913 | 1.1041 | 1.117 | 1.1301 | 1.1433 | 1.1567 | 1.1703 | 1.184 | 1.1978 | 1.2119 | 1.2261 | 1.2404 | 1.255 | 1.2697 | 1.2845 | 1.2996 | 1.3148 | 1.3302 | 1.3458 | 1.3616 | 1.3775 | 1.3937 | 1.41 | 1.4265 | 1.4432 | 1.4601 | 1.4772 | 1.4945 | 1.512 | 1.5298 | 1.5477 | 1.5658 | 1.5842 | 1.6027 | 1.6215 | 1.6405 | 1.6597 | 1.6791 | 1.6988 | 1.7187 | 1.7389
Development cost accrual (IAS 2 / 16 / 40 / 23) | የልማት ወጪ
Hard cost (escalated) | ETB | 319322348.7224 | 319619.5259 | 1058729.3306 | 1961008.4406 | 3045030.1505 | 4325214.4727 | 5808398.4564 | 7489584.6768 | 9347210.5628 | 11338664.365 | 13397202.7247 | 15431743.5317 | 17330976.9213 | 18972618.2768 | 20237347.4838 | 21025307.7541 | 21271617.4876 | 20956948.6305 | 20110276.2181 | 18803128.65 | 17137141.2835 | 15228383.8814 | 13192220.2574 | 11131516.298 | 9129486.3246 | 7247050.9603 | 5523684.5435 | 3980422.0603 | 2623815.5226 | 1449956.8751 | 448043.0557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingency | ETB | 25545787.8978 | 25569.5621 | 84698.3464 | 156880.6752 | 243602.412 | 346017.1578 | 464671.8765 | 599166.7741 | 747776.845 | 907093.1492 | 1071776.218 | 1234539.4825 | 1386478.1537 | 1517809.4621 | 1618987.7987 | 1682024.6203 | 1701729.399 | 1676555.8904 | 1608822.0975 | 1504250.292 | 1370971.3027 | 1218270.7105 | 1055377.6206 | 890521.3038 | 730358.906 | 579764.0768 | 441894.7635 | 318433.7648 | 209905.2418 | 115996.55 | 35843.4445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design fees | ETB | 13377850 | 6696869.0914 | 26009.8426 | 47618.3221 | 73084.9693 | 102609.1207 | 136199.8303 | 173588.019 | 214134.1257 | 256748.3168 | 299848.3621 | 341384.9689 | 378960.8004 | 410053.3465 | 432323.1852 | 443955.1991 | 443955.1991 | 432323.1852 | 410053.3465 | 378960.8004 | 341384.9689 | 299848.3621 | 256748.3168 | 214134.1257 | 173588.019 | 136199.8303 | 102609.1207 | 73084.9693 | 47618.3221 | 26009.8426 | 7944.0914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Supervision | ETB | 9579670.4617 | 9588.5858 | 31761.8799 | 58830.2532 | 91350.9045 | 129756.4342 | 174251.9537 | 224687.5403 | 280416.3169 | 340159.9309 | 401916.0817 | 462952.306 | 519929.3076 | 569178.5483 | 607120.4245 | 630759.2326 | 638148.5246 | 628708.4589 | 603308.2865 | 564093.8595 | 514114.2385 | 456851.5164 | 395766.6077 | 333945.4889 | 273884.5897 | 217411.5288 | 165710.5363 | 119412.6618 | 78714.4657 | 43498.7063 | 13441.2917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Specialist consultancy | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Permits & fees | ETB | 2500000 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FF&E / furniture | ETB | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Land (recognised month 1) | ETB | 150000000 | 150000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arrangement fee (on IDC-excluded facility) | ETB | 4113064.0858 | 4113064.0858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commitment fee on undrawn facility | ETB | 2932654.2481 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 108877.5677 | 101408.1141 | 94476.5103 | 88270.4846 | 82928.2159 | 78534.1078 | 75121.142 | 72678.0636 | 71159.2175 | 66234.4684 | 66234.4684 | 66234.4684 | 66234.4684 | 66234.4684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest during construction (from loan schedule) | ETB | 17456846.4028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161226.3752 | 387325.3128 | 600114.9911 | 793797.2001 | 963987.7263 | 1107860.8168 | 1224098.0495 | 1312691.6267 | 1374665.6566 | 1539591.4494 | 1558836.3425 | 1578321.7968 | 1598050.8193 | 1618026.4545 | 1638251.7852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total capex accrual | ETB | 550828221.8186 | 163778962.6312 | 1315451.1797 | 2338589.4713 | 3567320.2166 | 5017848.9656 | 6697773.8971 | 8601278.7904 | 10703789.6305 | 12956917.5421 | 15284995.1666 | 17584872.0693 | 19730596.9631 | 21583911.4139 | 23010030.6723 | 23896298.5863 | 24330928.7657 | 24190739.0455 | 23433983.0538 | 22138707.3122 | 20415870.0044 | 18394143.5031 | 16202744.9597 | 13957929.9851 | 11754661.5596 | 9791177.0632 | 7858969.7749 | 6135909.7215 | 4624338.8399 | 3319722.8969 | 8209758.1368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative capex accrual | ETB | 550828221.8186 | 163778962.6312 | 165094413.8109 | 167433003.2822 | 171000323.4988 | 176018172.4644 | 182715946.3615 | 191317225.152 | 202021014.7825 | 214977932.3245 | 230262927.4912 | 247847799.5604 | 267578396.5236 | 289162307.9375 | 312172338.6098 | 336068637.1961 | 360399565.9619 | 384590305.0073 | 408024288.0612 | 430162995.3734 | 450578865.3778 | 468973008.8809 | 485175753.8407 | 499133683.8258 | 510888345.3854 | 520679522.4486 | 528538492.2235 | 534674401.945 | 539298740.7849 | 542618463.6818 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186
Cash needed during construction | ለግንባታ የሚያስፈልግ ጥሬ ገንዘብ
Retention withheld from contractor | ETB | 15966117.4361 | 15980.9763 | 52936.4665 | 98050.422 | 152251.5075 | 216260.7236 | 290419.9228 | 374479.2338 | 467360.5281 | 566933.2182 | 669860.1362 | 771587.1766 | 866548.8461 | 948630.9138 | 1011867.3742 | 1051265.3877 | 1063580.8744 | 1047847.4315 | 1005513.8109 | 940156.4325 | 856857.0642 | 761419.1941 | 659611.0129 | 556575.8149 | 456474.3162 | 362352.548 | 276184.2272 | 199021.103 | 131190.7761 | 72497.8438 | 22402.1528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Land cash (lease down payment) | ETB | 15000000 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Development cash paid (excl. finance costs) | ETB | 375359539.6457 | 24535665.7889 | 1148262.933 | 2126287.2691 | 3300816.9289 | 4687336.4618 | 6293102.1942 | 8112547.7764 | 10122177.3222 | 12275732.5437 | 14500883.2503 | 16699033.1125 | 18749796.3369 | 20521028.7199 | 21883911.5179 | 22730781.4184 | 22991869.736 | 22646688.7335 | 21726946.1377 | 20310277.1693 | 18506754.7293 | 16441935.2764 | 14240501.7896 | 12013541.4015 | 9850843.5232 | 7818073.8483 | 5957714.7368 | 4292332.3533 | 2828862.776 | 1562964.1302 | 6482869.7304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Input VAT on capex (reclaimable) | ETB | 39251693.9936 | 740422.9103 | 126125.937 | 233555.4576 | 362572.1858 | 514877.7045 | 691269.8223 | 891137.8361 | 1111901.4743 | 1348479.905 | 1592928.0556 | 1834415.1304 | 2059716.2442 | 2254314.2615 | 2404056.7837 | 2497114.9146 | 2525822.3141 | 2487926.2973 | 2386908.2946 | 2231295.5282 | 2033179.2383 | 1806352.2194 | 1564511.8443 | 1319862.3077 | 1082268.3731 | 858944.7716 | 654559.3912 | 471592.1129 | 310805.623 | 171723.5073 | 683053.5477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pre-opening & launch marketing (expensed, funded) | ETB | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Land lease instalment (during construction) | ETB | 9000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Land lease interest (during construction) | ETB | 18585000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Funding need excl. finance costs | ETB | 443696233.6393 | 25276088.6992 | 1274388.87 | 2359842.7267 | 3663389.1147 | 5202214.1662 | 6984372.0164 | 9003685.6125 | 11234078.7965 | 13624212.4486 | 16093811.3058 | 18533448.2429 | 20809512.5811 | 36725342.9815 | 24287968.3016 | 25227896.3331 | 25517692.0501 | 25134615.0309 | 24113854.4323 | 22541572.6975 | 20539933.9677 | 18248287.4958 | 15805013.6339 | 13333403.7093 | 10933111.8963 | 22312018.6199 | 6612274.128 | 4763924.4662 | 3139668.399 | 1734687.6375 | 8665923.2782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Finance costs paid in cash (fees) | ETB | 7045718.334 | 4227315.866 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 114251.7802 | 108877.5677 | 101408.1141 | 94476.5103 | 88270.4846 | 82928.2159 | 78534.1078 | 75121.142 | 72678.0636 | 71159.2175 | 66234.4684 | 66234.4684 | 66234.4684 | 66234.4684 | 66234.4684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL FUNDING NEED | ETB | 450741951.9733 | 29503404.5652 | 1388640.6501 | 2474094.5069 | 3777640.8949 | 5316465.9464 | 7098623.7966 | 9117937.3927 | 11348330.5767 | 13738464.2288 | 16208063.086 | 18647700.023 | 20923764.3613 | 36839594.7617 | 24402220.0818 | 25342148.1132 | 25631943.8303 | 25243492.5985 | 24215262.5464 | 22636049.2078 | 20628204.4523 | 18331215.7117 | 15883547.7416 | 13408524.8513 | 11005789.9599 | 22383177.8374 | 6678508.5964 | 4830158.9346 | 3205902.8674 | 1800922.1059 | 8732157.7466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative funding need | ETB | 450741951.9733 | 29503404.5652 | 30892045.2154 | 33366139.7222 | 37143780.6171 | 42460246.5635 | 49558870.3601 | 58676807.7528 | 70025138.3295 | 83763602.5583 | 99971665.6443 | 118619365.6673 | 139543130.0286 | 176382724.7902 | 200784944.872 | 226127092.9852 | 251759036.8155 | 277002529.414 | 301217791.9604 | 323853841.1682 | 344482045.6205 | 362813261.3321 | 378696809.0738 | 392105333.9251 | 403111123.885 | 425494301.7224 | 432172810.3188 | 437002969.2534 | 440208872.1208 | 442009794.2267 | 450741951.9733 | 450741951.9733 | 450741951.9733 | 450741951.9733 | 450741951.9733 | 450741951.9733 | 450741951.9733 | 450741951.9733 | 450741951.9733 | 450741951.9733 | 450741951.9733 | 450741951.9733 | 450741951.9733 | 450741951.9733 | 450741951.9733 | 450741951.9733 | 450741951.9733 | 450741951.9733 | 450741951.9733
Presales (contracts signed during construction) | ቅድመ-ሽያጭ
Construction year (presale band) | no. |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Construction months in this band | no. |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Area presold | m² | 2352 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 112 | 112 | 112 | 112 | 112 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sale price (escalated) | ETB/m² |  | 125000 | 125996.7676 | 127001.4835 | 128014.2111 | 129035.0144 | 130063.9578 | 131101.106 | 132146.5247 | 133200.2796 | 134262.4373 | 135333.0649 | 136412.2297 | 137500 | 138596.4443 | 139701.6318 | 140815.6322 | 141938.5159 | 143070.3535 | 144211.2166 | 145361.1771 | 146520.3076 | 147688.6811 | 148866.3713 | 150053.4527 | 151250 | 152456.0887 | 153671.795 | 154897.1955 | 156132.3675 | 157377.3889 | 158632.3383 | 159897.2948 | 161172.3383 | 162457.5492 | 163753.0085 | 165058.798 | 166375 | 167701.6976 | 169038.9745 | 170386.915 | 171745.6042 | 173115.1278 | 174495.5721 | 175887.0243 | 177289.5721 | 178703.3041 | 180128.3093 | 181564.6778
Contract value signed (net of default allowance) | ETB | 327437856.5968 | 8575000 | 8643378.2542 | 8712301.7662 | 8781774.8839 | 8851801.99 | 8922387.5022 | 8993535.8731 | 9065251.5911 | 9137539.1803 | 9210403.2009 | 9283848.2494 | 9357878.9591 | 9432500 | 9507716.0796 | 9583531.9428 | 9659952.3723 | 9736982.189 | 9814626.2524 | 9892889.4604 | 9971776.7502 | 10051293.0983 | 10131443.521 | 10212233.0743 | 10293666.855 | 16601200 | 16733580.3001 | 16867016.2193 | 17001516.1752 | 17137088.6527 | 17273742.2042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative contract value | ETB | 327437856.5968 | 8575000 | 17218378.2542 | 25930680.0203 | 34712454.9042 | 43564256.8943 | 52486644.3964 | 61480180.2695 | 70545431.8606 | 79682971.0408 | 88893374.2417 | 98177222.4911 | 107535101.4502 | 116967601.4502 | 126475317.5298 | 136058849.4725 | 145718801.8448 | 155455784.0339 | 165270410.2862 | 175163299.7466 | 185135076.4968 | 195186369.5951 | 205317813.116 | 215530046.1904 | 225823713.0453 | 242424913.0453 | 259158493.3454 | 276025509.5647 | 293027025.7399 | 310164114.3927 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968
Cumulative area presold | m² | 2352 | 70 | 140 | 210 | 280 | 350 | 420 | 490 | 560 | 630 | 700 | 770 | 840 | 910 | 980 | 1050 | 1120 | 1190 | 1260 | 1330 | 1400 | 1470 | 1540 | 1610 | 1680 | 1792 | 1904 | 2016 | 2128 | 2240 | 2352 | 2352 | 2352 | 2352 | 2352 | 2352 | 2352 | 2352 | 2352 | 2352 | 2352 | 2352 | 2352 | 2352 | 2352 | 2352 | 2352 | 2352 | 2352
Collections – down payments | ETB | 98231356.979 | 2572500 | 2593013.4763 | 2613690.5298 | 2634532.4652 | 2655540.597 | 2676716.2506 | 2698060.7619 | 2719575.4773 | 2741261.7541 | 2763120.9603 | 2785154.4748 | 2807363.6877 | 2829750 | 2852314.8239 | 2875059.5828 | 2897985.7117 | 2921094.6567 | 2944387.8757 | 2967866.8381 | 2991533.0251 | 3015387.9295 | 3039433.0563 | 3063669.9223 | 3088100.0565 | 4980360 | 5020074.09 | 5060104.8658 | 5100454.8526 | 5141126.5958 | 5182122.6613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative milestone instalments due | ETB | 130975142.6387 | 4073.6342 | 34961.1741 | 126491.1221 | 321040.0454 | 670219.3368 | 1234979.8682 | 2084795.0403 | 3295553.0212 | 4945839.5818 | 7111469.9393 | 9858459.6858 | 13235089.4093 | 17264213.6638 | 21937311.7131 | 27211769.8945 | 33012401.1259 | 39237311.4286 | 45767190.5408 | 52476308.0569 | 59243224.479 | 65959531.7942 | 72535636.1665 | 78903387.152 | 85015986.0877 | 93240351.1713 | 101266555.7812 | 109063737.9256 | 116615831.5635 | 123918299.3844 | 130975142.6387 | 130975142.6387 | 130975142.6387 | 130975142.6387 | 130975142.6387 | 130975142.6387 | 130975142.6387 | 130975142.6387 | 130975142.6387 | 130975142.6387 | 130975142.6387 | 130975142.6387 | 130975142.6387 | 130975142.6387 | 130975142.6387 | 130975142.6387 | 130975142.6387 | 130975142.6387 | 130975142.6387
Collections – milestone instalments | ETB | 130975142.6387 | 4073.6342 | 30887.5399 | 91529.9479 | 194548.9233 | 349179.2915 | 564760.5313 | 849815.1721 | 1210757.9809 | 1650286.5606 | 2165630.3575 | 2746989.7465 | 3376629.7234 | 4029124.2546 | 4673098.0493 | 5274458.1814 | 5800631.2314 | 6224910.3027 | 6529879.1122 | 6709117.5161 | 6766916.4221 | 6716307.3152 | 6576104.3723 | 6367750.9855 | 6112598.9356 | 8224365.0836 | 8026204.6099 | 7797182.1443 | 7552093.6379 | 7302467.8209 | 7056843.2543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections – balance at handover | ETB | 98231356.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98231356.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total presale collections | ETB | 327437856.5968 | 2576573.6342 | 2623901.0162 | 2705220.4778 | 2829081.3885 | 3004719.8885 | 3241476.782 | 3547875.934 | 3930333.4583 | 4391548.3147 | 4928751.3178 | 5532144.2213 | 6183993.4111 | 6858874.2546 | 7525412.8732 | 8149517.7642 | 8698616.9431 | 9146004.9594 | 9474266.9879 | 9676984.3542 | 9758449.4472 | 9731695.2447 | 9615537.4286 | 9431420.9078 | 9200698.9921 | 13204725.0836 | 13046278.7 | 12857287.0101 | 12652548.4905 | 12443594.4167 | 110470322.8946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative revenue recognised (IFRS 15) | ETB | 327437856.5968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968 | 327437856.5968
Presale revenue recognised | ETB | 327437856.5968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327437856.5968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative cost of sales released (IAS 2) | ETB | 290156321.9972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290156321.9972 | 290156321.9972 | 290156321.9972 | 290156321.9972 | 290156321.9972 | 290156321.9972 | 290156321.9972 | 290156321.9972 | 290156321.9972 | 290156321.9972 | 290156321.9972 | 290156321.9972 | 290156321.9972 | 290156321.9972 | 290156321.9972 | 290156321.9972 | 290156321.9972 | 290156321.9972 | 290156321.9972
Presale cost of sales | ETB | 290156321.9972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290156321.9972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Funding waterfall: (1) presales → (2) equity → (3) debt → (4) top-up / gap | የገንዘብ ምንጭ ቅደም ተከተል
Presale cash usable for construction | ETB | 261950285.2775 | 2061258.9074 | 2099120.8129 | 2164176.3822 | 2263265.1108 | 2403775.9108 | 2593181.4256 | 2838300.7472 | 3144266.7666 | 3513238.6518 | 3943001.0542 | 4425715.3771 | 4947194.7289 | 5487099.4037 | 6020330.2985 | 6519614.2114 | 6958893.5545 | 7316803.9676 | 7579413.5903 | 7741587.4833 | 7806759.5577 | 7785356.1958 | 7692429.9429 | 7545136.7262 | 7360559.1937 | 10563780.0669 | 10437022.96 | 10285829.6081 | 10122038.7924 | 9954875.5334 | 88376258.3157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presale pool – opening | ETB |  | 0 | 0 | 710480.1628 | 400562.0382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3758514.3636 | 9214185.037 | 16130320.962 | 24284274.3895 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586
(1) Presale cash used | ETB | 158021910.3188 | 2061258.9074 | 1388640.6501 | 2474094.5069 | 2663827.1489 | 2403775.9108 | 2593181.4256 | 2838300.7472 | 3144266.7666 | 3513238.6518 | 3943001.0542 | 4425715.3771 | 4947194.7289 | 5487099.4037 | 6020330.2985 | 6519614.2114 | 6958893.5545 | 7316803.9676 | 7579413.5903 | 7741587.4833 | 7806759.5577 | 7785356.1958 | 7692429.9429 | 7545136.7262 | 7360559.1937 | 10563780.0669 | 6678508.5964 | 4830158.9346 | 3205902.8674 | 1800922.1059 | 8732157.7466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presale pool – closing | ETB | 103928374.9586 | 0 | 710480.1628 | 400562.0382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3758514.3636 | 9214185.037 | 16130320.962 | 24284274.3895 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586 | 103928374.9586
Need after presales | ETB | 292720041.6545 | 27442145.6579 | 0 | 0 | 1113813.7459 | 2912690.0356 | 4505442.371 | 6279636.6455 | 8204063.8101 | 10225225.577 | 12265062.0318 | 14221984.646 | 15976569.6324 | 31352495.358 | 18381889.7832 | 18822533.9019 | 18673050.2758 | 17926688.631 | 16635848.9561 | 14894461.7245 | 12821444.8945 | 10545859.5159 | 8191117.7987 | 5863388.125 | 3645230.7662 | 11819397.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(2) Equity draw | ETB | 177478493.4557 | 27442145.6579 | 0 | 0 | 1113813.7459 | 2912690.0356 | 4505442.371 | 6279636.6455 | 8204063.8101 | 10225225.577 | 12265062.0318 | 14221984.646 | 15976569.6324 | 31352495.358 | 18381889.7832 | 18822533.9019 | 5774940.2595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(3) Debt draw | ETB | 115241548.1987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12898110.0163 | 17926688.631 | 16635848.9561 | 14894461.7245 | 12821444.8945 | 10545859.5159 | 8191117.7987 | 5863388.125 | 3645230.7662 | 11819397.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(2b) Equity – pro-rata balance | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
(4) Sponsor top-up / funding gap | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative committed equity drawn | ETB | 177478493.4557 | 27442145.6579 | 27442145.6579 | 27442145.6579 | 28555959.4038 | 31468649.4394 | 35974091.8104 | 42253728.4559 | 50457792.266 | 60683017.843 | 72948079.8748 | 87170064.5208 | 103146634.1531 | 134499129.5111 | 152881019.2944 | 171703553.1962 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 177478493.4557
Cumulative debt drawn | ETB | 115241548.1987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12898110.0163 | 30824798.6472 | 47460647.6033 | 62355109.3278 | 75176554.2224 | 85722413.7382 | 93913531.537 | 99776919.662 | 103422150.4283 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987 | 115241548.1987
Total equity in (incl. top-up) | ETB | 177478493.4557 | 27442145.6579 | 0 | 0 | 1113813.7459 | 2912690.0356 | 4505442.371 | 6279636.6455 | 8204063.8101 | 10225225.577 | 12265062.0318 | 14221984.646 | 15976569.6324 | 31352495.358 | 18381889.7832 | 18822533.9019 | 5774940.2595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presale cash held (pool + escrow), cumulative | ETB | 169415946.278 | 515314.7268 | 1750575.0929 | 1981701.0638 | 2146955.3033 | 2747899.281 | 3396194.6374 | 4105769.8242 | 4891836.5159 | 5770146.1788 | 6755896.4424 | 7862325.2866 | 9099123.9689 | 10470898.8198 | 11975981.3944 | 13605884.9473 | 15345608.3359 | 17174809.3278 | 19069662.7253 | 21005059.5962 | 22956749.4856 | 24903088.5345 | 26826196.0203 | 28712480.2018 | 30552620.0003 | 33193565.017 | 39561335.1205 | 47588463.196 | 57035108.8191 | 67677781.13 | 169415946.278 | 169415946.278 | 169415946.278 | 169415946.278 | 169415946.278 | 169415946.278 | 169415946.278 | 169415946.278 | 169415946.278 | 169415946.278 | 169415946.278 | 169415946.278 | 169415946.278 | 169415946.278 | 169415946.278 | 169415946.278 | 169415946.278 | 169415946.278 | 169415946.278
Sources − uses (should be 0) | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Funding scalars | የገንዘብ ማጠቃለያ
User profile total (construction months) | % | 0%
Funding base (need excl. IDC & finance fees) | ETB | 443696233.6393
Equity commitment | ETB | 177478493.4557
Debt facility (cap) | ETB | 274204272.3891
Equity share for pro-rata draws | % | 39.29%
Peak cumulative funding requirement | ETB | 450741951.9733
Equity drawn (committed) | ETB | 177478493.4557
Debt drawn | ETB | 115241548.1987
Sponsor top-up / funding gap | ETB | 0
Presale cash used for construction | ETB | 158021910.3188
Handover collections at completion | ETB | 98231356.979
Total retention withheld | ETB | 15966117.4361
Land paid in cash in month 1 | ETB | 15000000
Pre-opening cost funded at completion | ETB | 1500000
Sources − uses (should be 0) | ETB | 0

## 24_Revenue
24 · Revenue – sales, rent, other income | [15 empty] | ◂ Start
ገቢ – ሽያጭ፣ ኪራይና ሌሎች | [15 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Period |  | Total | C1 | C2 | C3 | C4 | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | O9 | O10
Period end (Gregorian) |  |  | 2027-12-31 | 2028-12-31 | 2029-06-30 | 2029-06-30 | 2030-06-30 | 2031-06-30 | 2032-06-30 | 2033-06-30 | 2034-06-30 | 2035-06-30 | 2036-06-30 | 2037-06-30 | 2038-06-30 | 2039-06-30
Ethiopian calendar year |  |  | EC 2020 | EC 2021 | EC 2021 | EC 2021 | EC 2022 | EC 2023 | EC 2024 | EC 2025 | EC 2026 | EC 2027 | EC 2028 | EC 2029 | EC 2030 | EC 2031
Presale bands (effective after scenario, capped at 100%) | የቅድመ-ሽያጭ ድርሻ
Presale band 1 – raw | % | 25%
Presale band 2 – raw | % | 25%
Presale band 3 – raw | % | 20%
Presale band 4 – raw | % | 0%
Presales raw total | % | 70%
Presale band 1 – effective | % | 25%
Presale band 2 – effective | % | 25%
Presale band 3 – effective | % | 20%
Presale band 4 – effective | % | 0%
Total presold share | % | 70%
Unsold area at completion | m² | 1008
Absorption O1 – effective | % | 60%
Absorption O2 – effective | % | 40%
Absorption O3 – effective | % | 0%
Absorption O4 – effective | % | 0%
Sales – presales (from monthly sheet) | ቅድመ-ሽያጭ
Area presold | m² | 2352 | 840 | 840 | 672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract value signed | ETB | 327437856.5968 | 107535101.4502 | 118288611.5952 | 101614143.5515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presale collections | ETB | 327437856.5968 | 45495619.8443 | 107267480.157 | 174674756.5956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presale revenue recognised | ETB | 327437856.5968 | 0 | 0 | 327437856.5968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presale cost of sales | ETB | 290156321.9972 | 0 | 0 | 290156321.9972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales – after completion (point in time, cash on sale) | ከግንባታ በኋላ ሽያጭ
Area sold | m² | 1008 | 0 | 0 | 0 | 0 | 604.8 | 403.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unsold area remaining | m² | 0 | 0 | 0 | 0 | 0 | 403.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sale price (escalated) | ETB/m² |  | 0 | 0 | 0 | 0 | 166375 | 183012.5 | 201313.75 | 221445.125 | 243589.6375 | 267948.6013 | 294743.4614 | 324217.8075 | 356639.5883 | 392303.5471
Sales revenue = collections | ETB | 170925955.2 | 0 | 0 | 0 | 0 | 98611128 | 72314827.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost of sales | ETB | 124352709.4274 | 0 | 0 | 0 | 0 | 74611625.6564 | 49741083.7709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales totals and contract balances (IFRS 15) | የሽያጭ ድምር
Sales revenue recognised | ETB | 498363811.7968 | 0 | 0 | 327437856.5968 | 0 | 98611128 | 72314827.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales cash collected | ETB | 498363811.7968 | 45495619.8443 | 107267480.157 | 174674756.5956 | 0 | 98611128 | 72314827.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost of sales (IAS 2) | ETB | 414509031.4246 | 0 | 0 | 290156321.9972 | 0 | 74611625.6564 | 49741083.7709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract value signed in period | ETB | 498363811.7968 | 107535101.4502 | 118288611.5952 | 101614143.5515 | 0 | 98611128 | 72314827.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales commission | ETB | 9967276.2359 | 0 | 0 | 6548757.1319 | 0 | 1972222.56 | 1446296.544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marketing | ETB | 4983638.118 | 1075351.0145 | 1182886.116 | 1016141.4355 | 0 | 986111.28 | 723148.272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative collections | ETB | 498363811.7968 | 45495619.8443 | 152763100.0013 | 327437856.5968 | 327437856.5968 | 426048984.5968 | 498363811.7968 | 498363811.7968 | 498363811.7968 | 498363811.7968 | 498363811.7968 | 498363811.7968 | 498363811.7968 | 498363811.7968 | 498363811.7968
Cumulative revenue | ETB | 498363811.7968 | 0 | 0 | 327437856.5968 | 327437856.5968 | 426048984.5968 | 498363811.7968 | 498363811.7968 | 498363811.7968 | 498363811.7968 | 498363811.7968 | 498363811.7968 | 498363811.7968 | 498363811.7968 | 498363811.7968
Contract balance (+ liability / − asset) | ETB | 0 | 45495619.8443 | 152763100.0013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract liability | ETB | 0 | 45495619.8443 | 152763100.0013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract asset | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales collections in operating year (for sweep) | ETB | 170925955.2 | 0 | 0 | 0 | 0 | 98611128 | 72314827.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rent from the space schedule (IFRS 16 lessor) | ኪራይ ከቦታ ዝርዝር
Gross potential rent – spaces (100% let) | ETB | 465691436.522 | 0 | 0 | 0 | 0 | 32146441.7537 | 34718157.094 | 37495609.6615 | 40495258.4345 | 43734879.1092 | 47233669.438 | 51012362.993 | 55093352.0324 | 59500820.195 | 64260885.8106
Occupancy (rent-weighted; lease-up then stabilised) | % |  | 0% | 0% | 0% | 0% | 59.8% | 80.04% | 92% | 92% | 92% | 92% | 92% | 92% | 92% | 92%
Rent – spaces | ETB | 413932675.7671 | 0 | 0 | 0 | 0 | 19223572.1687 | 27788412.9381 | 34495960.8886 | 37255637.7597 | 40236088.7805 | 43454975.8829 | 46931373.9536 | 50685883.8698 | 54740754.5794 | 59120014.9458
Hotel operator lease (turnover rent, minimum guaranteed) | የሆቴል ኪራይ
Hotel occupancy | % | bar: 2027-12-31 to 2039-06-30
Average daily rate (escalated) | ETB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rooms revenue (operator) | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total hotel revenue (operator) | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Turnover rent | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Minimum guaranteed rent | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hotel rent to owner (higher of the two) | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total rent and other income | ጠቅላላ ኪራይና ሌሎች ገቢዎች
Rental income (spaces + hotel) | ETB | 413932675.7671 | 0 | 0 | 0 | 0 | 19223572.1687 | 27788412.9381 | 34495960.8886 | 37255637.7597 | 40236088.7805 | 43454975.8829 | 46931373.9536 | 50685883.8698 | 54740754.5794 | 59120014.9458
Key money received | ETB | 9611786.0844 | 0 | 0 | 0 | 0 | 9611786.0844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Key money released to income | ETB | 9611786.0844 | 0 | 0 | 0 | 0 | 1922357.2169 | 1922357.2169 | 1922357.2169 | 1922357.2169 | 1922357.2169 | 0 | 0 | 0 | 0 | 0
Deferred key money (liability) | ETB | 0 | 0 | 0 | 0 | 0 | 7689428.8675 | 5767071.6506 | 3844714.4337 | 1922357.2169 | 0 | 0 | 0 | 0 | 0 | 0
Service charge recoveries | ETB | 37253940.819 | 0 | 0 | 0 | 0 | 1730121.4952 | 2500957.1644 | 3104636.48 | 3353007.3984 | 3621247.9902 | 3910947.8295 | 4223823.6558 | 4561729.5483 | 4926667.9121 | 5320801.3451
Other income – stream 1 (Inputs block 8) | ETB | 5794624.9864 | 0 | 0 | 0 | 0 | 400000 | 432000 | 466560 | 503884.8 | 544195.584 | 587731.2307 | 634749.7292 | 685529.7075 | 740372.0841 | 799601.8508
Other income – stream 2 (Inputs block 8) | ETB | 2897312.4932 | 0 | 0 | 0 | 0 | 200000 | 216000 | 233280 | 251942.4 | 272097.792 | 293865.6154 | 317374.8646 | 342764.8538 | 370186.0421 | 399800.9254
Other income – stream 3 (Inputs block 8) | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other income – stream 4 (Inputs block 8) | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other income (4 streams) | ETB | 8691937.4795 | 0 | 0 | 0 | 0 | 600000 | 648000 | 699840 | 755827.2 | 816293.376 | 881596.8461 | 952124.5938 | 1028294.5613 | 1110558.1262 | 1199402.7763
TOTAL REVENUE | ETB | 967854151.9469 | 0 | 0 | 327437856.5968 | 0 | 122087178.8808 | 105174554.5194 | 40222794.5855 | 43286829.575 | 46595987.3636 | 48247520.5585 | 52107322.2031 | 56275907.9794 | 60777980.6177 | 65640219.0672
Net operating income of let property (NOI) | ETB | 364353633.0913 | 0 | 0 | 0 | 0 | 16909704.1817 | 24500484.9615 | 30434122.3822 | 32849509.7166 | 35456193.7921 | 38269284.9235 | 41305082.9082 | 44581170.2508 | 48116512.6518 | 51931567.3229

## 25_Opex
25 · Operating costs | [15 empty] | ◂ Start
የሥራ ማስኬጃ ወጪዎች | [15 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Period |  | Total | C1 | C2 | C3 | C4 | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | O9 | O10
Period end (Gregorian) |  |  | 2027-12-31 | 2028-12-31 | 2029-06-30 | 2029-06-30 | 2030-06-30 | 2031-06-30 | 2032-06-30 | 2033-06-30 | 2034-06-30 | 2035-06-30 | 2036-06-30 | 2037-06-30 | 2038-06-30 | 2039-06-30
Ethiopian calendar year |  |  | EC 2020 | EC 2021 | EC 2021 | EC 2021 | EC 2022 | EC 2023 | EC 2024 | EC 2025 | EC 2026 | EC 2027 | EC 2028 | EC 2029 | EC 2030 | EC 2031
Operating costs (positive = cost) | ወጪዎች
Opex escalation index (from today) | x |  | 0 | 0 | 0 | 0 | 1.2691 | 1.396 | 1.5356 | 1.6891 | 1.858 | 2.0438 | 2.2482 | 2.473 | 2.7203 | 2.9924
Property operating costs (hotel operator bears its own costs) | ETB | 62089901.3651 | 0 | 0 | 0 | 0 | 2883535.8253 | 4168261.9407 | 5174394.1333 | 5588345.664 | 6035413.3171 | 6518246.3824 | 7039706.093 | 7602882.5805 | 8211113.1869 | 8868002.2419
Management fee | ETB | 12417980.273 | 0 | 0 | 0 | 0 | 576707.1651 | 833652.3881 | 1034878.8267 | 1117669.1328 | 1207082.6634 | 1303649.2765 | 1407941.2186 | 1520576.5161 | 1642222.6374 | 1773600.4484
Insurance | ETB | 2397514.5136 | 0 | 0 | 0 | 0 | 150432.9949 | 165476.2944 | 182023.9238 | 200226.3162 | 220248.9478 | 242273.8426 | 266501.2269 | 293151.3496 | 322466.4845 | 354713.133
Property tax | ETB | 2349156.262 | 0 | 0 | 0 | 0 | 147398.7373 | 162138.611 | 178352.4721 | 196187.7193 | 215806.4913 | 237387.1404 | 261125.8544 | 287238.4399 | 315962.2839 | 347558.5123
Maintenance reserve | ETB | 7991715.0454 | 0 | 0 | 0 | 0 | 501443.3163 | 551587.6479 | 606746.4127 | 667421.054 | 734163.1594 | 807579.4754 | 888337.4229 | 977171.1652 | 1074888.2817 | 1182377.1099
Marketing | ETB | 4983638.118 | 1075351.0145 | 1182886.116 | 1016141.4355 | 0 | 986111.28 | 723148.272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Owner overheads | ETB | 24270632.9348 | 0 | 0 | 0 | 0 | 1522870.4475 | 1675157.4923 | 1842673.2415 | 2026940.5657 | 2229634.6222 | 2452598.0845 | 2697857.8929 | 2967643.6822 | 3264408.0504 | 3590848.8555
Pre-opening & launch marketing (expensed at completion) | ETB | 1500000 | 0 | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bad debts | ETB | 8278653.5153 | 0 | 0 | 0 | 0 | 384471.4434 | 555768.2588 | 689919.2178 | 745112.7552 | 804721.7756 | 869099.5177 | 938627.4791 | 1013717.6774 | 1094815.0916 | 1182400.2989
TOTAL OPERATING COSTS | ETB | 126279192.0272 | 1075351.0145 | 1182886.116 | 2516141.4355 | 0 | 7152971.2098 | 8835190.9053 | 9708988.2279 | 10541903.2072 | 11447070.9769 | 12430833.7194 | 13500097.1878 | 14662381.4108 | 15925876.0164 | 17299500.5997
Opex base carrying input VAT | ETB | 43741617.4007 | 537675.5073 | 591443.058 | 508070.7178 | 0 | 2473898.7933 | 3138325.1244 | 3408009.6863 | 3686717.9254 | 3988329.57 | 4314737.5671 | 4667992.3673 | 5050315.1309 | 5464112.053 | 5911989.9001

## 26_Assets
26 · Assets & depreciation (IAS 2 / 16 / 40) | [15 empty] | ◂ Start
ንብረትና የእርጅና ቅናሽ | [15 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Period |  | Total | C1 | C2 | C3 | C4 | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | O9 | O10
Period end (Gregorian) |  |  | 2027-12-31 | 2028-12-31 | 2029-06-30 | 2029-06-30 | 2030-06-30 | 2031-06-30 | 2032-06-30 | 2033-06-30 | 2034-06-30 | 2035-06-30 | 2036-06-30 | 2037-06-30 | 2038-06-30 | 2039-06-30
Ethiopian calendar year |  |  | EC 2020 | EC 2021 | EC 2021 | EC 2021 | EC 2022 | EC 2023 | EC 2024 | EC 2025 | EC 2026 | EC 2027 | EC 2028 | EC 2029 | EC 2030 | EC 2031
Capex accrual and allocation | የወጪ ድልድል
Capex accrual (incl. capitalised finance) | ETB | 550828221.8186 | 267578396.5236 | 243309948.8618 | 39939876.4332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
of which IDC (non-cash) | ETB | 17456846.4028 | 0 | 7925767.755 | 9531078.6478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative capex | ETB | 550828221.8186 | 267578396.5236 | 510888345.3854 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186 | 550828221.8186
Additions – inventory (IAS 2) | ETB | 414509031.4246 | 201357987.0816 | 183095504.6306 | 30055539.7124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Additions – investment property (IAS 40) | ETB | 136319190.3941 | 66220409.442 | 60214444.2312 | 9884336.7209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Additions – owner-occupied (IAS 16) | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Accounting depreciation – components, straight line from O1 | የሂሳብ እርጅና ቅናሽ
Structure | ETB | 14198819.525 | 0 | 0 | 0 | 0 | 1419881.9525 | 1419881.9525 | 1419881.9525 | 1419881.9525 | 1419881.9525 | 1419881.9525 | 1419881.9525 | 1419881.9525 | 1419881.9525 | 1419881.9525
cumulative | ETB | 14198819.525 | 0 | 0 | 0 | 0 | 1419881.9525 | 2839763.905 | 4259645.8575 | 5679527.81 | 7099409.7625 | 8519291.715 | 9939173.6675 | 11359055.62 | 12778937.5725 | 14198819.525
Systems (MEP, lifts) | ETB | 13359074.94 | 0 | 0 | 0 | 0 | 1335907.494 | 1335907.494 | 1335907.494 | 1335907.494 | 1335907.494 | 1335907.494 | 1335907.494 | 1335907.494 | 1335907.494 | 1335907.494
cumulative | ETB | 13359074.94 | 0 | 0 | 0 | 0 | 1335907.494 | 2671814.988 | 4007722.482 | 5343629.976 | 6679537.47 | 8015444.964 | 9351352.458 | 10687259.952 | 12023167.446 | 13359074.94
FF&E (life capped) | ETB | 1484882.4188 | 0 | 0 | 0 | 0 | 212126.0598 | 212126.0598 | 212126.0598 | 212126.0598 | 212126.0598 | 212126.0598 | 212126.0598 | 0 | 0 | 0
cumulative | ETB | 1484882.4188 | 0 | 0 | 0 | 0 | 212126.0598 | 424252.1197 | 636378.1795 | 848504.2393 | 1060630.2992 | 1272756.359 | 1484882.4188 | 1484882.4188 | 1484882.4188 | 1484882.4188
Total depreciation | ETB | 29042776.8838 | 0 | 0 | 0 | 0 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2755789.4465 | 2755789.4465 | 2755789.4465
Cumulative depreciation | ETB | 29042776.8838 | 0 | 0 | 0 | 0 | 2967915.5063 | 5935831.0127 | 8903746.519 | 11871662.0253 | 14839577.5317 | 17807493.038 | 20775408.5443 | 23531197.9908 | 26286987.4373 | 29042776.8838
allocated to investment property | ETB | 29042776.8838 | 0 | 0 | 0 | 0 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2755789.4465 | 2755789.4465 | 2755789.4465
allocated to owner-occupied PPE | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Carrying amounts | የመዝገብ ዋጋ
Investment property (cost model) | ETB | 107276413.5103 | 66220409.442 | 126434853.6732 | 136319190.3941 | 136319190.3941 | 133351274.8878 | 130383359.3814 | 127415443.8751 | 124447528.3688 | 121479612.8624 | 118511697.3561 | 115543781.8498 | 112787992.4033 | 110032202.9568 | 107276413.5103
cumulative depreciation IP | ETB | 29042776.8838 | 0 | 0 | 0 | 0 | 2967915.5063 | 5935831.0127 | 8903746.519 | 11871662.0253 | 14839577.5317 | 17807493.038 | 20775408.5443 | 23531197.9908 | 26286987.4373 | 29042776.8838
Owner-occupied PPE | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
cumulative depreciation PPE | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inventory (IAS 2) | ETB | 0 | 201357987.0816 | 384453491.7122 | 124352709.4274 | 124352709.4274 | 49741083.7709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
cumulative cost of sales | ETB | 414509031.4246 | 0 | 0 | 290156321.9972 | 290156321.9972 | 364767947.6536 | 414509031.4246 | 414509031.4246 | 414509031.4246 | 414509031.4246 | 414509031.4246 | 414509031.4246 | 414509031.4246 | 414509031.4246 | 414509031.4246
Depreciable base (excl. land) | ETB | 99197129.9238 | 99197129.9238 | 99197129.9238 | 99197129.9238 | 99197129.9238 | 99197129.9238 | 99197129.9238 | 99197129.9238 | 99197129.9238 | 99197129.9238 | 99197129.9238 | 99197129.9238 | 99197129.9238 | 99197129.9238 | 99197129.9238
IAS 36 impairment test (value in use vs carrying amount) | የንብረት ዋጋ መቀነስ ፈተና
Value in use (PV of NOI + exit value) | ETB |  | 0 | 0 | 0 | 0 | 291933841.0097 | 319981447.4299 | 347143985.5851 | 376780393.2738 | 409144670.271 | 444521425.9963 | 483230199.7674 | 525630465.4747 | 572127436.6084 | 623178807.875
Carrying amount (IP + PPE) | ETB |  | 66220409.442 | 126434853.6732 | 136319190.3941 | 136319190.3941 | 133351274.8878 | 130383359.3814 | 127415443.8751 | 124447528.3688 | 121479612.8624 | 118511697.3561 | 115543781.8498 | 112787992.4033 | 110032202.9568 | 107276413.5103
Headroom | ETB | 0 | 0 | 0 | 0 | 0 | 158582566.1219 | 189598088.0485 | 219728541.71 | 252332864.9051 | 287665057.4086 | 326009728.6402 | 367686417.9176 | 412842473.0714 | 462095233.6516 | 515902394.3647
Impairment indicator (1 = review) | flag | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 27_Loan
27 · Loan – amortization schedule | [15 empty] | ◂ Start
የብድር ክፍያ ሰንጠረዥ | [15 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Month |  | Total | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36 | M37 | M38 | M39 | M40 | M41 | M42 | M43 | M44 | M45 | M46 | M47 | M48 | M49 | M50 | M51 | M52 | M53 | M54 | M55 | M56 | M57 | M58 | M59 | M60 | M61 | M62 | M63 | M64 | M65 | M66 | M67 | M68 | M69 | M70 | M71 | M72 | M73 | M74 | M75 | M76 | M77 | M78 | M79 | M80 | M81 | M82 | M83 | M84 | M85 | M86 | M87 | M88 | M89 | M90 | M91 | M92 | M93 | M94 | M95 | M96 | M97 | M98 | M99 | M100 | M101 | M102 | M103 | M104 | M105 | M106 | M107 | M108 | M109 | M110 | M111 | M112 | M113 | M114 | M115 | M116 | M117 | M118 | M119 | M120 | M121 | M122 | M123 | M124 | M125 | M126 | M127 | M128 | M129 | M130 | M131 | M132 | M133 | M134 | M135 | M136 | M137 | M138 | M139 | M140 | M141 | M142 | M143 | M144 | M145 | M146 | M147 | M148 | M149 | M150 | M151 | M152 | M153 | M154 | M155 | M156 | M157 | M158 | M159 | M160 | M161 | M162 | M163 | M164 | M165 | M166 | M167 | M168 | M169 | M170 | M171 | M172 | M173 | M174 | M175 | M176 | M177 | M178 | M179 | M180 | M181 | M182 | M183 | M184 | M185 | M186 | M187 | M188 | M189 | M190 | M191 | M192 | M193 | M194 | M195 | M196 | M197 | M198 | M199 | M200 | M201 | M202 | M203 | M204 | M205 | M206 | M207 | M208 | M209 | M210 | M211 | M212 | M213 | M214 | M215 | M216 | M217 | M218 | M219 | M220 | M221 | M222 | M223 | M224 | M225 | M226 | M227 | M228 | M229 | M230 | M231 | M232 | M233 | M234 | M235 | M236 | M237 | M238 | M239 | M240 | M241 | M242 | M243 | M244 | M245 | M246 | M247 | M248 | M249 | M250 | M251 | M252 | M253 | M254 | M255 | M256 | M257 | M258 | M259 | M260 | M261 | M262 | M263 | M264 | M265 | M266 | M267 | M268 | M269 | M270 | M271 | M272 | M273 | M274 | M275 | M276 | M277 | M278 | M279 | M280 | M281 | M282 | M283 | M284 | M285 | M286 | M287 | M288
Month start | time axis 2027-01-01 to 2050-12-01
Annual period |  |  | C1 | C1 | C1 | C1 | C1 | C1 | C1 | C1 | C1 | C1 | C1 | C1 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C2 | C3 | C3 | C3 | C3 | C3 | C3 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O1 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O2 | O3 | O3 | O3 | O3 | O3 | O3 | O3 | O3 | O3 | O3 | O3 | O3 | O4 | O4 | O4 | O4 | O4 | O4 | O4 | O4 | O4 | O4 | O4 | O4 | O5 | O5 | O5 | O5 | O5 | O5 | O5 | O5 | O5 | O5 | O5 | O5 | O6 | O6 | O6 | O6 | O6 | O6 | O6 | O6 | O6 | O6 | O6 | O6 | O7 | O7 | O7 | O7 | O7 | O7 | O7 | O7 | O7 | O7 | O7 | O7 | O8 | O8 | O8 | O8 | O8 | O8 | O8 | O8 | O8 | O8 | O8 | O8 | O9 | O9 | O9 | O9 | O9 | O9 | O9 | O9 | O9 | O9 | O9 | O9 | O10 | O10 | O10 | O10 | O10 | O10 | O10 | O10 | O10 | O10 | O10 | O10 | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – | –
Annual roll-up (C1–C4, O1–O10) | ዓመታዊ ማጠቃለያ
Period |  |  | C1 | C2 | C3 | C4 | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | O9 | O10
Drawdowns | ETB | 115241548.1987 | 0 | 103422150.4283 | 11819397.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IDC capitalised (construction) | ETB | 17456846.4028 | 0 | 7925767.755 | 9531078.6478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest capitalised (grace) | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest paid | ETB | 38525021.0391 | 0 | 0 | 0 | 0 | 14502034.5564 | 7925287.3584 | 3206193.5137 | 2960572.0793 | 2675982.7025 | 2346243.1028 | 1964190.1788 | 1521524.3999 | 1008629.5114 | 414363.6359
Interest expense (P&L) | ETB | 38525021.0391 | 0 | 0 | 0 | 0 | 14502034.5564 | 7925287.3584 | 3206193.5137 | 2960572.0793 | 2675982.7025 | 2346243.1028 | 1964190.1788 | 1521524.3999 | 1008629.5114 | 414363.6359
Scheduled principal | ETB | 25035469.7299 | 0 | 0 | 0 | 0 | 0 | 3098078.1374 | 1548192.8259 | 1793814.2602 | 2078403.6371 | 2408143.2368 | 2790196.1608 | 3232861.9397 | 3745756.8282 | 4340022.7037
Cash sweep prepayment | ETB | 107662924.8716 | 0 | 0 | 0 | 0 | 78736993.9916 | 28925930.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Debt service (interest paid + scheduled principal) | ETB | 63560490.769 | 0 | 0 | 0 | 0 | 14502034.5564 | 11023365.4959 | 4754386.3396 | 4754386.3396 | 4754386.3396 | 4754386.3396 | 4754386.3396 | 4754386.3396 | 4754386.3396 | 4754386.3396
Closing loan balance | ETB | 0 | 0 | 111347918.1833 | 132698394.6015 | 132698394.6015 | 53961400.6099 | 21937391.5925 | 20389198.7666 | 18595384.5064 | 16516980.8692 | 14108837.6324 | 11318641.4716 | 8085779.5319 | 4340022.7037 | 0
Opening loan balance | ETB |  | 0 | 0 | 111347918.1833 | 132698394.6015 | 132698394.6015 | 53961400.6099 | 21937391.5925 | 20389198.7666 | 18595384.5064 | 16516980.8692 | 14108837.6324 | 11318641.4716 | 8085779.5319 | 4340022.7037
Land lease principal paid | ETB | 54000000 | 0 | 4500000 | 4500000 | 0 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000
Land lease interest | ETB | 92610000 | 0 | 9450000 | 9135000 | 0 | 8820000 | 8505000 | 8190000 | 7875000 | 7560000 | 7245000 | 6930000 | 6615000 | 6300000 | 5985000
Lease liability recognised | ETB | 135000000 | 135000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closing lease liability | ETB | 81000000 | 135000000 | 130500000 | 126000000 | 126000000 | 121500000 | 117000000 | 112500000 | 108000000 | 103500000 | 99000000 | 94500000 | 90000000 | 85500000 | 81000000
Loan scalars and lender summary | የብድር ማጠቃለያ
Months between repayments | months | 3
Tenor after completion | months | 120
Number of scheduled repayments | no. | 36
Annual lease instalment | ETB | 4500000
Total drawdowns | ETB | 115241548.1987
Total interest capitalised (IDC + grace) | ETB | 17456846.4028
Total interest (all) | ETB | 55981867.4419
Total principal repaid (scheduled + sweep) | ETB | 132698394.6015
Peak debt (incl. capitalised interest) | ETB | 132698394.6015
Balance at start of repayment | ETB | 53961400.6099
Average life after completion | years | 1.9355
Final repayment month index | no. | 150
Final repayment date | date | 2039-06-30
First scheduled repayment month | no. | 45
Instalment at first scheduled repayment | ETB | 1406806.3587
Monthly-equivalent instalment | ETB | 468935.4529
Balance outstanding at end of tenor | ETB | 0
Balance outstanding at end of O10 | ETB | 0
Min DSCR (from ratios) | x | 1.7682
Average DSCR | x | 4.451
LLCR at completion | x | 1.4636
Min interest cover (ICR) | x | 1.6444
Max gearing | % | 95.47%
Timing and rate | ጊዜና የወለድ መጠን
Month t | no. |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288
Construction flag | flag | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Months after completion k | no. |  | -29 | -28 | -27 | -26 | -25 | -24 | -23 | -22 | -21 | -20 | -19 | -18 | -17 | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258
Loan year after completion | no. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 22
Annual period index | no. |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest rate (p.a.) | % |  | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15%
Grace flag | flag | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Repayment event flag | flag | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining payments incl. this one | no. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 35 | 0 | 0 | 34 | 0 | 0 | 33 | 0 | 0 | 32 | 0 | 0 | 31 | 0 | 0 | 30 | 0 | 0 | 29 | 0 | 0 | 28 | 0 | 0 | 27 | 0 | 0 | 26 | 0 | 0 | 25 | 0 | 0 | 24 | 0 | 0 | 23 | 0 | 0 | 22 | 0 | 0 | 21 | 0 | 0 | 20 | 0 | 0 | 19 | 0 | 0 | 18 | 0 | 0 | 17 | 0 | 0 | 16 | 0 | 0 | 15 | 0 | 0 | 14 | 0 | 0 | 13 | 0 | 0 | 12 | 0 | 0 | 11 | 0 | 0 | 10 | 0 | 0 | 9 | 0 | 0 | 8 | 0 | 0 | 7 | 0 | 0 | 6 | 0 | 0 | 5 | 0 | 0 | 4 | 0 | 0 | 3 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan balance | የብድር ቀሪ ሂሳብ
Opening balance | ETB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13059336.3915 | 31373350.3352 | 48609314.2825 | 64297573.207 | 78083005.8278 | 89736726.1605 | 99151942.0087 | 106328021.7605 | 111347918.1833 | 124706907.4032 | 126265743.7457 | 127844065.5425 | 129442116.3618 | 131060142.8163 | 132698394.6015 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53229111.7588 | 53229111.7588 | 53229111.7588 | 52469362.0758 | 52469362.0758 | 52469362.0758 | 51681121.7797 | 51681121.7797 | 51681121.7797 | 21937391.5925 | 21937391.5925 | 21937391.5925 | 21571447.1923 | 21571447.1923 | 21571447.1923 | 21191779.8771 | 21191779.8771 | 21191779.8771 | 20797875.0376 | 20797875.0376 | 20797875.0376 | 20389198.7666 | 20389198.7666 | 20389198.7666 | 19965197.1355 | 19965197.1355 | 19965197.1355 | 19525295.4431 | 19525295.4431 | 19525295.4431 | 19068897.4374 | 19068897.4374 | 19068897.4374 | 18595384.5064 | 18595384.5064 | 18595384.5064 | 18104114.8404 | 18104114.8404 | 18104114.8404 | 17594422.5621 | 17594422.5621 | 17594422.5621 | 17065616.8232 | 17065616.8232 | 17065616.8232 | 16516980.8692 | 16516980.8692 | 16516980.8692 | 15947771.0669 | 15947771.0669 | 15947771.0669 | 15357215.897 | 15357215.897 | 15357215.897 | 14744514.9083 | 14744514.9083 | 14744514.9083 | 14108837.6324 | 14108837.6324 | 14108837.6324 | 13449322.4587 | 13449322.4587 | 13449322.4587 | 12765075.466 | 12765075.466 | 12765075.466 | 12055169.2111 | 12055169.2111 | 12055169.2111 | 11318641.4716 | 11318641.4716 | 11318641.4716 | 10554493.9419 | 10554493.9419 | 10554493.9419 | 9761690.8798 | 9761690.8798 | 9761690.8798 | 8939157.7029 | 8939157.7029 | 8939157.7029 | 8085779.5319 | 8085779.5319 | 8085779.5319 | 7200399.6795 | 7200399.6795 | 7200399.6795 | 6281818.0825 | 6281818.0825 | 6281818.0825 | 5328789.6757 | 5328789.6757 | 5328789.6757 | 4340022.7037 | 4340022.7037 | 4340022.7037 | 3314176.9702 | 3314176.9702 | 3314176.9702 | 2249862.0216 | 2249862.0216 | 2249862.0216 | 1145635.2626 | 1145635.2626 | 1145635.2626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drawdowns | ETB | 115241548.1987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12898110.0163 | 17926688.631 | 16635848.9561 | 14894461.7245 | 12821444.8945 | 10545859.5159 | 8191117.7987 | 5863388.125 | 3645230.7662 | 11819397.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest accrued | ETB | 55981867.4419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161226.3752 | 387325.3128 | 600114.9911 | 793797.2001 | 963987.7263 | 1107860.8168 | 1224098.0495 | 1312691.6267 | 1374665.6566 | 1539591.4494 | 1558836.3425 | 1578321.7968 | 1598050.8193 | 1618026.4545 | 1638251.7852 | 1658729.9325 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 674517.5076 | 674517.5076 | 674517.5076 | 665363.897 | 665363.897 | 665363.897 | 655867.0259 | 655867.0259 | 655867.0259 | 646014.0222 | 646014.0222 | 646014.0222 | 274217.3949 | 274217.3949 | 274217.3949 | 269643.0899 | 269643.0899 | 269643.0899 | 264897.2485 | 264897.2485 | 264897.2485 | 259973.438 | 259973.438 | 259973.438 | 254864.9846 | 254864.9846 | 254864.9846 | 249564.9642 | 249564.9642 | 249564.9642 | 244066.193 | 244066.193 | 244066.193 | 238361.218 | 238361.218 | 238361.218 | 232442.3063 | 232442.3063 | 232442.3063 | 226301.4355 | 226301.4355 | 226301.4355 | 219930.282 | 219930.282 | 219930.282 | 213320.2103 | 213320.2103 | 213320.2103 | 206462.2609 | 206462.2609 | 206462.2609 | 199347.1383 | 199347.1383 | 199347.1383 | 191965.1987 | 191965.1987 | 191965.1987 | 184306.4364 | 184306.4364 | 184306.4364 | 176360.4704 | 176360.4704 | 176360.4704 | 168116.5307 | 168116.5307 | 168116.5307 | 159563.4433 | 159563.4433 | 159563.4433 | 150689.6151 | 150689.6151 | 150689.6151 | 141483.0184 | 141483.0184 | 141483.0184 | 131931.1743 | 131931.1743 | 131931.1743 | 122021.136 | 122021.136 | 122021.136 | 111739.4713 | 111739.4713 | 111739.4713 | 101072.2441 | 101072.2441 | 101072.2441 | 90004.996 | 90004.996 | 90004.996 | 78522.726 | 78522.726 | 78522.726 | 66609.8709 | 66609.8709 | 66609.8709 | 54250.2838 | 54250.2838 | 54250.2838 | 41427.2121 | 41427.2121 | 41427.2121 | 28123.2753 | 28123.2753 | 28123.2753 | 14320.4408 | 14320.4408 | 14320.4408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest capitalised – construction (IDC) | ETB | 17456846.4028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161226.3752 | 387325.3128 | 600114.9911 | 793797.2001 | 963987.7263 | 1107860.8168 | 1224098.0495 | 1312691.6267 | 1374665.6566 | 1539591.4494 | 1558836.3425 | 1578321.7968 | 1598050.8193 | 1618026.4545 | 1638251.7852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest capitalised – grace | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interest paid in cash | ETB | 38525021.0391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658729.9325 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 674517.5076 | 674517.5076 | 674517.5076 | 665363.897 | 665363.897 | 665363.897 | 655867.0259 | 655867.0259 | 655867.0259 | 646014.0222 | 646014.0222 | 646014.0222 | 274217.3949 | 274217.3949 | 274217.3949 | 269643.0899 | 269643.0899 | 269643.0899 | 264897.2485 | 264897.2485 | 264897.2485 | 259973.438 | 259973.438 | 259973.438 | 254864.9846 | 254864.9846 | 254864.9846 | 249564.9642 | 249564.9642 | 249564.9642 | 244066.193 | 244066.193 | 244066.193 | 238361.218 | 238361.218 | 238361.218 | 232442.3063 | 232442.3063 | 232442.3063 | 226301.4355 | 226301.4355 | 226301.4355 | 219930.282 | 219930.282 | 219930.282 | 213320.2103 | 213320.2103 | 213320.2103 | 206462.2609 | 206462.2609 | 206462.2609 | 199347.1383 | 199347.1383 | 199347.1383 | 191965.1987 | 191965.1987 | 191965.1987 | 184306.4364 | 184306.4364 | 184306.4364 | 176360.4704 | 176360.4704 | 176360.4704 | 168116.5307 | 168116.5307 | 168116.5307 | 159563.4433 | 159563.4433 | 159563.4433 | 150689.6151 | 150689.6151 | 150689.6151 | 141483.0184 | 141483.0184 | 141483.0184 | 131931.1743 | 131931.1743 | 131931.1743 | 122021.136 | 122021.136 | 122021.136 | 111739.4713 | 111739.4713 | 111739.4713 | 101072.2441 | 101072.2441 | 101072.2441 | 90004.996 | 90004.996 | 90004.996 | 78522.726 | 78522.726 | 78522.726 | 66609.8709 | 66609.8709 | 66609.8709 | 54250.2838 | 54250.2838 | 54250.2838 | 41427.2121 | 41427.2121 | 41427.2121 | 28123.2753 | 28123.2753 | 28123.2753 | 14320.4408 | 14320.4408 | 14320.4408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance at start of repayment | ETB | 53961400.6099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53961400.6099
Periodic rate | % |  | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75% | 3.75%
Balloon amount | ETB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scheduled principal | ETB | 25035469.7299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732288.8511 | 0 | 0 | 759749.683 | 0 | 0 | 788240.2961 | 0 | 0 | 817799.3072 | 0 | 0 | 365944.4002 | 0 | 0 | 379667.3152 | 0 | 0 | 393904.8395 | 0 | 0 | 408676.271 | 0 | 0 | 424001.6312 | 0 | 0 | 439901.6923 | 0 | 0 | 456398.0058 | 0 | 0 | 473512.931 | 0 | 0 | 491269.6659 | 0 | 0 | 509692.2784 | 0 | 0 | 528805.7388 | 0 | 0 | 548635.954 | 0 | 0 | 569209.8023 | 0 | 0 | 590555.1699 | 0 | 0 | 612700.9888 | 0 | 0 | 635677.2758 | 0 | 0 | 659515.1737 | 0 | 0 | 684246.9927 | 0 | 0 | 709906.2549 | 0 | 0 | 736527.7395 | 0 | 0 | 764147.5297 | 0 | 0 | 792803.0621 | 0 | 0 | 822533.1769 | 0 | 0 | 853378.171 | 0 | 0 | 885379.8525 | 0 | 0 | 918581.5969 | 0 | 0 | 953028.4068 | 0 | 0 | 988766.9721 | 0 | 0 | 1025845.7335 | 0 | 0 | 1064314.9485 | 0 | 0 | 1104226.7591 | 0 | 0 | 1145635.2626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash sweep base (sales proceeds) | ETB | 269157312.179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98231356.979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98611128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72314827.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash sweep prepayment | ETB | 107662924.8716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39292542.7916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39444451.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28925930.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closing balance | ETB | 132698394.6015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13059336.3915 | 31373350.3352 | 48609314.2825 | 64297573.207 | 78083005.8278 | 89736726.1605 | 99151942.0087 | 106328021.7605 | 111347918.1833 | 124706907.4032 | 126265743.7457 | 127844065.5425 | 129442116.3618 | 131060142.8163 | 132698394.6015 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 93405851.8099 | 53961400.6099 | 53961400.6099 | 53961400.6099 | 53229111.7588 | 53229111.7588 | 53229111.7588 | 52469362.0758 | 52469362.0758 | 52469362.0758 | 51681121.7797 | 51681121.7797 | 51681121.7797 | 21937391.5925 | 21937391.5925 | 21937391.5925 | 21571447.1923 | 21571447.1923 | 21571447.1923 | 21191779.8771 | 21191779.8771 | 21191779.8771 | 20797875.0376 | 20797875.0376 | 20797875.0376 | 20389198.7666 | 20389198.7666 | 20389198.7666 | 19965197.1355 | 19965197.1355 | 19965197.1355 | 19525295.4431 | 19525295.4431 | 19525295.4431 | 19068897.4374 | 19068897.4374 | 19068897.4374 | 18595384.5064 | 18595384.5064 | 18595384.5064 | 18104114.8404 | 18104114.8404 | 18104114.8404 | 17594422.5621 | 17594422.5621 | 17594422.5621 | 17065616.8232 | 17065616.8232 | 17065616.8232 | 16516980.8692 | 16516980.8692 | 16516980.8692 | 15947771.0669 | 15947771.0669 | 15947771.0669 | 15357215.897 | 15357215.897 | 15357215.897 | 14744514.9083 | 14744514.9083 | 14744514.9083 | 14108837.6324 | 14108837.6324 | 14108837.6324 | 13449322.4587 | 13449322.4587 | 13449322.4587 | 12765075.466 | 12765075.466 | 12765075.466 | 12055169.2111 | 12055169.2111 | 12055169.2111 | 11318641.4716 | 11318641.4716 | 11318641.4716 | 10554493.9419 | 10554493.9419 | 10554493.9419 | 9761690.8798 | 9761690.8798 | 9761690.8798 | 8939157.7029 | 8939157.7029 | 8939157.7029 | 8085779.5319 | 8085779.5319 | 8085779.5319 | 7200399.6795 | 7200399.6795 | 7200399.6795 | 6281818.0825 | 6281818.0825 | 6281818.0825 | 5328789.6757 | 5328789.6757 | 5328789.6757 | 4340022.7037 | 4340022.7037 | 4340022.7037 | 3314176.9702 | 3314176.9702 | 3314176.9702 | 2249862.0216 | 2249862.0216 | 2249862.0216 | 1145635.2626 | 1145635.2626 | 1145635.2626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scheduled debt service (interest paid + principal) | ETB | 63560490.769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1658729.9325 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 1167573.1476 | 674517.5076 | 674517.5076 | 1406806.3587 | 665363.897 | 665363.897 | 1425113.58 | 655867.0259 | 655867.0259 | 1444107.3221 | 646014.0222 | 646014.0222 | 1463813.3295 | 274217.3949 | 274217.3949 | 640161.7951 | 269643.0899 | 269643.0899 | 649310.4051 | 264897.2485 | 264897.2485 | 658802.088 | 259973.438 | 259973.438 | 668649.709 | 254864.9846 | 254864.9846 | 678866.6157 | 249564.9642 | 249564.9642 | 689466.6565 | 244066.193 | 244066.193 | 700464.1988 | 238361.218 | 238361.218 | 711874.149 | 232442.3063 | 232442.3063 | 723711.9722 | 226301.4355 | 226301.4355 | 735993.7139 | 219930.282 | 219930.282 | 748736.0208 | 213320.2103 | 213320.2103 | 761956.1643 | 206462.2609 | 206462.2609 | 775672.0632 | 199347.1383 | 199347.1383 | 789902.3082 | 191965.1987 | 191965.1987 | 804666.1875 | 184306.4364 | 184306.4364 | 819983.7122 | 176360.4704 | 176360.4704 | 835875.6441 | 168116.5307 | 168116.5307 | 852363.5234 | 159563.4433 | 159563.4433 | 869469.6982 | 150689.6151 | 150689.6151 | 887217.3546 | 141483.0184 | 141483.0184 | 905630.5481 | 131931.1743 | 131931.1743 | 924734.2364 | 122021.136 | 122021.136 | 944554.3129 | 111739.4713 | 111739.4713 | 965117.6423 | 101072.2441 | 101072.2441 | 986452.0966 | 90004.996 | 90004.996 | 1008586.5929 | 78522.726 | 78522.726 | 1031551.1328 | 66609.8709 | 66609.8709 | 1055376.843 | 54250.2838 | 54250.2838 | 1080096.0173 | 41427.2121 | 41427.2121 | 1105742.1606 | 28123.2753 | 28123.2753 | 1132350.0344 | 14320.4408 | 14320.4408 | 1159955.7033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Helper: month index if principal paid | no. | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 45 | 0 | 0 | 48 | 0 | 0 | 51 | 0 | 0 | 54 | 0 | 0 | 57 | 0 | 0 | 60 | 0 | 0 | 63 | 0 | 0 | 66 | 0 | 0 | 69 | 0 | 0 | 72 | 0 | 0 | 75 | 0 | 0 | 78 | 0 | 0 | 81 | 0 | 0 | 84 | 0 | 0 | 87 | 0 | 0 | 90 | 0 | 0 | 93 | 0 | 0 | 96 | 0 | 0 | 99 | 0 | 0 | 102 | 0 | 0 | 105 | 0 | 0 | 108 | 0 | 0 | 111 | 0 | 0 | 114 | 0 | 0 | 117 | 0 | 0 | 120 | 0 | 0 | 123 | 0 | 0 | 126 | 0 | 0 | 129 | 0 | 0 | 132 | 0 | 0 | 135 | 0 | 0 | 138 | 0 | 0 | 141 | 0 | 0 | 144 | 0 | 0 | 147 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Helper: month index of scheduled payment (else 999) | no. | 45 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 45 | 999 | 999 | 48 | 999 | 999 | 51 | 999 | 999 | 54 | 999 | 999 | 57 | 999 | 999 | 60 | 999 | 999 | 63 | 999 | 999 | 66 | 999 | 999 | 69 | 999 | 999 | 72 | 999 | 999 | 75 | 999 | 999 | 78 | 999 | 999 | 81 | 999 | 999 | 84 | 999 | 999 | 87 | 999 | 999 | 90 | 999 | 999 | 93 | 999 | 999 | 96 | 999 | 999 | 99 | 999 | 999 | 102 | 999 | 999 | 105 | 999 | 999 | 108 | 999 | 999 | 111 | 999 | 999 | 114 | 999 | 999 | 117 | 999 | 999 | 120 | 999 | 999 | 123 | 999 | 999 | 126 | 999 | 999 | 129 | 999 | 999 | 132 | 999 | 999 | 135 | 999 | 999 | 138 | 999 | 999 | 141 | 999 | 999 | 144 | 999 | 999 | 147 | 999 | 999 | 150 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999
Helper: principal × years after completion | ETB | 256833473.5939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3274378.566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39444451.2 | 0 | 0 | 915361.0639 | 0 | 0 | 1139624.5245 | 0 | 0 | 1379420.5182 | 0 | 0 | 59487460.3745 | 0 | 0 | 823374.9004 | 0 | 0 | 949168.288 | 0 | 0 | 1083238.3086 | 0 | 0 | 1226028.813 | 0 | 0 | 1378005.3012 | 0 | 0 | 1539655.9231 | 0 | 0 | 1711492.5217 | 0 | 0 | 1894051.724 | 0 | 0 | 2087896.0801 | 0 | 0 | 2293615.2527 | 0 | 0 | 2511827.2594 | 0 | 0 | 2743179.7701 | 0 | 0 | 2988351.4621 | 0 | 0 | 3248053.4344 | 0 | 0 | 3523030.6854 | 0 | 0 | 3814063.655 | 0 | 0 | 4121969.8355 | 0 | 0 | 4447605.4525 | 0 | 0 | 4791867.2207 | 0 | 0 | 5155694.1764 | 0 | 0 | 5540069.5904 | 0 | 0 | 5946022.9656 | 0 | 0 | 6374632.121 | 0 | 0 | 6827025.3683 | 0 | 0 | 7304383.7827 | 0 | 0 | 7807943.5738 | 0 | 0 | 8338998.5595 | 0 | 0 | 8898902.7485 | 0 | 0 | 9489073.035 | 0 | 0 | 10110992.0109 | 0 | 0 | 10766210.9011 | 0 | 0 | 11456352.6255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Land lease liability | የሊዝ ዕዳ
Lease liability recognised | ETB | 135000000 | 135000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Opening lease liability | ETB |  | 0 | 135000000 | 135000000 | 135000000 | 135000000 | 135000000 | 135000000 | 135000000 | 135000000 | 135000000 | 135000000 | 135000000 | 135000000 | 130500000 | 130500000 | 130500000 | 130500000 | 130500000 | 130500000 | 130500000 | 130500000 | 130500000 | 130500000 | 130500000 | 130500000 | 126000000 | 126000000 | 126000000 | 126000000 | 126000000 | 126000000 | 126000000 | 126000000 | 126000000 | 126000000 | 126000000 | 126000000 | 121500000 | 121500000 | 121500000 | 121500000 | 121500000 | 121500000 | 121500000 | 121500000 | 121500000 | 121500000 | 121500000 | 121500000 | 117000000 | 117000000 | 117000000 | 117000000 | 117000000 | 117000000 | 117000000 | 117000000 | 117000000 | 117000000 | 117000000 | 117000000 | 112500000 | 112500000 | 112500000 | 112500000 | 112500000 | 112500000 | 112500000 | 112500000 | 112500000 | 112500000 | 112500000 | 112500000 | 108000000 | 108000000 | 108000000 | 108000000 | 108000000 | 108000000 | 108000000 | 108000000 | 108000000 | 108000000 | 108000000 | 108000000 | 103500000 | 103500000 | 103500000 | 103500000 | 103500000 | 103500000 | 103500000 | 103500000 | 103500000 | 103500000 | 103500000 | 103500000 | 99000000 | 99000000 | 99000000 | 99000000 | 99000000 | 99000000 | 99000000 | 99000000 | 99000000 | 99000000 | 99000000 | 99000000 | 94500000 | 94500000 | 94500000 | 94500000 | 94500000 | 94500000 | 94500000 | 94500000 | 94500000 | 94500000 | 94500000 | 94500000 | 90000000 | 90000000 | 90000000 | 90000000 | 90000000 | 90000000 | 90000000 | 90000000 | 90000000 | 90000000 | 90000000 | 90000000 | 85500000 | 85500000 | 85500000 | 85500000 | 85500000 | 85500000 | 85500000 | 85500000 | 85500000 | 85500000 | 85500000 | 85500000 | 81000000 | 81000000 | 81000000 | 81000000 | 81000000 | 81000000 | 81000000 | 81000000 | 81000000 | 81000000 | 81000000 | 81000000 | 76500000 | 76500000 | 76500000 | 76500000 | 76500000 | 76500000 | 76500000 | 76500000 | 76500000 | 76500000 | 76500000 | 76500000 | 72000000 | 72000000 | 72000000 | 72000000 | 72000000 | 72000000 | 72000000 | 72000000 | 72000000 | 72000000 | 72000000 | 72000000 | 67500000 | 67500000 | 67500000 | 67500000 | 67500000 | 67500000 | 67500000 | 67500000 | 67500000 | 67500000 | 67500000 | 67500000 | 63000000 | 63000000 | 63000000 | 63000000 | 63000000 | 63000000 | 63000000 | 63000000 | 63000000 | 63000000 | 63000000 | 63000000 | 58500000 | 58500000 | 58500000 | 58500000 | 58500000 | 58500000 | 58500000 | 58500000 | 58500000 | 58500000 | 58500000 | 58500000 | 54000000 | 54000000 | 54000000 | 54000000 | 54000000 | 54000000 | 54000000 | 54000000 | 54000000 | 54000000 | 54000000 | 54000000 | 49500000 | 49500000 | 49500000 | 49500000 | 49500000 | 49500000 | 49500000 | 49500000 | 49500000 | 49500000 | 49500000 | 49500000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 40500000 | 40500000 | 40500000 | 40500000 | 40500000 | 40500000 | 40500000 | 40500000 | 40500000 | 40500000 | 40500000 | 40500000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 31500000 | 31500000 | 31500000 | 31500000 | 31500000 | 31500000 | 31500000 | 31500000 | 31500000 | 31500000 | 31500000
Instalment month flag | flag | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lease instalment (principal) | ETB | 103500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lease interest | ETB | 137655000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9450000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8820000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8505000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8190000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7875000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7560000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7245000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6930000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6615000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5985000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5670000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5355000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5040000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4725000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4410000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4095000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3780000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3465000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2835000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closing lease liability | ETB | 31500000 | 135000000 | 135000000 | 135000000 | 135000000 | 135000000 | 135000000 | 135000000 | 135000000 | 135000000 | 135000000 | 135000000 | 135000000 | 130500000 | 130500000 | 130500000 | 130500000 | 130500000 | 130500000 | 130500000 | 130500000 | 130500000 | 130500000 | 130500000 | 130500000 | 126000000 | 126000000 | 126000000 | 126000000 | 126000000 | 126000000 | 126000000 | 126000000 | 126000000 | 126000000 | 126000000 | 126000000 | 121500000 | 121500000 | 121500000 | 121500000 | 121500000 | 121500000 | 121500000 | 121500000 | 121500000 | 121500000 | 121500000 | 121500000 | 117000000 | 117000000 | 117000000 | 117000000 | 117000000 | 117000000 | 117000000 | 117000000 | 117000000 | 117000000 | 117000000 | 117000000 | 112500000 | 112500000 | 112500000 | 112500000 | 112500000 | 112500000 | 112500000 | 112500000 | 112500000 | 112500000 | 112500000 | 112500000 | 108000000 | 108000000 | 108000000 | 108000000 | 108000000 | 108000000 | 108000000 | 108000000 | 108000000 | 108000000 | 108000000 | 108000000 | 103500000 | 103500000 | 103500000 | 103500000 | 103500000 | 103500000 | 103500000 | 103500000 | 103500000 | 103500000 | 103500000 | 103500000 | 99000000 | 99000000 | 99000000 | 99000000 | 99000000 | 99000000 | 99000000 | 99000000 | 99000000 | 99000000 | 99000000 | 99000000 | 94500000 | 94500000 | 94500000 | 94500000 | 94500000 | 94500000 | 94500000 | 94500000 | 94500000 | 94500000 | 94500000 | 94500000 | 90000000 | 90000000 | 90000000 | 90000000 | 90000000 | 90000000 | 90000000 | 90000000 | 90000000 | 90000000 | 90000000 | 90000000 | 85500000 | 85500000 | 85500000 | 85500000 | 85500000 | 85500000 | 85500000 | 85500000 | 85500000 | 85500000 | 85500000 | 85500000 | 81000000 | 81000000 | 81000000 | 81000000 | 81000000 | 81000000 | 81000000 | 81000000 | 81000000 | 81000000 | 81000000 | 81000000 | 76500000 | 76500000 | 76500000 | 76500000 | 76500000 | 76500000 | 76500000 | 76500000 | 76500000 | 76500000 | 76500000 | 76500000 | 72000000 | 72000000 | 72000000 | 72000000 | 72000000 | 72000000 | 72000000 | 72000000 | 72000000 | 72000000 | 72000000 | 72000000 | 67500000 | 67500000 | 67500000 | 67500000 | 67500000 | 67500000 | 67500000 | 67500000 | 67500000 | 67500000 | 67500000 | 67500000 | 63000000 | 63000000 | 63000000 | 63000000 | 63000000 | 63000000 | 63000000 | 63000000 | 63000000 | 63000000 | 63000000 | 63000000 | 58500000 | 58500000 | 58500000 | 58500000 | 58500000 | 58500000 | 58500000 | 58500000 | 58500000 | 58500000 | 58500000 | 58500000 | 54000000 | 54000000 | 54000000 | 54000000 | 54000000 | 54000000 | 54000000 | 54000000 | 54000000 | 54000000 | 54000000 | 54000000 | 49500000 | 49500000 | 49500000 | 49500000 | 49500000 | 49500000 | 49500000 | 49500000 | 49500000 | 49500000 | 49500000 | 49500000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 40500000 | 40500000 | 40500000 | 40500000 | 40500000 | 40500000 | 40500000 | 40500000 | 40500000 | 40500000 | 40500000 | 40500000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 31500000 | 31500000 | 31500000 | 31500000 | 31500000 | 31500000 | 31500000 | 31500000 | 31500000 | 31500000 | 31500000 | 31500000

## 28_Tax
28 · Tax – CIT, losses, deferred tax, UPT | [15 empty] | ◂ Start
ግብር – የገቢ ግብር፣ ኪሳራ፣ የዘገየ ግብር | [15 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Period |  | Total | C1 | C2 | C3 | C4 | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | O9 | O10
Period end (Gregorian) |  |  | 2027-12-31 | 2028-12-31 | 2029-06-30 | 2029-06-30 | 2030-06-30 | 2031-06-30 | 2032-06-30 | 2033-06-30 | 2034-06-30 | 2035-06-30 | 2036-06-30 | 2037-06-30 | 2038-06-30 | 2039-06-30
Ethiopian calendar year |  |  | EC 2020 | EC 2021 | EC 2021 | EC 2021 | EC 2022 | EC 2023 | EC 2024 | EC 2025 | EC 2026 | EC 2027 | EC 2028 | EC 2029 | EC 2030 | EC 2031
Taxable profit | ግብር የሚከፈልበት ትርፍ
Profit before tax | ETB | 256920854.3363 | -1075351.0145 | -10632886.116 | 19081636.0322 | 0 | 12060409.3919 | 25753780.4344 | 16149697.3375 | 18941438.7821 | 21945018.178 | 23257528.2299 | 26745119.3302 | 30721212.7222 | 34787685.6435 | 39185565.385
Add: accounting depreciation | ETB | 29042776.8838 | 0 | 0 | 0 | 0 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2755789.4465 | 2755789.4465 | 2755789.4465
Less: tax depreciation – buildings (straight line) | ETB | 35497048.8124 | 0 | 0 | 0 | 0 | 3549704.8812 | 3549704.8812 | 3549704.8812 | 3549704.8812 | 3549704.8812 | 3549704.8812 | 3549704.8812 | 3549704.8812 | 3549704.8812 | 3549704.8812
cumulative | ETB | 35497048.8124 | 0 | 0 | 0 | 0 | 3549704.8812 | 7099409.7625 | 10649114.6437 | 14198819.525 | 17748524.4062 | 21298229.2875 | 24847934.1687 | 28397639.05 | 31947343.9312 | 35497048.8124
Plant pool – opening WDV | ETB |  | 0 | 0 | 0 | 0 | 28203032.2989 | 22562425.8391 | 18049940.6713 | 14439952.537 | 11551962.0296 | 9241569.6237 | 7393255.699 | 5914604.5592 | 4731683.6473 | 3785346.9179
Less: tax depreciation – plant pool (diminishing) | ETB | 25174754.7646 | 0 | 0 | 0 | 0 | 5640606.4598 | 4512485.1678 | 3609988.1343 | 2887990.5074 | 2310392.4059 | 1848313.9247 | 1478651.1398 | 1182920.9118 | 946336.7295 | 757069.3836
Plant pool – closing WDV | ETB | 3028277.5343 | 0 | 0 | 0 | 0 | 22562425.8391 | 18049940.6713 | 14439952.537 | 11551962.0296 | 9241569.6237 | 7393255.699 | 5914604.5592 | 4731683.6473 | 3785346.9179 | 3028277.5343
cumulative plant allowances | ETB | 25174754.7646 | 0 | 0 | 0 | 0 | 5640606.4598 | 10153091.6276 | 13763079.7619 | 16651070.2693 | 18961462.6752 | 20809776.5999 | 22288427.7397 | 23471348.6516 | 24417685.381 | 25174754.7646
Taxable income before losses | ETB | 225291827.6431 | -1075351.0145 | -10632886.116 | 19081636.0322 | 0 | 5838013.5572 | 20659505.8917 | 11957919.8283 | 15471658.8998 | 19052836.3971 | 20827424.9303 | 24684678.8155 | 28744376.3757 | 33047433.4793 | 37634580.5667
Tax loss arising | ETB | 11708237.1305 | 1075351.0145 | 10632886.116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loss carry-forward by vintage (FIFO, expiry after LCF_YEARS) | ኪሳራ በዓመት
Vintage C1 – available at start | ETB |  | 0 | 1075351.0145 | 1075351.0145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vintage C2 – available at start | ETB |  | 0 | 0 | 10632886.116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vintage C3 – available at start | ETB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vintage C4 – available at start | ETB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vintage O1 – available at start | ETB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vintage O2 – available at start | ETB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vintage O3 – available at start | ETB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vintage O4 – available at start | ETB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vintage O5 – available at start | ETB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vintage O6 – available at start | ETB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vintage O7 – available at start | ETB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vintage O8 – available at start | ETB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vintage O9 – available at start | ETB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vintage O10 – available at start | ETB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Losses available at start | ETB |  | 0 | 1075351.0145 | 11708237.1305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Losses used | ETB | 11708237.1305 | 0 | 0 | 11708237.1305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used from vintage C1 | ETB | 1075351.0145 | 0 | 0 | 1075351.0145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used from vintage C2 | ETB | 10632886.116 | 0 | 0 | 10632886.116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used from vintage C3 | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used from vintage C4 | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used from vintage O1 | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used from vintage O2 | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used from vintage O3 | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used from vintage O4 | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used from vintage O5 | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used from vintage O6 | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used from vintage O7 | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used from vintage O8 | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used from vintage O9 | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used from vintage O10 | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Losses carried forward (end) | ETB | 0 | 1075351.0145 | 11708237.1305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Losses expired | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Current tax | የዘመኑ ግብር
Taxable profit after losses | ETB | 225291827.6431 | 0 | 0 | 7373398.9017 | 0 | 5838013.5572 | 20659505.8917 | 11957919.8283 | 15471658.8998 | 19052836.3971 | 20827424.9303 | 24684678.8155 | 28744376.3757 | 33047433.4793 | 37634580.5667
Corporate income tax | ETB | 67587548.2929 | 0 | 0 | 2212019.6705 | 0 | 1751404.0672 | 6197851.7675 | 3587375.9485 | 4641497.6699 | 5715850.9191 | 6248227.4791 | 7405403.6446 | 8623312.9127 | 9914230.0438 | 11290374.17
Deferred tax (IAS 12) | የዘገየ ግብር
Temporary difference (tax allowances − book depreciation) | ETB | 31629026.6932 | 0 | 0 | 0 | 0 | 6222395.8347 | 11316670.3774 | 15508447.8866 | 18978227.7689 | 21870409.5497 | 24300512.8494 | 26360953.3641 | 28337789.7107 | 30078041.8749 | 31629026.6932
Deferred tax liability on assets | ETB | 9488708.008 | 0 | 0 | 0 | 0 | 1866718.7504 | 3395001.1132 | 4652534.366 | 5693468.3307 | 6561122.8649 | 7290153.8548 | 7908286.0092 | 8501336.9132 | 9023412.5625 | 9488708.008
Deferred tax asset on losses | ETB | 0 | 322605.3044 | 3512471.1391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net deferred tax liability / (asset) | ETB | 9488708.008 | -322605.3044 | -3512471.1391 | 0 | 0 | 1866718.7504 | 3395001.1132 | 4652534.366 | 5693468.3307 | 6561122.8649 | 7290153.8548 | 7908286.0092 | 8501336.9132 | 9023412.5625 | 9488708.008
Deferred tax expense / (credit) | ETB | 9488708.008 | -322605.3044 | -3189865.8348 | 3512471.1391 | 0 | 1866718.7504 | 1528282.3628 | 1257533.2528 | 1040933.9647 | 867654.5343 | 729030.9899 | 618132.1544 | 593050.904 | 522075.6493 | 465295.4455
Undistributed profits tax (closed form – no circularity) | ያልተከፋፈለ ትርፍ ግብር
Profit after CIT & deferred tax | ETB | 179844598.0354 | -752745.7102 | -7443020.2812 | 13357145.2225 | 0 | 8442286.5743 | 18027646.3041 | 11304788.1362 | 13259007.1475 | 15361512.7246 | 16280269.7609 | 18721583.5311 | 21504848.9056 | 24351379.9504 | 27429895.7695
Undistributed share k = (1 − reserve %)(1 − payout) | % |  | 47.5% | 47.5% | 47.5% | 47.5% | 47.5% | 47.5% | 47.5% | 47.5% | 47.5% | 47.5% | 47.5% | 47.5% | 47.5% | 47.5%
UPT = r·k·PAT / (1 + r·k) | ETB | 8526890.0155 | 0 | 0 | 605693.9361 | 0 | 382824.4509 | 817482.768 | 512627.6243 | 601243.7609 | 696584.1092 | 738246.1228 | 848950.0885 | 975160.2129 | 1104239.1863 | 1243837.7557
Tax payable and cash | የሚከፈል ግብር
Current tax charge (CIT + UPT) | ETB | 76114438.3085 | 0 | 0 | 2817713.6066 | 0 | 2134228.518 | 7015334.5355 | 4100003.5728 | 5242741.4308 | 6412435.0284 | 6986473.6019 | 8254353.7332 | 9598473.1256 | 11018469.2301 | 12534211.9257
Tax paid (following period) | ETB | 63580226.3828 | 0 | 0 | 0 | 2817713.6066 | 0 | 2134228.518 | 7015334.5355 | 4100003.5728 | 5242741.4308 | 6412435.0284 | 6986473.6019 | 8254353.7332 | 9598473.1256 | 11018469.2301
Tax payable (end) | ETB | 12534211.9257 | 0 | 0 | 2817713.6066 | 0 | 2134228.518 | 7015334.5355 | 4100003.5728 | 5242741.4308 | 6412435.0284 | 6986473.6019 | 8254353.7332 | 9598473.1256 | 11018469.2301 | 12534211.9257
Memo: dividend WHT (borne by shareholders) | ETB | -16162691.1894 | 0 | 0 | 0 | 0 | -817077.8569 | -2061398.6715 | -1079216.0512 | -1265776.3387 | -1466492.8615 | -1554202.3638 | -1787263.3443 | -1762980.2542 | -1946981.6963 | -2421301.751
Check: negative loss balances | flag | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 29_VAT
29 · VAT – output, input, refunds | [15 empty] | ◂ Start
የተጨማሪ እሴት ታክስ | [15 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Period |  | Total | C1 | C2 | C3 | C4 | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | O9 | O10
Period end (Gregorian) |  |  | 2027-12-31 | 2028-12-31 | 2029-06-30 | 2029-06-30 | 2030-06-30 | 2031-06-30 | 2032-06-30 | 2033-06-30 | 2034-06-30 | 2035-06-30 | 2036-06-30 | 2037-06-30 | 2038-06-30 | 2039-06-30
Ethiopian calendar year |  |  | EC 2020 | EC 2021 | EC 2021 | EC 2021 | EC 2022 | EC 2023 | EC 2024 | EC 2025 | EC 2026 | EC 2027 | EC 2028 | EC 2029 | EC 2030 | EC 2031
Output VAT – rent & recoveries | ETB | 67677992.4879 | 0 | 0 | 0 | 0 | 3143054.0496 | 4543405.5154 | 5640089.6053 | 6091296.7737 | 6578600.5156 | 7104888.5569 | 7673279.6414 | 8287142.0127 | 8950113.3737 | 9666122.4436
Output VAT – sales | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total output VAT | ETB | 67677992.4879 | 0 | 0 | 0 | 0 | 3143054.0496 | 4543405.5154 | 5640089.6053 | 6091296.7737 | 6578600.5156 | 7104888.5569 | 7673279.6414 | 8287142.0127 | 8950113.3737 | 9666122.4436
Input VAT – capex | ETB | 39251693.9936 | 11507402.663 | 24593612.3769 | 3150678.9537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Input VAT – opex | ETB | 6561242.6101 | 80651.3261 | 88716.4587 | 76210.6077 | 0 | 371084.819 | 470748.7687 | 511201.453 | 553007.6888 | 598249.4355 | 647210.6351 | 700198.8551 | 757547.2696 | 819616.8079 | 886798.485
Total input VAT | ETB | 45812936.6037 | 11588053.989 | 24682328.8356 | 3226889.5614 | 0 | 371084.819 | 470748.7687 | 511201.453 | 553007.6888 | 598249.4355 | 647210.6351 | 700198.8551 | 757547.2696 | 819616.8079 | 886798.485
Opening VAT credit (receivable) | ETB |  | 0 | 11588053.989 | 24682328.8356 | 3226889.5614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Refund received (prior credit) | ETB | 39497272.386 | 0 | 11588053.989 | 24682328.8356 | 3226889.5614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VAT paid to authority | ETB | 61362328.2703 | 0 | 0 | 0 | 0 | 2771969.2306 | 4072656.7467 | 5128888.1523 | 5538289.0849 | 5980351.0801 | 6457677.9218 | 6973080.7863 | 7529594.7431 | 8130496.5658 | 8779323.9586
Closing VAT credit (receivable) | ETB | 0 | 11588053.989 | 24682328.8356 | 3226889.5614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Check: roll-forward difference | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 30_WorkingCap
30 · Working capital | [15 empty] | ◂ Start
የሥራ ማስኬጃ ካፒታል | [15 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Period |  | Total | C1 | C2 | C3 | C4 | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | O9 | O10
Period end (Gregorian) |  |  | 2027-12-31 | 2028-12-31 | 2029-06-30 | 2029-06-30 | 2030-06-30 | 2031-06-30 | 2032-06-30 | 2033-06-30 | 2034-06-30 | 2035-06-30 | 2036-06-30 | 2037-06-30 | 2038-06-30 | 2039-06-30
Ethiopian calendar year |  |  | EC 2020 | EC 2021 | EC 2021 | EC 2021 | EC 2022 | EC 2023 | EC 2024 | EC 2025 | EC 2026 | EC 2027 | EC 2028 | EC 2029 | EC 2030 | EC 2031
Retention release period index | no. | 5
Rent receivables | ETB | 4761995.7244 | 0 | 0 | 0 | 0 | 1548419.2377 | 2238299.5627 | 2778578.7675 | 3000865.0689 | 3240934.2744 | 3500209.0163 | 3780225.7376 | 4082643.7966 | 4409255.3004 | 4761995.7244
Opex payables | ETB | 1324693.1754 | 88385.0149 | 97223.5164 | 206806.1454 | 0 | 556315.0493 | 680500.4915 | 741293.3433 | 805215.6536 | 874713.633 | 950279.5234 | 1032449.5651 | 1121807.9781 | 1218991.3089 | 1324693.1754
Retention withheld | ETB | 15966117.4361 | 4542669.158 | 10359799.6273 | 1063648.6509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention released | ETB | 15966117.4361 | 0 | 0 | 0 | 0 | 15966117.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Retention payable | ETB | 0 | 4542669.158 | 14902468.7852 | 15966117.4361 | 15966117.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
VAT receivable | ETB | 0 | 11588053.989 | 24682328.8356 | 3226889.5614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract liability | ETB | 0 | 45495619.8443 | 152763100.0013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract asset | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Deferred key money | ETB | 0 | 0 | 0 | 0 | 0 | 7689428.8675 | 5767071.6506 | 3844714.4337 | 1922357.2169 | 0 | 0 | 0 | 0 | 0 | 0
Net working capital (assets − liabilities) | ETB | 3437302.549 | -38538620.0281 | -143080463.4673 | -12946034.0201 | -15966117.4361 | -6697324.6791 | -4209272.5794 | -1807429.0096 | 273292.1984 | 2366220.6414 | 2549929.4929 | 2747776.1725 | 2960835.8186 | 3190263.9915 | 3437302.549

## 40_PL
40 · Profit & loss | [15 empty] | ◂ Start
የትርፍና ኪሳራ መግለጫ | [15 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Period |  | Total | C1 | C2 | C3 | C4 | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | O9 | O10
Period end (Gregorian) |  |  | 2027-12-31 | 2028-12-31 | 2029-06-30 | 2029-06-30 | 2030-06-30 | 2031-06-30 | 2032-06-30 | 2033-06-30 | 2034-06-30 | 2035-06-30 | 2036-06-30 | 2037-06-30 | 2038-06-30 | 2039-06-30
Ethiopian calendar year |  |  | EC 2020 | EC 2021 | EC 2021 | EC 2021 | EC 2022 | EC 2023 | EC 2024 | EC 2025 | EC 2026 | EC 2027 | EC 2028 | EC 2029 | EC 2030 | EC 2031
Revenue (IFRS 15 / IFRS 16) | ገቢ
Sales of units (IFRS 15) | ETB '000 | 498363811.7968 | 0 | 0 | 327437856.5968 | 0 | 98611128 | 72314827.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rental income (IFRS 16) | ETB '000 | 413932675.7671 | 0 | 0 | 0 | 0 | 19223572.1687 | 27788412.9381 | 34495960.8886 | 37255637.7597 | 40236088.7805 | 43454975.8829 | 46931373.9536 | 50685883.8698 | 54740754.5794 | 59120014.9458
Key money released | ETB '000 | 9611786.0844 | 0 | 0 | 0 | 0 | 1922357.2169 | 1922357.2169 | 1922357.2169 | 1922357.2169 | 1922357.2169 | 0 | 0 | 0 | 0 | 0
Service charge recoveries | ETB '000 | 37253940.819 | 0 | 0 | 0 | 0 | 1730121.4952 | 2500957.1644 | 3104636.48 | 3353007.3984 | 3621247.9902 | 3910947.8295 | 4223823.6558 | 4561729.5483 | 4926667.9121 | 5320801.3451
Other income | ETB '000 | 8691937.4795 | 0 | 0 | 0 | 0 | 600000 | 648000 | 699840 | 755827.2 | 816293.376 | 881596.8461 | 952124.5938 | 1028294.5613 | 1110558.1262 | 1199402.7763
Total revenue | ETB '000 | 967854151.9469 | 0 | 0 | 327437856.5968 | 0 | 122087178.8808 | 105174554.5194 | 40222794.5855 | 43286829.575 | 46595987.3636 | 48247520.5585 | 52107322.2031 | 56275907.9794 | 60777980.6177 | 65640219.0672
Cost of sales – units (IAS 2) | ETB '000 | -414509031.4246 | 0 | 0 | -290156321.9972 | 0 | -74611625.6564 | -49741083.7709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales commission | ETB '000 | -9967276.2359 | 0 | 0 | -6548757.1319 | 0 | -1972222.56 | -1446296.544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gross profit | ETB '000 | 543377844.2864 | 0 | 0 | 30732777.4677 | 0 | 45503330.6644 | 53987174.2044 | 40222794.5855 | 43286829.575 | 46595987.3636 | 48247520.5585 | 52107322.2031 | 56275907.9794 | 60777980.6177 | 65640219.0672
Operating expenses | የሥራ ማስኬጃ ወጪ
Property operating costs | ETB '000 | -62089901.3651 | 0 | 0 | 0 | 0 | -2883535.8253 | -4168261.9407 | -5174394.1333 | -5588345.664 | -6035413.3171 | -6518246.3824 | -7039706.093 | -7602882.5805 | -8211113.1869 | -8868002.2419
Management fee | ETB '000 | -12417980.273 | 0 | 0 | 0 | 0 | -576707.1651 | -833652.3881 | -1034878.8267 | -1117669.1328 | -1207082.6634 | -1303649.2765 | -1407941.2186 | -1520576.5161 | -1642222.6374 | -1773600.4484
Insurance | ETB '000 | -2397514.5136 | 0 | 0 | 0 | 0 | -150432.9949 | -165476.2944 | -182023.9238 | -200226.3162 | -220248.9478 | -242273.8426 | -266501.2269 | -293151.3496 | -322466.4845 | -354713.133
Property tax | ETB '000 | -2349156.262 | 0 | 0 | 0 | 0 | -147398.7373 | -162138.611 | -178352.4721 | -196187.7193 | -215806.4913 | -237387.1404 | -261125.8544 | -287238.4399 | -315962.2839 | -347558.5123
Maintenance | ETB '000 | -7991715.0454 | 0 | 0 | 0 | 0 | -501443.3163 | -551587.6479 | -606746.4127 | -667421.054 | -734163.1594 | -807579.4754 | -888337.4229 | -977171.1652 | -1074888.2817 | -1182377.1099
Marketing | ETB '000 | -4983638.118 | -1075351.0145 | -1182886.116 | -1016141.4355 | 0 | -986111.28 | -723148.272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Owner overheads | ETB '000 | -24270632.9348 | 0 | 0 | 0 | 0 | -1522870.4475 | -1675157.4923 | -1842673.2415 | -2026940.5657 | -2229634.6222 | -2452598.0845 | -2697857.8929 | -2967643.6822 | -3264408.0504 | -3590848.8555
Pre-opening & launch marketing | ETB '000 | -1500000 | 0 | 0 | -1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bad debts | ETB '000 | -8278653.5153 | 0 | 0 | 0 | 0 | -384471.4434 | -555768.2588 | -689919.2178 | -745112.7552 | -804721.7756 | -869099.5177 | -938627.4791 | -1013717.6774 | -1094815.0916 | -1182400.2989
Total operating expenses | ETB '000 | -126279192.0272 | -1075351.0145 | -1182886.116 | -2516141.4355 | 0 | -7152971.2098 | -8835190.9053 | -9708988.2279 | -10541903.2072 | -11447070.9769 | -12430833.7194 | -13500097.1878 | -14662381.4108 | -15925876.0164 | -17299500.5997
EBITDA | ETB '000 | 417098652.2592 | -1075351.0145 | -1182886.116 | 28216636.0322 | 0 | 38350359.4546 | 45151983.2991 | 30513806.3575 | 32744926.3678 | 35148916.3867 | 35816686.839 | 38607225.0153 | 41613526.5686 | 44852104.6013 | 48340718.4674
Depreciation – investment property | ETB '000 | -29042776.8838 | 0 | 0 | 0 | 0 | -2967915.5063 | -2967915.5063 | -2967915.5063 | -2967915.5063 | -2967915.5063 | -2967915.5063 | -2967915.5063 | -2755789.4465 | -2755789.4465 | -2755789.4465
Depreciation – owner-occupied PPE | ETB '000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating profit (EBIT) | ETB '000 | 388055875.3754 | -1075351.0145 | -1182886.116 | 28216636.0322 | 0 | 35382443.9482 | 42184067.7928 | 27545890.8512 | 29777010.8614 | 32181000.8804 | 32848771.3327 | 35639309.509 | 38857737.1221 | 42096315.1548 | 45584929.0209
Finance cost – bank loan (post-completion) | ETB '000 | -38525021.0391 | 0 | 0 | 0 | 0 | -14502034.5564 | -7925287.3584 | -3206193.5137 | -2960572.0793 | -2675982.7025 | -2346243.1028 | -1964190.1788 | -1521524.3999 | -1008629.5114 | -414363.6359
Finance cost – land lease | ETB '000 | -92610000 | 0 | -9450000 | -9135000 | 0 | -8820000 | -8505000 | -8190000 | -7875000 | -7560000 | -7245000 | -6930000 | -6615000 | -6300000 | -5985000
Profit before tax | ETB '000 | 256920854.3363 | -1075351.0145 | -10632886.116 | 19081636.0322 | 0 | 12060409.3919 | 25753780.4344 | 16149697.3375 | 18941438.7821 | 21945018.178 | 23257528.2299 | 26745119.3302 | 30721212.7222 | 34787685.6435 | 39185565.385
Current income tax | ETB '000 | -67587548.2929 | 0 | 0 | -2212019.6705 | 0 | -1751404.0672 | -6197851.7675 | -3587375.9485 | -4641497.6699 | -5715850.9191 | -6248227.4791 | -7405403.6446 | -8623312.9127 | -9914230.0438 | -11290374.17
Deferred tax | ETB '000 | -9488708.008 | 322605.3044 | 3189865.8348 | -3512471.1391 | 0 | -1866718.7504 | -1528282.3628 | -1257533.2528 | -1040933.9647 | -867654.5343 | -729030.9899 | -618132.1544 | -593050.904 | -522075.6493 | -465295.4455
Undistributed profits tax | ETB '000 | -8526890.0155 | 0 | 0 | -605693.9361 | 0 | -382824.4509 | -817482.768 | -512627.6243 | -601243.7609 | -696584.1092 | -738246.1228 | -848950.0885 | -975160.2129 | -1104239.1863 | -1243837.7557
PROFIT AFTER TAX | ETB '000 | 171317708.0199 | -752745.7102 | -7443020.2812 | 12751451.2864 | 0 | 8059462.1234 | 17210163.5361 | 10792160.5119 | 12657763.3866 | 14664928.6153 | 15542023.6381 | 17872633.4426 | 20529688.6927 | 23247140.7641 | 26186058.0138
attributable to non-controlling interest | ETB '000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
attributable to owners | ETB '000 | 171317708.0199 | -752745.7102 | -7443020.2812 | 12751451.2864 | 0 | 8059462.1234 | 17210163.5361 | 10792160.5119 | 12657763.3866 | 14664928.6153 | 15542023.6381 | 17872633.4426 | 20529688.6927 | 23247140.7641 | 26186058.0138
Appropriations | የትርፍ ድልድል
Transfer to legal reserve (Commercial Code) | ETB '000 | 1040545.6705 | 0 | 0 | 637572.5643 | 0 | 402973.1062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legal reserve balance | ETB '000 | 1040545.6705 | 0 | 0 | 637572.5643 | 637572.5643 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705
Dividends paid (incl. special) | ETB '000 | 161626911.8943 | 0 | 0 | 0 | 0 | 8170778.5693 | 20613986.7148 | 10792160.5119 | 12657763.3866 | 14664928.6153 | 15542023.6381 | 17872633.4426 | 17629802.5422 | 19469816.9632 | 24213017.5101
Retained earnings (total, before NCI split) | ETB '000 | 8650250.4551 | -752745.7102 | -8195765.9913 | 3918112.7308 | 3918112.7308 | 3403823.1787 | 0 | 0 | 0 | 0 | 0 | 0 | 2899886.1504 | 6677209.9513 | 8650250.4551
EBITDA margin | % |  | 0% | 0% | 8.617% | 0% | 31.41% | 42.93% | 75.86% | 75.65% | 75.43% | 74.24% | 74.09% | 73.95% | 73.8% | 73.64%

## 41_BS
41 · Balance sheet | [15 empty] | ◂ Start
የሀብትና ዕዳ መግለጫ | [15 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Period |  | Total | C1 | C2 | C3 | C4 | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | O9 | O10
Period end (Gregorian) |  |  | 2027-12-31 | 2028-12-31 | 2029-06-30 | 2029-06-30 | 2030-06-30 | 2031-06-30 | 2032-06-30 | 2033-06-30 | 2034-06-30 | 2035-06-30 | 2036-06-30 | 2037-06-30 | 2038-06-30 | 2039-06-30
Ethiopian calendar year |  |  | EC 2020 | EC 2021 | EC 2021 | EC 2021 | EC 2022 | EC 2023 | EC 2024 | EC 2025 | EC 2026 | EC 2027 | EC 2028 | EC 2029 | EC 2030 | EC 2031
Assets | ሀብት
Investment property (IAS 40, cost) | ETB '000 | 107276413.5103 | 66220409.442 | 126434853.6732 | 136319190.3941 | 136319190.3941 | 133351274.8878 | 130383359.3814 | 127415443.8751 | 124447528.3688 | 121479612.8624 | 118511697.3561 | 115543781.8498 | 112787992.4033 | 110032202.9568 | 107276413.5103
Property, plant & equipment (IAS 16) | ETB '000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Deferred tax asset | ETB '000 | 0 | 322605.3044 | 3512471.1391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-current assets | ETB '000 | 107276413.5103 | 66543014.7464 | 129947324.8123 | 136319190.3941 | 136319190.3941 | 133351274.8878 | 130383359.3814 | 127415443.8751 | 124447528.3688 | 121479612.8624 | 118511697.3561 | 115543781.8498 | 112787992.4033 | 110032202.9568 | 107276413.5103
Inventory – units for sale (IAS 2) | ETB '000 | 0 | 201357987.0816 | 384453491.7122 | 124352709.4274 | 124352709.4274 | 49741083.7709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade receivables | ETB '000 | 4761995.7244 | 0 | 0 | 0 | 0 | 1548419.2377 | 2238299.5627 | 2778578.7675 | 3000865.0689 | 3240934.2744 | 3500209.0163 | 3780225.7376 | 4082643.7966 | 4409255.3004 | 4761995.7244
VAT receivable | ETB '000 | 0 | 11588053.989 | 24682328.8356 | 3226889.5614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract asset (IFRS 15) | ETB '000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Restricted cash – DSRA | ETB '000 | 0 | 0 | 0 | 0 | 0 | 5511682.7479 | 2377193.1698 | 2377193.1698 | 2377193.1698 | 2377193.1698 | 2377193.1698 | 2377193.1698 | 2377193.1698 | 2377193.1698 | 0
Cash and cash equivalents | ETB '000 | 2000000 | 8031506.6432 | 39810292.5904 | 195824421.1577 | 196026790.967 | 2000000 | 21836992.9399 | 14697074.3406 | 11474126.2014 | 7808057.7594 | 4987190.7408 | 2353075.6924 | 2000000 | 2000000 | 2000000
Current assets | ETB '000 | 6761995.7244 | 220977547.7138 | 448946113.1382 | 323404020.1464 | 320379500.3944 | 58801185.7566 | 26452485.6723 | 19852846.2778 | 16852184.44 | 13426185.2035 | 10864592.927 | 8510494.5999 | 8459836.9664 | 8786448.4702 | 6761995.7244
TOTAL ASSETS | ETB '000 | 114038409.2347 | 287520562.4601 | 578893437.9506 | 459723210.5405 | 456698690.7885 | 192152460.6443 | 156835845.0538 | 147268290.1529 | 141299712.8088 | 134905798.066 | 129376290.2831 | 124054276.4496 | 121247829.3697 | 118818651.4269 | 114038409.2347
Liabilities | ዕዳ
Bank loan | ETB '000 | 0 | 0 | 111347918.1833 | 132698394.6015 | 132698394.6015 | 53961400.6099 | 21937391.5925 | 20389198.7666 | 18595384.5064 | 16516980.8692 | 14108837.6324 | 11318641.4716 | 8085779.5319 | 4340022.7037 | 0
Land lease liability | ETB '000 | 81000000 | 135000000 | 130500000 | 126000000 | 126000000 | 121500000 | 117000000 | 112500000 | 108000000 | 103500000 | 99000000 | 94500000 | 90000000 | 85500000 | 81000000
Deferred tax liability | ETB '000 | 9488708.008 | 0 | 0 | 0 | 0 | 1866718.7504 | 3395001.1132 | 4652534.366 | 5693468.3307 | 6561122.8649 | 7290153.8548 | 7908286.0092 | 8501336.9132 | 9023412.5625 | 9488708.008
Deferred income – key money | ETB '000 | 0 | 0 | 0 | 0 | 0 | 7689428.8675 | 5767071.6506 | 3844714.4337 | 1922357.2169 | 0 | 0 | 0 | 0 | 0 | 0
Retention payable | ETB '000 | 0 | 4542669.158 | 14902468.7852 | 15966117.4361 | 15966117.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Trade payables | ETB '000 | 1324693.1754 | 88385.0149 | 97223.5164 | 206806.1454 | 0 | 556315.0493 | 680500.4915 | 741293.3433 | 805215.6536 | 874713.633 | 950279.5234 | 1032449.5651 | 1121807.9781 | 1218991.3089 | 1324693.1754
Contract liability – customer advances (IFRS 15) | ETB '000 | 0 | 45495619.8443 | 152763100.0013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Income tax payable | ETB '000 | 12534211.9257 | 0 | 0 | 2817713.6066 | 0 | 2134228.518 | 7015334.5355 | 4100003.5728 | 5242741.4308 | 6412435.0284 | 6986473.6019 | 8254353.7332 | 9598473.1256 | 11018469.2301 | 12534211.9257
TOTAL LIABILITIES | ETB '000 | 104347613.109 | 185126674.0171 | 409610710.4862 | 277689031.7897 | 274664512.0377 | 187708091.7951 | 155795299.3833 | 146227744.4824 | 140259167.1383 | 133865252.3955 | 128335744.6126 | 123013730.7791 | 117307397.5488 | 111100895.8051 | 104347613.109
Equity | የባለቤት ሀብት
Share capital / owner contributions | ETB '000 | 0 | 103146634.1531 | 177478493.4557 | 177478493.4557 | 177478493.4557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legal reserve | ETB '000 | 1040545.6705 | 0 | 0 | 637572.5643 | 637572.5643 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705
Retained earnings | ETB '000 | 8650250.4551 | -752745.7102 | -8195765.9913 | 3918112.7308 | 3918112.7308 | 3403823.1787 | 0 | 0 | 0 | 0 | 0 | 0 | 2899886.1504 | 6677209.9513 | 8650250.4551
Equity attributable to owners | ETB '000 | 9690796.1256 | 102393888.443 | 169282727.4644 | 182034178.7508 | 182034178.7508 | 4444368.8492 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 3940431.8209 | 7717755.6218 | 9690796.1256
Non-controlling interest (in-kind land partner) | ETB '000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL EQUITY | ETB '000 | 9690796.1256 | 102393888.443 | 169282727.4644 | 182034178.7508 | 182034178.7508 | 4444368.8492 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 1040545.6705 | 3940431.8209 | 7717755.6218 | 9690796.1256
TOTAL LIABILITIES AND EQUITY | ETB '000 | 114038409.2347 | 287520562.4601 | 578893437.9506 | 459723210.5405 | 456698690.7885 | 192152460.6443 | 156835845.0538 | 147268290.1529 | 141299712.8088 | 134905798.066 | 129376290.2831 | 124054276.4496 | 121247829.3697 | 118818651.4269 | 114038409.2347
Balance check (assets − liabilities − equity) | ETB '000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NCI share (land in-kind ÷ total equity) | % | 0%

## 42_CF
42 · Cash flow statement (IAS 7, indirect) | [15 empty] | ◂ Start
የጥሬ ገንዘብ ፍሰት መግለጫ | [15 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Period |  | Total | C1 | C2 | C3 | C4 | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | O9 | O10
Period end (Gregorian) |  |  | 2027-12-31 | 2028-12-31 | 2029-06-30 | 2029-06-30 | 2030-06-30 | 2031-06-30 | 2032-06-30 | 2033-06-30 | 2034-06-30 | 2035-06-30 | 2036-06-30 | 2037-06-30 | 2038-06-30 | 2039-06-30
Ethiopian calendar year |  |  | EC 2020 | EC 2021 | EC 2021 | EC 2021 | EC 2022 | EC 2023 | EC 2024 | EC 2025 | EC 2026 | EC 2027 | EC 2028 | EC 2029 | EC 2030 | EC 2031
Memo: development cash paid (capex − IDC − non-cash land − Δretention) | ETB '000 | 398371375.4158 | 128035727.3656 | 225024381.4795 | 29345149.1346 | 0 | 15966117.4361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating activities | ከሥራ እንቅስቃሴ
Profit before tax | ETB '000 | 256920854.3363 | -1075351.0145 | -10632886.116 | 19081636.0322 | 0 | 12060409.3919 | 25753780.4344 | 16149697.3375 | 18941438.7821 | 21945018.178 | 23257528.2299 | 26745119.3302 | 30721212.7222 | 34787685.6435 | 39185565.385
Add: depreciation | ETB '000 | 29042776.8838 | 0 | 0 | 0 | 0 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2967915.5063 | 2755789.4465 | 2755789.4465 | 2755789.4465
Add: cost of sales released (non-cash) | ETB '000 | 414509031.4246 | 0 | 0 | 290156321.9972 | 0 | 74611625.6564 | 49741083.7709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add: finance costs (shown in financing) | ETB '000 | 131135021.0391 | 0 | 9450000 | 9135000 | 0 | 23322034.5564 | 16430287.3584 | 11396193.5137 | 10835572.0793 | 10235982.7025 | 9591243.1028 | 8894190.1788 | 8136524.3999 | 7308629.5114 | 6399363.6359
Increase in contract liability / (asset) | ETB '000 | 0 | 45495619.8443 | 107267480.157 | -152763100.0013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Increase in deferred key money | ETB '000 | 0 | 0 | 0 | 0 | 0 | 7689428.8675 | -1922357.2169 | -1922357.2169 | -1922357.2169 | -1922357.2169 | 0 | 0 | 0 | 0 | 0
(Increase) in receivables | ETB '000 | -4761995.7244 | 0 | 0 | 0 | 0 | -1548419.2377 | -689880.325 | -540279.2048 | -222286.3014 | -240069.2055 | -259274.7419 | -280016.7213 | -302418.059 | -326611.5037 | -352740.424
Increase in payables | ETB '000 | 1324693.1754 | 88385.0149 | 8838.5015 | 109582.629 | -206806.1454 | 556315.0493 | 124185.4422 | 60792.8518 | 63922.3103 | 69497.9794 | 75565.8905 | 82170.0417 | 89358.413 | 97183.3308 | 105701.8665
(Increase) in VAT receivable | ETB '000 | 0 | -11588053.989 | -13094274.8466 | 21455439.2742 | 3226889.5614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Income tax paid | ETB '000 | -63580226.3828 | 0 | 0 | 0 | -2817713.6066 | 0 | -2134228.518 | -7015334.5355 | -4100003.5728 | -5242741.4308 | -6412435.0284 | -6986473.6019 | -8254353.7332 | -9598473.1256 | -11018469.2301
Development costs paid – units for sale (IAS 2) | ETB '000 | -299782266.8303 | -96349393.9414 | -169335256.8356 | -22082799.7967 | 0 | -12014816.2565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net cash from operating activities | ETB '000 | 464807887.9217 | -63428794.0858 | -76336099.1397 | 165092080.1347 | 202369.8094 | 107644493.5336 | 90270786.4524 | 21096628.2522 | 26564201.587 | 27813246.513 | 29220542.9592 | 31422904.7338 | 33146113.1894 | 35024203.3028 | 37075210.6799
Investing activities | ከኢንቨስትመንት
Development costs paid – retained property (IAS 40 / 16) | ETB '000 | -98589108.5856 | -31686333.4242 | -55689124.6439 | -7262349.3379 | 0 | -3951301.1796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net cash from investing activities | ETB '000 | -98589108.5856 | -31686333.4242 | -55689124.6439 | -7262349.3379 | 0 | -3951301.1796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Financing activities | ከፋይናንስ
Equity injected (incl. top-up) | ETB '000 | 177478493.4557 | 103146634.1531 | 74331859.3026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan drawdowns | ETB '000 | 115241548.1987 | 0 | 103422150.4283 | 11819397.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Loan principal repaid (incl. sweep) | ETB '000 | -132698394.6015 | 0 | 0 | 0 | 0 | -78736993.9916 | -32024009.0174 | -1548192.8259 | -1793814.2602 | -2078403.6371 | -2408143.2368 | -2790196.1608 | -3232861.9397 | -3745756.8282 | -4340022.7037
Loan interest paid | ETB '000 | -38525021.0391 | 0 | 0 | 0 | 0 | -14502034.5564 | -7925287.3584 | -3206193.5137 | -2960572.0793 | -2675982.7025 | -2346243.1028 | -1964190.1788 | -1521524.3999 | -1008629.5114 | -414363.6359
Land lease instalments | ETB '000 | -54000000 | 0 | -4500000 | -4500000 | 0 | -4500000 | -4500000 | -4500000 | -4500000 | -4500000 | -4500000 | -4500000 | -4500000 | -4500000 | -4500000
Land lease interest | ETB '000 | -92610000 | 0 | -9450000 | -9135000 | 0 | -8820000 | -8505000 | -8190000 | -7875000 | -7560000 | -7245000 | -6930000 | -6615000 | -6300000 | -5985000
(Funding) / release of DSRA | ETB '000 | 0 | 0 | 0 | 0 | 0 | -5511682.7479 | 3134489.5781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2377193.1698
Net financing before dividends | ETB '000 | -25113373.9862 | 103146634.1531 | 163804009.7309 | -1815602.2295 | 0 | -112070711.2959 | -49819806.7977 | -17444386.3396 | -17129386.3396 | -16814386.3396 | -16499386.3396 | -16184386.3396 | -15869386.3396 | -15554386.3396 | -12862193.1698
Cash available before dividends | ETB '000 |  | 8031506.6432 | 39810292.5904 | 195824421.1577 | 196026790.967 | 187649272.0251 | 42450979.6547 | 25489234.8525 | 24131889.588 | 22472986.3747 | 20529214.379 | 20225709.135 | 19629802.5422 | 21469816.9632 | 26213017.5101
Dividend lock-up flag (DSCR below covenant) | flag | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dividends (positive) | ETB '000 | 83179524.8093 | 0 | 0 | 0 | 0 | 3828244.5086 | 8605081.7681 | 5396080.256 | 6328881.6933 | 7332464.3077 | 7771011.8191 | 8936316.7213 | 10264844.3463 | 11623570.3821 | 13093029.0069
Special dividend of surplus cash (positive) | ETB '000 | 78447387.085 | 0 | 0 | 0 | 0 | 4342534.0607 | 12008904.9468 | 5396080.256 | 6328881.6933 | 7332464.3077 | 7771011.8191 | 8936316.7213 | 7364958.1959 | 7846246.5811 | 11119988.5031
Dividends paid | ETB '000 | -161626911.8943 | 0 | 0 | 0 | 0 | -8170778.5693 | -20613986.7148 | -10792160.5119 | -12657763.3866 | -14664928.6153 | -15542023.6381 | -17872633.4426 | -17629802.5422 | -19469816.9632 | -24213017.5101
Return of surplus capital (positive) | ETB '000 | 177478493.4557 | 0 | 0 | 0 | 0 | 177478493.4557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capital returned to shareholders | ETB '000 | -177478493.4557 | 0 | 0 | 0 | 0 | -177478493.4557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net cash from financing activities | ETB '000 | -364218779.3361 | 103146634.1531 | 163804009.7309 | -1815602.2295 | 0 | -297719983.321 | -70433793.5126 | -28236546.8515 | -29787149.7262 | -31479314.9549 | -32041409.9777 | -34057019.7822 | -33499188.8818 | -35024203.3028 | -37075210.6799
Net change in cash | ETB '000 | 2000000 | 8031506.6432 | 31778785.9473 | 156014128.5672 | 202369.8094 | -194026790.967 | 19836992.9399 | -7139918.5993 | -3222948.1392 | -3666068.442 | -2820867.0185 | -2634115.0484 | -353075.6924 | 0 | 0
Opening cash | ETB '000 | 0 | 0 | 8031506.6432 | 39810292.5904 | 195824421.1577 | 196026790.967 | 2000000 | 21836992.9399 | 14697074.3406 | 11474126.2014 | 7808057.7594 | 4987190.7408 | 2353075.6924 | 2000000 | 2000000
CLOSING CASH | ETB '000 | 2000000 | 8031506.6432 | 39810292.5904 | 195824421.1577 | 196026790.967 | 2000000 | 21836992.9399 | 14697074.3406 | 11474126.2014 | 7808057.7594 | 4987190.7408 | 2353075.6924 | 2000000 | 2000000 | 2000000
Debt service reserve account (DSRA) | የዕዳ ክፍያ መጠባበቂያ
DSRA balance (restricted cash) | ETB '000 | 0 | 0 | 0 | 0 | 0 | 5511682.7479 | 2377193.1698 | 2377193.1698 | 2377193.1698 | 2377193.1698 | 2377193.1698 | 2377193.1698 | 2377193.1698 | 2377193.1698 | 0

## 43_Ratios
43 · Ratios & lender pack | [15 empty] | ◂ Start
የአፈጻጸም ምጣኔዎችና የባንክ መረጃ | [15 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Period |  | Total | C1 | C2 | C3 | C4 | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | O9 | O10
Period end (Gregorian) |  |  | 2027-12-31 | 2028-12-31 | 2029-06-30 | 2029-06-30 | 2030-06-30 | 2031-06-30 | 2032-06-30 | 2033-06-30 | 2034-06-30 | 2035-06-30 | 2036-06-30 | 2037-06-30 | 2038-06-30 | 2039-06-30
Ethiopian calendar year |  |  | EC 2020 | EC 2021 | EC 2021 | EC 2021 | EC 2022 | EC 2023 | EC 2024 | EC 2025 | EC 2026 | EC 2027 | EC 2028 | EC 2029 | EC 2030 | EC 2031
Cash flow available for debt service (CFADS) | ETB '000 | 219608779.3361 | -95115127.51 | -145975223.7836 | 144194730.7968 | 202369.8094 | 90373192.354 | 77265786.4524 | 8406628.2522 | 14189201.587 | 15753246.513 | 17475542.9592 | 19992904.7338 | 22031113.1894 | 24224203.3028 | 26590210.6799
Debt service | ETB '000 | 63560490.769 | 0 | 0 | 0 | 0 | 14502034.5564 | 11023365.4959 | 4754386.3396 | 4754386.3396 | 4754386.3396 | 4754386.3396 | 4754386.3396 | 4754386.3396 | 4754386.3396 | 4754386.3396
DSCR | x |  | 0 | 0 | 0 | 0 | 6.2318 | 7.0093 | 1.7682 | 2.9844 | 3.3134 | 3.6757 | 4.2051 | 4.6339 | 5.0951 | 5.5928
DSCR (numeric helper, 99 = no debt service) | x |  | 99 | 99 | 99 | 99 | 6.2318 | 7.0093 | 1.7682 | 2.9844 | 3.3134 | 3.6757 | 4.2051 | 4.6339 | 5.0951 | 5.5928
Covenant | x |  | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
PV of CFADS over remaining loan life | ETB '000 |  | 0 | 0 | 0 | 0 | 194213750.8021 | 132972621.0684 | 75652727.7763 | 78594008.6905 | 76193908.4071 | 71869748.1552 | 65174667.4193 | 54957962.7984 | 41170544.0288 | 23121922.3303
LLCR | x |  | 0 | 0 | 0 | 0 | 1.4636 | 2.4642 | 3.4486 | 3.8547 | 4.0975 | 4.3513 | 4.6194 | 4.8555 | 5.0917 | 5.3276
Interest cover (EBITDA ÷ finance cost) | x |  | 0 | 0 | 0 | 0 | 1.6444 | 2.7481 | 2.6775 | 3.022 | 3.4339 | 3.7343 | 4.3407 | 5.1144 | 6.1369 | 7.554
Gearing (loan ÷ (loan + equity)) | % | 95.47% | 0% | 39.68% | 42.16% | 42.16% | 92.39% | 95.47% | 95.14% | 94.7% | 94.07% | 93.13% | 91.58% | 67.23% | 35.99% | 0%
Net debt ÷ EBITDA | x |  |  |  | -2.2372 |  | 1.3549 | 0.0022236 | 0.18654 | 0.21748 | 0.24777 | 0.25468 | 0.23223 | 0.14625 | 0.052172 | -0.041373
Cash balance in operating years | ETB '000 |  | 0 | 0 | 0 | 0 | 2000000 | 21836992.9399 | 14697074.3406 | 11474126.2014 | 7808057.7594 | 4987190.7408 | 2353075.6924 | 2000000 | 2000000 | 2000000
Covenant breach flag | flag | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Below minimum cash flag (operating years) | flag | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary | ማጠቃለያ
Minimum DSCR | x | 1.7682
Average DSCR | x | 4.451
Years with debt service | no. | 10
LLCR at first operating year | x | 1.4636
Minimum ICR | x | 1.6444
Maximum gearing | % | 95.47%
Years below DSCR covenant | no. | 0
Minimum cash in operating years | ETB '000 | 2000000
Years below minimum cash | no. | 0

## 50_Returns
50 · Returns – NPV, IRR, MOIC, margins | [15 empty] | ◂ Start
ተመላሽ – NPV፣ IRR፣ ትርፋማነት | [15 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Period |  | Total | C1 | C2 | C3 | C4 | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | O9 | O10
Period end (Gregorian) |  |  | 2027-12-31 | 2028-12-31 | 2029-06-30 | 2029-06-30 | 2030-06-30 | 2031-06-30 | 2032-06-30 | 2033-06-30 | 2034-06-30 | 2035-06-30 | 2036-06-30 | 2037-06-30 | 2038-06-30 | 2039-06-30
Ethiopian calendar year |  |  | EC 2020 | EC 2021 | EC 2021 | EC 2021 | EC 2022 | EC 2023 | EC 2024 | EC 2025 | EC 2026 | EC 2027 | EC 2028 | EC 2029 | EC 2030 | EC 2031
Terminal value at O10 | የመጨረሻ ዋጋ
NOI in O10 | ETB | 51931567.3229
Stabilised NOI (O3) | ETB | 30434122.3822
Terminal value (gross) | ETB | 623178807.875
Terminal value net of exit costs | ETB | 610715231.7175
Equity exit value (owners' book equity + TV uplift) | ETB | 513129614.3328
Project cash flow (unlevered, after tax paid) | የፕሮጀክት የገንዘብ ፍሰት
Operating + investing cash flow | ETB '000 | 366218779.3361 | -95115127.51 | -132025223.7836 | 157829730.7968 | 202369.8094 | 103693192.354 | 90270786.4524 | 21096628.2522 | 26564201.587 | 27813246.513 | 29220542.9592 | 31422904.7338 | 33146113.1894 | 35024203.3028 | 37075210.6799
Add back: financing fees paid | ETB '000 | 7045718.334 | 5484085.4478 | 1159301.3266 | 402331.5595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Less: land lease payments | ETB '000 | -146610000 | 0 | -13950000 | -13635000 | 0 | -13320000 | -13005000 | -12690000 | -12375000 | -12060000 | -11745000 | -11430000 | -11115000 | -10800000 | -10485000
Terminal value | ETB '000 | 610715231.7175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610715231.7175
PROJECT CASH FLOW | ETB '000 | 837369729.3876 | -89631042.0622 | -144815922.457 | 144597062.3563 | 202369.8094 | 90373192.354 | 77265786.4524 | 8406628.2522 | 14189201.587 | 15753246.513 | 17475542.9592 | 19992904.7338 | 22031113.1894 | 24224203.3028 | 637305442.3973
Discounted @ project rate | ETB '000 | 112309020.4366 | -75958510.2222 | -103957389.0443 | 95620920.4979 | 133825.5919 | 50646689.8979 | 36695825.7654 | 3381990.1182 | 4837560.8713 | 4551520.9469 | 4278929.6609 | 4146688.5893 | 3872397.7538 | 3608369.5821 | 80450200.4274
Equity cash flow | የባለቤት የገንዘብ ፍሰት
Equity injected | ETB '000 | -177478493.4557 | -103146634.1531 | -74331859.3026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dividends + capital returned | ETB '000 | 339105405.35 | 0 | 0 | 0 | 0 | 185649272.0251 | 20613986.7148 | 10792160.5119 | 12657763.3866 | 14664928.6153 | 15542023.6381 | 17872633.4426 | 17629802.5422 | 19469816.9632 | 24213017.5101
Equity exit value | ETB '000 | 513129614.3328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 513129614.3328
EQUITY CASH FLOW | ETB '000 | 674756526.2271 | -103146634.1531 | -74331859.3026 | 0 | 0 | 185649272.0251 | 20613986.7148 | 10792160.5119 | 12657763.3866 | 14664928.6153 | 15542023.6381 | 17872633.4426 | 17629802.5422 | 19469816.9632 | 537342631.8429
Discounted @ cost of equity | ETB '000 | 31378305.8978 | -84546421.437 | -49913581.4076 | 0 | 0 | 92587454.5286 | 8426768.3402 | 3614190.3845 | 3474559.6554 | 3299612.3626 | 2866359.7931 | 2700320.1272 | 2183304.564 | 1976373.0016 | 44709365.9853
Cash flow date (period end) | date |  | 2027-12-31 | 2028-12-31 | 2029-06-30 | 2029-06-30 | 2030-06-30 | 2031-06-30 | 2032-06-30 | 2033-06-30 | 2034-06-30 | 2035-06-30 | 2036-06-30 | 2037-06-30 | 2038-06-30 | 2039-06-30
Return metrics | የተመላሽ መለኪያዎች
Project cash flow valid for IRR (has + and −) | flag | 1
Equity cash flow valid for IRR | flag | 1
Project NPV @ discount rate | ETB | 112309020.4366
Project IRR (XIRR, dated) | % | 34.59%
Equity NPV @ cost of equity | ETB | 31378305.8978
Equity IRR (XIRR, dated) | % | 27.4%
Memo: project IRR per period (IRR on columns) | % | 25.05%
Equity multiple (MOIC) | x | 4.8019
Project multiple | x | 4.5717
Sales revenue (nominal, net) | ETB | 498363811.7968
Value of retained property at stabilisation (NOI O3 ÷ exit cap) | ETB | 338156915.3576
Gross development value (GDV) | ETB | 836520727.1544
Profit on cost | % | 51.87%
Development margin (profit ÷ GDV) | % | 34.15%
Yield on cost (stabilised NOI ÷ retained cost) | % | 22.33%
GDV ÷ TDC | x | 1.5187
Total profit after tax (C1–O10) | ETB | 171317708.0199
Peak equity (committed + top-up) | ETB | 177478493.4557
DSCR test passed (or no debt service) | flag | 1
VERDICT |  | VIABLE
ውሳኔ |  | አዋጭ
IAS 36 – impairment test summary | የንብረት ዋጋ መቀነስ ፈተና
Years with impairment indicator | no. | 0
Lowest headroom (value in use − carrying amount) | ETB | 0

## 51_Payback
51 · Payback – simple and discounted | [15 empty] | ◂ Start
የመመለሻ ጊዜ | [15 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Period |  | Total | C1 | C2 | C3 | C4 | O1 | O2 | O3 | O4 | O5 | O6 | O7 | O8 | O9 | O10
Period end (Gregorian) |  |  | 2027-12-31 | 2028-12-31 | 2029-06-30 | 2029-06-30 | 2030-06-30 | 2031-06-30 | 2032-06-30 | 2033-06-30 | 2034-06-30 | 2035-06-30 | 2036-06-30 | 2037-06-30 | 2038-06-30 | 2039-06-30
Ethiopian calendar year |  |  | EC 2020 | EC 2021 | EC 2021 | EC 2021 | EC 2022 | EC 2023 | EC 2024 | EC 2025 | EC 2026 | EC 2027 | EC 2028 | EC 2029 | EC 2030 | EC 2031
Project – simple
Cash flow | ETB '000 | 837369729.3876 | -89631042.0622 | -144815922.457 | 144597062.3563 | 202369.8094 | 90373192.354 | 77265786.4524 | 8406628.2522 | 14189201.587 | 15753246.513 | 17475542.9592 | 19992904.7338 | 22031113.1894 | 24224203.3028 | 637305442.3973
Cumulative | ETB '000 | 837369729.3876 | -89631042.0622 | -234446964.5191 | -89849902.1628 | -89647532.3534 | 725660.0005 | 77991446.4529 | 86398074.7051 | 100587276.2921 | 116340522.8051 | 133816065.7643 | 153808970.498 | 175840083.6874 | 200064286.9903 | 837369729.3876
Crossing point (years from start) | years | 3.4906 | 0 | 0 | 0 | 0 | 3.4906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project – discounted
Cash flow | ETB '000 | 112309020.4366 | -75958510.2222 | -103957389.0443 | 95620920.4979 | 133825.5919 | 50646689.8979 | 36695825.7654 | 3381990.1182 | 4837560.8713 | 4551520.9469 | 4278929.6609 | 4146688.5893 | 3872397.7538 | 3608369.5821 | 80450200.4274
Cumulative | ETB '000 | 112309020.4366 | -75958510.2222 | -179915899.2665 | -84294978.7686 | -84161153.1767 | -33514463.2788 | 3181362.4866 | 6563352.6048 | 11400913.4761 | 15952434.423 | 20231364.0839 | 24378052.6732 | 28250450.427 | 31858820.0091 | 112309020.4366
Crossing point (years from start) | years | 4.4119 | 0 | 0 | 0 | 0 | 0 | 4.4119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equity – simple
Cash flow | ETB '000 | 674756526.2271 | -103146634.1531 | -74331859.3026 | 0 | 0 | 185649272.0251 | 20613986.7148 | 10792160.5119 | 12657763.3866 | 14664928.6153 | 15542023.6381 | 17872633.4426 | 17629802.5422 | 19469816.9632 | 537342631.8429
Cumulative | ETB '000 | 674756526.2271 | -103146634.1531 | -177478493.4557 | -177478493.4557 | -177478493.4557 | 8170778.5693 | 28784765.2842 | 39576925.7961 | 52234689.1827 | 66899617.798 | 82441641.4361 | 100314274.8787 | 117944077.421 | 137413894.3842 | 674756526.2271
Crossing point (years from start) | years | 3.4546 | 0 | 0 | 0 | 0 | 3.4546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Equity – discounted
Cash flow | ETB '000 | 31378305.8978 | -84546421.437 | -49913581.4076 | 0 | 0 | 92587454.5286 | 8426768.3402 | 3614190.3845 | 3474559.6554 | 3299612.3626 | 2866359.7931 | 2700320.1272 | 2183304.564 | 1976373.0016 | 44709365.9853
Cumulative | ETB '000 | 31378305.8978 | -84546421.437 | -134460002.8446 | -134460002.8446 | -134460002.8446 | -41872548.3159 | -33445779.9757 | -29831589.5913 | -26357029.9359 | -23057417.5733 | -20191057.7802 | -17490737.653 | -15307433.089 | -13331060.0874 | 31378305.8978
Crossing point (years from start) | years | 11.8023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.8023
Payback results (years from construction start; fractional-year method) | ውጤት
Project payback – simple | years | 3.4906 | 2027-12-31: 0 = not reached within the horizon
Project payback – discounted | years | 4.4119 | 2027-12-31: 0 = not reached within the horizon
Equity payback – simple | years | 3.4546 | 2027-12-31: 0 = not reached within the horizon
Equity payback – discounted | years | 11.8023 | 2027-12-31: 0 = not reached within the horizon

## 52_Sensitivity
52 · Sensitivity & break-even (LIVE) | [15 empty] | ◂ Start
የስጋት ትንተናና የሚዛን ነጥብ | [15 empty] | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
What-if dials – change one and every sheet updates (100% = as input). Put them back to 100% / 0 afterwards. | የማስተካከያ ሕዋሶች
Sale price | x | 100%
Construction cost | x | 100%
Rent and hotel rate | x | 100%
Occupancy | x | 100%
Interest rate | x | 100%
Operating costs | x | 100%
Extra construction delay (months) | months | 0
Dials changed from neutral? (1 = yes – results are NOT the base case) | flag | 0
Live outputs | ውጤቶች
Equity IRR |  | 27.4%
Project IRR |  | 34.59%
Project NPV | ETB | 112309020.4366
Profit on cost |  | 51.87%
Minimum DSCR |  | 1.7682
Peak debt | ETB | 132698394.6015
Total development cost | ETB | 550828221.8186
Verdict |  | VIABLE
Present values used by the tornado and break-evens (annual, @ project discount rate) | ረዳት ስሌቶች
Discount factor @ project rate | x |  | 0.84746 | 0.71786 | 0.66129 | 0.66129 | 0.56042 | 0.47493 | 0.4023 | 0.34093 | 0.28893 | 0.24485 | 0.20741 | 0.17577 | 0.14896 | 0.12623
Space rent less %-based costs | ETB | 331146140.6137 | 0 | 0 | 0 | 0 | 15378857.735 | 22230730.3504 | 27596768.7109 | 29804510.2078 | 32188871.0244 | 34763980.7063 | 37545099.1628 | 40548707.0959 | 43792603.6635 | 47296011.9566
Hotel rent less %-based costs | ETB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction cost driven by the cost dial | ETB | 367825657.0819 | 109594311.0758 | 234224879.7802 | 24006466.2259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating costs driven by the opex dial | ETB | 34659862.4938 | 0 | 0 | 0 | 0 | 2174746.7587 | 2392221.4346 | 2631443.5781 | 2894587.9359 | 3184046.7295 | 3502451.4024 | 3852696.5427 | 4237966.1969 | 4661762.8166 | 5127939.0983
Loan interest (paid + capitalised) | ETB | 55981867.4419 | 0 | 7925767.755 | 9531078.6478 | 0 | 14502034.5564 | 7925287.3584 | 3206193.5137 | 2960572.0793 | 2675982.7025 | 2346243.1028 | 1964190.1788 | 1521524.3999 | 1008629.5114 | 414363.6359
Operating inflows (NOI + sales collections) | ETB | 862717444.8881 | 45495619.8443 | 107267480.157 | 174674756.5956 | 0 | 115520832.1817 | 96815312.1615 | 30434122.3822 | 32849509.7166 | 35456193.7921 | 38269284.9235 | 41305082.9082 | 44581170.2508 | 48116512.6518 | 51931567.3229
PV of terminal value | ETB | 77093587.3558
PV of sales collections net of commission & marketing | ETB | 311057100.9835
PV of space rent (incl. its share of terminal value) | ETB | 155872390.1287
PV of hotel rent (incl. its share of terminal value) | ETB | 0
PV of construction cost (cost dial) | ETB | 276892224.2811
PV of operating costs (opex dial, incl. terminal value effect) | ETB | 16676185.434
PV of loan interest | ETB | 28407784.4076
PV of operating inflows incl. terminal value | ETB | 492067073.2334
Value lost from a 6-month delay (first-order) | ETB | 49103418.2119
Tornado – first-order change in project value for ±20% (delay: +6 months), ETB million | የቶርኔዶ ሰንጠረዥ
Pre-tax estimate from the present values above. For the exact effect of any driver, change the matching dial at the top.
Driver |  |  | Adverse case | Favourable case | Swing | Rank key
Sale price |  |  | -62.2114 | 62.2114 | 124.4228 | 124.4228
Rent – spaces |  |  | -31.1745 | 31.1745 | 62.349 | 62.349
Hotel trading (rate × occupancy) |  |  | 0 | 0 | 0 | 3e-06
Construction cost |  |  | -55.3784 | 55.3784 | 110.7569 | 110.7569
Operating costs |  |  | -3.3352 | 3.3352 | 6.6705 | 6.6705
Interest rate (value to owner) |  |  | -5.6816 | 5.6816 | 11.3631 | 11.3631
Construction delay +6 months |  |  | -49.1034 | 0 | 49.1034 | 49.1034
Sorted (largest swing first) – chart source
Sale price |  |  | -62.2114 | 62.2114
Construction cost |  |  | -55.3784 | 55.3784
Rent – spaces |  |  | -31.1745 | 31.1745
Construction delay +6 months |  |  | -49.1034 | 0
Interest rate (value to owner) |  |  | -5.6816 | 5.6816
Operating costs |  |  | -3.3352 | 3.3352
Hotel trading (rate × occupancy) |  |  | 0 | 0
Break-even analysis (live, closed-form – each holds the other drivers at their inputs) | የሚዛን ነጥብ ትንተና
Break-even |  |  | Value | Unit | Current | Headroom
Sale price at which project NPV = 0 |  |  | 79868.0049 | ETB/m² | 125000 | 36.11%
Sale price at which profit on cost = 0 |  |  | 53342.383 | ETB/m² | 125000 | 57.33%
Rent level at which project NPV = 0 (% of today's input) |  |  | 27.95% | % of rent | 100% | 72.05%
Stabilised occupancy at which min DSCR = covenant |  |  | 84.58% | % occ. | 92% | 8.066%
Cost overrun before equity IRR falls below the hurdle |  |  | 17.69% | overrun | 0% | 17.69%
Interest rate at which min DSCR = covenant |  |  | 23.01% | % p.a. | 15% | 53.4%
Delay before equity IRR falls below the hurdle |  |  | 19.5635 | months | 0 | 1.6303
Exit cap rate at which project NPV = 0 |  |  | 0% | % yield | 9% | -100%
0 = not applicable for this project (e.g. no sales, no debt service). Headroom = how far the input can move before the break-even is reached.
Closed-form helpers for break-evens | ረዳት ስሌቶች
Discount factor @ hurdle | x |  | 0.83333 | 0.6941 | 0.6341 | 0.6341 | 0.52841 | 0.44034 | 0.36677 | 0.30564 | 0.2547 | 0.21225 | 0.17679 | 0.14732 | 0.12277 | 0.10231
Equity NPV @ hurdle | ETB | 47610416.3584
PV @ hurdle of construction cost (cost dial) | ETB | 269125946.8848
Equity inflows (positive) | ETB | 852235019.6828 | 0 | 0 | 0 | 0 | 185649272.0251 | 20613986.7148 | 10792160.5119 | 12657763.3866 | 14664928.6153 | 15542023.6381 | 17872633.4426 | 17629802.5422 | 19469816.9632 | 537342631.8429
PV @ hurdle of equity inflows | ETB | 185159513.5586
PV @ hurdle of equity outflows | ETB | 137549097.2002
Rent-driven cash (spaces + hotel, after %-based costs) | ETB | 331146140.6137 | 0 | 0 | 0 | 0 | 15378857.735 | 22230730.3504 | 27596768.7109 | 29804510.2078 | 32188871.0244 | 34763980.7063 | 37545099.1628 | 40548707.0959 | 43792603.6635 | 47296011.9566
Occupancy multiplier needed for DSCR = covenant | x | 0.91934 | 0 | 0 | 0 | 0 | -3.6506 | -1.831 | 0.91934 | 0.7313 | 0.70261 | 0.6751 | 0.63212 | 0.6091 | 0.58798 | 0.56847
Binding occupancy multiplier | x | 0.91934
Rate at which DSCR = covenant (by year) | % | 23.01% | 9900% | 9900% | 9900% | 9900% | 71.9% | 106.6% | 23.01% | 46.21% | 56.28% | 70.55% | 96.14% | 135.2% | 221.4% | 583.3%
Binding break-even rate | % | 23.01%

## 60_Checks
60 · Checks |  |  |  | ◂ Start
ማረጋገጫዎች |  |  |  | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
Model integrity checks – all must PASS; warnings are advisory | የሞዴል ማረጋገጫዎች
Check | Type | Value | Tolerance | Status
C01 Balance sheet balances every year | Error | 0 | 1 | PASS
C02 Cash-flow closing cash = balance-sheet cash | Error | 0 | 1 | PASS
C03 Sources = uses (monthly funding waterfall) | Error | 0 | 1 | PASS
C04 TDC = monthly capex accrual; cost categories sum to TDC | Error | 0 | 1 | PASS
C05 Capex fully allocated across IAS 2 / 40 / 16 | Error | 0 | 1 | PASS
C06 Loan fully repaid within tenor | Error | 0 | 1 | PASS
C07 Σ principal repaid = debt drawn + capitalised interest | Error | 0 | 1 | PASS
C08 Inventory fully released by final sale (end O10) | Error | 0 | 1 | PASS
C09 Contract liabilities / assets unwind to zero (end O10) | Error | 0 | 1 | PASS
C10 Land not depreciated (cum. depreciation ≤ depreciable base) | Error | 0 | 1 | PASS
C11 Net area of the spaces ≤ gross floor area | Error | 0 | 0.5 | PASS
C12 Tax losses never negative | Error | 0 | 0.5 | PASS
C13 Track, project type, data set and scenario switches valid | Error | 0 | 0.5 | PASS
C14 No formula errors anywhere (REF, DIV/0, N/A, VALUE – ISERROR scan) | Error | 0 | 0.5 | PASS
C15 Payment plan and presales ≤ 100% | Error | 0 | 0.0001 | PASS
C16 VAT account rolls forward | Error | 0 | 1 | PASS
C17 What-if dials at neutral (100% / 0) – otherwise results are not the base case | Warning | 0 | 0.5 | PASS
C18 DSCR ≥ covenant in every repayment year | Warning | 0 | 0.5 | PASS
C19 Cash never below minimum in operating years | Warning | 0 | 0.5 | PASS
C20 Funding gap = 0 (equity + debt + presales cover the cost) | Warning | 0 | 1 | PASS
C21 FAR within permitted limit | Warning | 0 | 0.5 | PASS
C22 Net-to-gross ratio plausible (50%–95%) | Warning | 0 | 0.5 | PASS
C23 Hotel inputs consistent (hotel space ⇔ keys and room rate) | Warning | 0 | 0.5 | PASS
C24 At least one space entered on sheet 13 | Warning | 0 | 0.5 | PASS
C25 No IAS 36 impairment indicator | Warning | 0 | 0.5 | PASS
Checks passed |  | 25
Errors (FAIL) |  | 0
Warnings |  | 0
Total checks |  | 25
Status |  | ALL CHECKS PASS
How to fix common failures: C01/C02 – never type over black formula cells; C06 – increase tenor or reduce grace; C11 – net areas on sheet 13 exceed the floors on Inputs block 2; C15 – payment plan or presales above 100%; C17 – set the dials on sheet 52 back to 100% / 0.

## 61_Glossary
61 · Glossary (English – Amharic) |  | ◂ Start
መዝገበ ቃላት (እንግሊዝኛ – አማርኛ) |  | Dashboard ▸
SAMPLE 1 — B+G+8 mixed-use building, Addis Ababa ¦ Type: Mixed ¦ Scenario: Base
English term | የአማርኛ ቃል | ትርጉም (Meaning)
Assumption | ግምት (መነሻ መረጃ) | ሞዴሉ ለስሌት የሚጠቀምበት፣ እርስዎ የሚያስገቡት ቁጥር።
Input cell | የግብዓት ሕዋስ | በሰማያዊ ፊደልና ቀላል ቢጫ ጀርባ የተለየ፤ ሊቀየር የሚችል ሕዋስ።
Formula | ቀመር | በራሱ የሚሰላ ሕዋስ (ጥቁር ፊደል)፤ በእጅ አይጻፍበትም።
Cross-sheet link | የሌላ ገጽ ማገናኛ | ከሌላ ገጽ ቁጥር የሚያመጣ ቀመር (አረንጓዴ ፊደል)።
Scenario | ሁኔታ (ሴናሪዮ) | መሠረታዊ፣ ብሩህ፣ አስቸጋሪና የባንክ ሁኔታዎች — የተለያዩ ግምቶች ስብስብ።
Flex cell | የማስተካከያ ሕዋስ | አንድን ግምት በመቶኛ ከፍ ወይም ዝቅ አድርጎ ውጤቱን ለማየት።
Sensitivity analysis | የተጽዕኖ ትንተና | አንድ ግምት ሲቀየር ውጤቱ ምን ያህል እንደሚለወጥ ማሳያ።
Data Table | የመረጃ ሰንጠረዥ (Data Table) | የExcel መሣሪያ፤ ለብዙ ዋጋዎች ውጤቱን በአንድ ጊዜ ያሰላል።
Tornado chart | የቶርኔዶ ሰንጠረዥ | የትኛው ግምት ውጤቱን በብዛት እንደሚያናውጥ በቅደም ተከተል የሚያሳይ።
Break-even | የሚዛን ነጥብ | ትርፍም ኪሳራም የማይኖርበት ወይም ገደቡ የሚደረስበት ዋጋ።
Capex | የካፒታል ወጪ | ሕንፃውን ለመገንባት የሚወጣ ጠቅላላ ወጪ።
Hard cost | ቀጥተኛ የግንባታ ወጪ | ለግንባታ ሥራ፣ ለዕቃና ለሠራተኛ የሚከፈል ወጪ።
Soft cost | ቀጥተኛ ያልሆነ ወጪ | ዲዛይን፣ ቁጥጥር፣ ፈቃድና መሰል ክፍያዎች።
Contingency | ያልተጠበቀ ወጪ መጠባበቂያ | ላልታሰቡ ችግሮች የሚያዝ ተጨማሪ በጀት።
Escalation | የዋጋ ጭማሪ | በጊዜ ሂደት የግንባታ ዕቃና የሠራተኛ ዋጋ መጨመር።
Bill of Quantities (BOQ) | የሥራ መጠን ዝርዝር (BOQ) | የእያንዳንዱ ሥራ መጠንና ዋጋ ዝርዝር ሰነድ።
Elemental cost plan | በክፍል የተከፋፈለ የወጪ ዕቅድ | ወጪን በመሠረት፣ በፍሬም፣ በማጠናቀቂያ ወዘተ መከፋፈል።
Cost index | የግንባታ ዋጋ ኢንዴክስ | የግንባታ ዋጋ ለውጥን በጊዜ የሚከታተል ቁጥር (ለምሳሌ የራፋ ኢንዴክስ)።
S-curve | የወጪ ስርጭት ኩርባ (S-ኩርባ) | ወጪ በመጀመሪያና በመጨረሻ ዝግ፣ በመሃል ፈጣን መሆኑን የሚያሳይ።
Gross floor area (GFA) | ጠቅላላ የወለል ስፋት | የሁሉም ፎቆች ስፋት ድምር (ግድግዳና የጋራ ቦታን ጨምሮ)።
Net area | የተጣራ ስፋት | ሊሸጥ ወይም ሊከራይ የሚችል ስፋት ብቻ።
Net-to-gross efficiency | የተጣራ-ለጠቅላላ ጥምርታ | የተጣራ ስፋት ከጠቅላላ ስፋት ያለው ድርሻ።
Floor-area ratio (FAR) | የወለል ስፋት ጥምርታ | ከመሬት በላይ ያለ ጠቅላላ ስፋት ለቦታው ስፋት ሲካፈል።
Presale | ቅድመ-ሽያጭ | ግንባታው ሳያልቅ ቤት ወይም ሱቅ መሸጥ።
Payment plan | የክፍያ ዕቅድ | ገዢው ቅድመ ክፍያ፣ በሂደት ክፍያና በርክክብ ቀሪውን የሚከፍልበት ቅደም ተከተል።
Down payment | ቅድመ ክፍያ | ውል ሲፈረም የሚከፈል የመጀመሪያ ገንዘብ።
Handover | ርክክብ | ግንባታው ሲያልቅ ቤቱን ለገዢው ማስረከብ።
Sales absorption | የሽያጭ ፍጥነት | ከግንባታ በኋላ በየዓመቱ የሚሸጠው ድርሻ።
Occupancy | የተያዘ መጠን | ከሚከራየው ቦታ በተከራይ የተያዘው ድርሻ።
Key money | የቁልፍ ገንዘብ | ተከራይ ሲገባ በቅድሚያ የሚከፍለው ተጨማሪ ገንዘብ።
Service charge | የአገልግሎት ክፍያ | ተከራዮች ለጋራ አገልግሎቶች የሚከፍሉት።
Bad debt | የማይሰበሰብ ዕዳ | ተከራዮች ሳይከፍሉ የሚቀር ኪራይ።
Operating costs (opex) | የሥራ ማስኬጃ ወጪ | ሕንፃውን ለማስተዳደር በየዓመቱ የሚወጣ ወጪ።
Net operating income (NOI) | የተጣራ የሥራ ገቢ | የኪራይ ገቢ ከሥራ ማስኬጃ ወጪ በኋላ።
Gross development value (GDV) | ጠቅላላ የልማት ዋጋ | የሚሸጡ ቤቶችና የሚቀሩ ንብረቶች ጠቅላላ ዋጋ።
Total development cost (TDC) | ጠቅላላ የልማት ወጪ | መሬት፣ ግንባታ፣ ክፍያዎችና የብድር ወጪን ጨምሮ ጠቅላላ ወጪ።
Equity | የባለቤት ካፒታል | ባለቤቱ (ወይም ባለአክሲዮኖች) ከራሳቸው የሚያዋጡት ገንዘብ።
Debt | ብድር | ከባንክ የሚገኝና በወለድ የሚመለስ ገንዘብ።
Funding waterfall | የገንዘብ ምንጭ ቅደም ተከተል | ወጪ በምን ቅደም ተከተል እንደሚሸፈን፡ ቅድመ-ሽያጭ → ካፒታል → ብድር።
Funding gap | የገንዘብ ክፍተት | ያሉ ምንጮች ሁሉ ተጠቅመው ያልተሸፈነ ወጪ።
Interest rate | የወለድ መጠን | ለብድር በዓመት የሚከፈል መቶኛ።
Interest during construction (IDC) | በግንባታ ጊዜ የሚታሰብ ወለድ | በግንባታ ወቅት የሚጠራቀምና ወደ ወጪው የሚጨመር ወለድ።
Capitalised interest | ወደ ዋና ገንዘብ የተጨመረ ወለድ | ያልተከፈለና በብድር ቀሪ ላይ የተደመረ ወለድ።
Grace period | የእፎይታ ጊዜ | ዋና ገንዘብ መክፈል ሳይጀመር ወለድ ብቻ የሚከፈልበት ጊዜ።
Tenor | የብድር ዘመን | ብድሩ ተከፍሎ የሚያልቅበት ጠቅላላ ጊዜ።
Annuity | እኩል ክፍያ (አንዩቲ) | በየጊዜው እኩል የሆነ (ወለድ + ዋና) ክፍያ።
Equal principal | እኩል ዋና ገንዘብ | ዋና ገንዘብ በእኩል ክፍሎች፤ ወለዱ በየጊዜው ይቀንሳል።
Balloon payment | የመጨረሻ ትልቅ ክፍያ | በብድሩ መጨረሻ የሚከፈል ትልቅ ቀሪ መጠን።
Amortization schedule | የብድር ክፍያ ሰንጠረዥ | እያንዳንዱ ክፍያ ወለድና ዋና ገንዘብ እንደሆነ የሚያሳይ ሰንጠረዥ።
Principal | ዋና ገንዘብ | የተበደሩት መጠን (ወለድን ሳይጨምር)።
Arrangement fee | የብድር ማመቻቻ ክፍያ | ብድሩ ሲፈቀድ ለባንክ የሚከፈል የአንድ ጊዜ ክፍያ።
Commitment fee | ባልወጣ ብድር ላይ ክፍያ | ለተፈቀደ ግን ላልወጣ ብድር የሚከፈል።
Debt service | የዕዳ ክፍያ | በአንድ ጊዜ የሚከፈል ወለድና ዋና ገንዘብ።
CFADS | ለዕዳ ክፍያ የሚገኝ ገንዘብ | ከሥራ የሚገኝ የተጣራ ገንዘብ ብድር ከመክፈሉ በፊት።
DSCR | የዕዳ ክፍያ ሽፋን ጥምርታ | CFADS ለዕዳ ክፍያ ሲካፈል፤ 1.30x ማለት ለ1 ብር ክፍያ 1.30 ብር ገቢ።
LLCR | የብድር ዘመን ሽፋን ጥምርታ | በቀሪው የብድር ዘመን የገንዘብ ፍሰት የአሁን ዋጋ ለብድሩ ቀሪ ሲካፈል።
ICR | የወለድ ሽፋን | EBITDA ለወለድ ወጪ ሲካፈል።
Gearing | የብድር ድርሻ | ብድር ከጠቅላላ ገንዘብ (ብድር + ካፒታል) ያለው ድርሻ።
Covenant | የብድር ውል ግዴታ | ባንኩ የሚጠይቀው ዝቅተኛ ገደብ (ለምሳሌ DSCR ≥ 1.30x)።
DSRA | የዕዳ ክፍያ መጠባበቂያ ሂሳብ | ለወደፊት የዕዳ ክፍያ በባንክ የሚያዝ ገንዘብ።
Cash sweep | ትርፍ ገንዘብ ለብድር | ከሽያጭ የሚገኝን ገንዘብ ከፊሉን ብድር ቀድሞ ለመክፈል ማዋል።
Profit & loss (P&L) | የትርፍና ኪሳራ መግለጫ | በዓመቱ የተገኘ ገቢ፣ ወጪና ትርፍ።
Balance sheet | የሀብትና ዕዳ መግለጫ | በዓመቱ መጨረሻ ያለ ሀብት፣ ዕዳና የባለቤት ሀብት።
Cash flow statement | የጥሬ ገንዘብ ፍሰት መግለጫ | የገባና የወጣ ጥሬ ገንዘብ።
EBITDA | ከወለድ፣ ግብርና እርጅና በፊት ትርፍ | የሥራ ትርፍ ከወለድ፣ ግብርና የእርጅና ቅናሽ በፊት።
Depreciation | የእርጅና ቅናሽ | የንብረት ዋጋ በአገልግሎት ዘመኑ ተከፋፍሎ ወጪ መሆኑ።
Inventory (IAS 2) | ለሽያጭ የተያዘ ንብረት | ለመሸጥ የተሠሩ ቤቶች/ሱቆች ወጪ።
Investment property (IAS 40) | ለኪራይ የተያዘ ንብረት | ለኪራይ ገቢ የሚያዝ ሕንፃ ክፍል።
Owner-occupied property (IAS 16) | ባለቤቱ የሚጠቀምበት ንብረት | ባለቤቱ ራሱ የሚኖርበት ወይም የሚሠራበት ክፍል።
Contract liability (IFRS 15) | ከደንበኞች የተቀበለ ቅድሚያ | ገቢ ሳይታወቅ ከገዢዎች የተቀበለ ገንዘብ (ዕዳ)።
Revenue recognition | የገቢ ዕውቅና | ገቢ በሂሳብ መዝገብ የሚመዘገብበት ጊዜ (በርክክብ ወይም በሂደት)።
Corporate income tax (CIT) | የንግድ ሥራ ገቢ ግብር | በኩባንያ ትርፍ ላይ የሚከፈል ግብር።
Tax loss carry-forward | ኪሳራን ማሸጋገር | የአንድ ዓመት ኪሳራ የሚቀጥሉትን ዓመታት ግብር እንዲቀንስ ማድረግ።
Deferred tax | የዘገየ ግብር | በሂሳብና በግብር ሕግ ልዩነት ምክንያት ወደፊት የሚከፈል ወይም የሚቀነስ ግብር።
VAT | ተጨማሪ እሴት ታክስ (ተ.እ.ታ) | በዕቃና አገልግሎት ሽያጭ ላይ የሚጣል ታክስ።
Withholding tax | ተቀናሽ ግብር | ክፍያ ሲፈጸም ተቀንሶ ለመንግሥት የሚገባ ግብር።
Undistributed profits tax | ያልተከፋፈለ ትርፍ ግብር | ያልተከፋፈለና ያልተዋለ ትርፍ ላይ የሚጣል ግብር።
Legal reserve | ሕጋዊ መጠባበቂያ | በንግድ ሕጉ መሠረት ከትርፍ የሚያዝ መጠባበቂያ።
Dividend | የትርፍ ድርሻ | ለባለአክሲዮኖች የሚከፈል ትርፍ።
Net present value (NPV) | የተጣራ የአሁን ዋጋ | የወደፊት ገንዘብ ወደ ዛሬ ዋጋ ተቀይሮ ሲደመር።
Internal rate of return (IRR) | የውስጥ ተመላሽ መጠን | NPV ዜሮ የሚሆንበት ዓመታዊ ተመላሽ መቶኛ።
MOIC (equity multiple) | የካፒታል ብዜት | የተመለሰ ገንዘብ ለተዋጣ ገንዘብ ሲካፈል።
Discount rate | የቅናሽ መጠን | የወደፊት ገንዘብን ወደ ዛሬ ዋጋ ለመቀየር የሚጠቅም መቶኛ።
Cost of equity | የባለቤት ካፒታል ወጪ | ባለሀብቱ ከገንዘቡ የሚጠብቀው ዝቅተኛ ተመላሽ።
Hurdle rate | ዝቅተኛ ተፈላጊ ተመላሽ | ፕሮጀክቱ አዋጭ ለመባል ሊደርስበት የሚገባ IRR።
Payback period | የመመለሻ ጊዜ | የተዋጣው ገንዘብ ተመልሶ የሚያልቅበት ጊዜ።
Profit on cost | ትርፍ ከወጪ አንጻር | (GDV − TDC) ÷ TDC።
Development margin | የልማት ትርፍ ህዳግ | (GDV − TDC) ÷ GDV።
Yield on cost | ከወጪ አንጻር ዓመታዊ ገቢ | የተረጋጋ NOI ለተያዘው ንብረት ወጪ ሲካፈል።
Terminal value | የመጨረሻ ዋጋ | በ10ኛው ዓመት መጨረሻ የንብረቱ የተገመተ ዋጋ።
Exit cap rate | የመውጫ ካፕ ሬት | NOI ለንብረት ዋጋ የሚካፈልበት መቶኛ (ዋጋ = NOI ÷ ካፕ ሬት)።
Impairment (IAS 36) | የንብረት ዋጋ መቀነስ | የንብረቱ ጥቅም ዋጋ ከመዝገብ ዋጋው ሲያንስ።
Affordability | የመክፈል አቅም | ወርሃዊ ክፍያ ከቤተሰብ ገቢ ያለው ድርሻ።
Retention | የኮንትራክተር ማስያዣ | ሥራው በትክክል እስኪጠናቀቅ ከኮንትራክተሩ ክፍያ የሚያዝ መቶኛ።
Working capital | የሥራ ማስኬጃ ካፒታል | ተሰብሳቢ፣ ተከፋይና መሰል የአጭር ጊዜ ሂሳቦች።
Non-controlling interest (NCI) | አናሳ ባለድርሻ | መሬትን በዓይነት ያዋጣ አጋር ድርሻ።
Land lease | የመሬት ሊዝ | የከተማ መሬትን ለተወሰነ ዘመን በክፍያ የመጠቀም መብት።
Circularity | ዙሪያ-ጥገኛ ቀመር | ቀመር በራሱ ውጤት ላይ ሲመሠረት የሚፈጠር ችግር፤ በዚህ ሞዴል የለም።
Checks | ማረጋገጫዎች | ሞዴሉ በትክክል መሥራቱን የሚፈትሹ ራስ-ሰር ፈተናዎች።
Verdict | ውሳኔ | አዋጭ / በድንበር ላይ / አዋጭ አይደለም የሚል የዳሽቦርድ መልስ።
Track | መንገድ (የሞዴል ክፍል) | በመጀመሪያ ገጽ የሚመረጠው ክፍል፡ የግል መኖሪያ ቤት ወይም የንግድ ፕሮጀክት።
Rent roll / space schedule | የኪራይ መዝገብ / የቦታ ዝርዝር | እያንዳንዱ የሚከራይ ወይም የሚሸጥ ቦታ፣ ስፋቱ፣ ዋጋውና ኪራዩ የተዘረዘረበት ሰንጠረዥ (ገጽ 13)።
Net-to-gross ratio | የተጣራ/ጠቅላላ ስፋት ጥምርታ | ሊከራይ ወይም ሊሸጥ የሚችለው ስፋት ከጠቅላላው የወለል ስፋት ያለው ድርሻ።
Lease-up | የተከራዮች መሙላት ጊዜ | ሕንፃው ከተጠናቀቀ በኋላ ተከራዮች ቀስ በቀስ የሚገቡበት የመጀመሪያ ዓመታት።
Operator lease (hotel) | የሆቴል ኦፕሬተር ኪራይ | ሆቴሉን የሚያስተዳድር ድርጅት ለባለቤቱ ከገቢው መቶኛ ወይም ዝቅተኛ ዋስትና ያለው ኪራይ የሚከፍልበት ውል።
Turnover rent | ከገቢ የሚሰላ ኪራይ | ከተከራዩ ጠቅላላ ሽያጭ ወይም ገቢ በመቶኛ የሚከፈል ኪራይ።
ADR (average daily rate) | አማካይ የቀን ክፍል ዋጋ | ለአንድ የተሸጠ የሆቴል ክፍል በአማካይ በቀን የሚገኝ ገቢ።
Pre-opening cost | ከመክፈቻ በፊት ወጪ | ሕንፃው ሥራ ከመጀመሩ በፊት የሚወጣ የሥልጠና፣ የማስተዋወቂያና የማስጀመሪያ ወጪ፤ እንደ ወጪ ይመዘገባል።
Confidence (input) | የግብዓት እርግጠኝነት | ለእያንዳንዱ ግብዓት ምን ያህል እርግጠኛ እንደሆኑ የሚያሳይ ምልክት (ከፍተኛ/መካከለኛ/ዝቅተኛ)።
What-if dial | የ'ቢሆንስ' ማስተካከያ | በገጽ 52 ያለ ሕዋስ፤ አንድን ነጂ በመቶኛ ቀይረው ውጤቱን ወዲያውኑ ለማየት።
Tornado chart | የቶርኔዶ ሠንጠረዥ | የትኛው ግምት በውጤቱ ላይ ትልቁን ተፅዕኖ እንዳለው በቅደም ተከተል የሚያሳይ ሠንጠረዥ።
Affordability | የመክፈል አቅም | ወርሃዊ የብድር ክፍያዎች ከቤተሰብ ገቢ ያላቸው ድርሻ።
Funding gap | የገንዘብ ክፍተት | ቁጠባ፣ የቤተሰብ መዋጮና ብድር ሸፍነው የማይጨርሱት ቀሪ ወጪ።

## Lists (hidden)
L_TRACK | L_MODE | L_DATASET | L_PDATASET | L_SCEN | L_FINISH | L_YN | L_SPACE | L_CONF | L_METHOD | L_LOC | L_LAND | L_SCURVE | L_DRAW | L_RATETYPE | L_GRACE | L_REPAY | L_FREQ | L_REV | L_OPEXM | L_EXIT | L_BTYPE | L_IDC | L_PLAND
Private residence – cost estimate & home loan · የግል መኖሪያ ቤት | 1 – Build-to-Sell · ለሽያጭ መገንባት | 1 – My project · የእኔ ፕሮጀክት | 1 – My house · የእኔ ቤት | 1 – Base · መሠረታዊ | Basic | Yes | Retail | High | Rate x area | Addis Ababa | Lease (cash) | S-curve (sigmoid) | Equity first | Fixed | Interest-only (paid) | Annuity (PMT) | Monthly | Point in time (handover) | % of rent | Exit cap rate | G+0 villa | Paid monthly during construction | Already owned – no cost
Commercial project – full profitability · የንግድ ፕሮጀክት | 2 – Build-to-Rent / Hold · ለኪራይ መገንባት | 2 – SAMPLE 1: B+G+8 mixed-use · ምሳሌ 1 | 2 – SAMPLE: G+1 family house · ምሳሌ ቤት | 2 – Upside · ብሩህ | Standard | No | Office | Medium | Lump sum (BOQ) | Regional town | Already owned (in-kind by owner) | Linear | Pro-rata | Variable path by year | Capitalised | Equal principal | Quarterly | Over time (% complete) | ETB per m2 per year | EBITDA multiple | G+1 | Capitalised into the loan | Buying / lease payment in the build period
| 3 – Mixed (sell part, hold part) · ቅይጥ | 3 – SAMPLE 2: B+G+10 trade centre & hotel · ምሳሌ 2 |  | 3 – Downside · አስቸጋሪ | Premium |  | Residential | Low |  |  | Partner in-kind (NCI) | User % row |  |  |  | Balloon % | Annual |  |  |  | G+2
|  |  |  | 4 – Lender case · የባንክ |  |  | Showroom / wholesale | [13 empty] | G+3
Food & beverage
Warehouse / storage
Hotel (operator lease)
Parking
Owner-occupied
Rent-free / public service
Other